## Dashboard
Today's Notora Due Dates | [8 empty] | Today's S2A Due Dates
Today's Date |  | 2026-09-10 | [6 empty] | Today's Date | 2026-09-10
50% Design |  | 100% IFR | IFP | IFC |  |  |  |  | 50% Design | 100% IFR | IFP | IFC
Nothing Due |  | - | - | - |  |  |  |  | - | - | - | -
Nothing Due |  | Nothing Due | Nothing Due | Nothing Due |  |  |  |  | Nothing Due | Nothing Due | Nothing Due | Nothing Due
Notora Due Dates
Todays Date |  | 2026-09-10
| 2026-09-10 | 2026-09-11 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25
50% Design | bar: 2026-09-10 to 2026-09-25
100% IFR | bar: 2026-09-10 to 2026-09-25
IFP | bar: 2026-09-10 to 2026-09-25
IFC | bar: 2026-09-10 to 2026-09-25
S2A Due Dates
Todays Date | 2026-09-11: 2026-09-10
| 2026-09-10 | 2026-09-11 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25
Floor Plans | bar: 2026-09-10 to 2026-09-25
50% Design | bar: 2026-09-10 to 2026-09-25
100% IFR | bar: 2026-09-10 to 2026-09-25
IFP | bar: 2026-09-10 to 2026-09-25
IFC | bar: 2026-09-10 to 2026-09-25
Iss Record | bar: 2026-09-10 to 2026-09-14; 2026-09-16 to 2026-09-25
Past Due: | 1D | 2D | 3D | 4D | 5D | 6D | 7D | 8D | 9D | 10D | 11D | 12D
| - | - | - | - | - | - | - | - | - | - | - | -

## Info Needed
50% Design
Address or Lat/Long
Approved Floorplans
Headend Location
Parent or Child Site?
Greenfield site?
Project Specific Notes
90/100% CAD Set
Packaging Preferences
CAD Titleblock with Client Logo Images (dwg & jpgs)
CAD Floor Plans of the building and The Site Plan or Survey (dwg files)
Cover Sheet if/when available (dwg or pdf)
Submission Date for Plans
DAS Design Package in (pdf & ibwave)
PS Design Package in (pdf & ibwave)
ROIP Design Package (in pdf & ibwave)
DAS BOM – (Excel File)
PS BOM – (Excel File)
ROIP BOM – (Excel File)
IFP CAD Set
Updated Titleblock (dwg)
Any redlines/instructions for changes
IFC CAD Set
Updated Titleblock (dwg)
Any redlines/instructions for changes

## Design-formattingv2 (hidden)
NAME | LOCATION | A/E | Phase (Design or CA) | AE-PM Name | AE-PM Contact | S2 PM | Project Status | Floorplans Received | Floor Plans Needed | 50% IFR - Notora | 50% IFR - AE | 100% IFR - Notora | 100% IFR - AE | IFP - Notora | IFP - AE | IFC | Project Start | Submittal | Substantial Completion | Issue For Record | Completion | Commissioning | Action Item Needed | Comments
ATL06 | Atlanta | Highland Associates | Design | Christopher Ritchie | critchie@ha-ny.com |  | A | Supposed to be 4/7/2023 |  | Complete |  | No Notora | 10/3/2023- Complete | No Notora | 10/24/2023-Complete | 2/12/2024-complete | [6 empty] | Need to track down: Floor Plans, AHJ (Authorities having jurisdiction contact), enforced code | Location: East Point GA Lat Long: 33*38'30"N, 84*30'59"W FloorPlans to be updated Friday the 7th
ATL07 | [6 empty] | A |  | 5/13/2024-complete | 2024-05-23 | 2024-05-24 |  | 2024-06-25
AVC02 | [6 empty] | A |  |  |  | 3/25/2024-Complete |  | 4/29/2024-complete |  | 2024-05-15 | [5 empty] | Need as-builts/testing for AVC01. Some weirdness w AVC01 |  | DAS and Public safety Proposal needed.
AVC17 | SOUTH HILL, VA | Highland Associates | Design | Hector Hernandez | hhernandez@ha-ny.com | Bram Wathen | A | 2023-02-24 |  | 3/8/2023 - complete | 3/20/2023- complete | 4/17/2023 - complete | 4/24/2023 - complete | 6/2/2023 - complete | 6/5/2023 - complete | 8/3/2023-Complete | [6 empty] | Update the IFC Date | 3 Different Issues. Need to confrim if power supply for fiber optical master is required. Need ROIP specs, Site Heat map.
AVC18 | SOUTH HILL, VA | Highland Associates | Design | Hector Hernandez | hhernandez@ha-ny.com | Bram Wathen | A | 2023-03-03 |  | 3/15/2023 - complete | 3/20/2023 - complete | 4/17/2023 - complete | 4/24/2023 - complete | 6/2/2023 - complete | 6/5/2023 - complete | 8/3/2023-Complete | [6 empty] | Update the IFC Date | Review Drawings prior to IFP
AVC43 | SOUTH HILL, VA | Swanson Rink | Design | Ryan Sims | RSims@swansonrink.com |  | C | 2022-11-09 |  | Complete | 11/21/2022 - Complete | Complete |  |  | Complete | [7 empty] | 2x2 cabinet
CCO07 | [6 empty] | A |  |  | 8/23/2023 - complete | 9/7/2023 - complete | No Notora | 10/19/2023-Complete | No Notora | 11/7/2023-Complete
CHI05 | Chicago | [6 empty] | 2023-05-19 |  | 5/26/2023 - complete | [5 empty] | 2024-04-02 |  |  |  | No Notora |  |  |  | We need NT proposal
CHI11 | Chicago | [6 empty] | X |  | 5/26/2023 - complete |  |  |  |  | 3/11/2024-Complete | [8 empty] | We need NT proposal
CHI22 | Chicago | [5 empty] | A | [7 empty] | 1/11/2024-COMPLETE | 1/19/2024-complete | [7 empty] | IFP DRB17 Print
CLT04 | North Carolina | Olson | Design | David Barber | dbarber@olsson.com | Bram Wathen | A | 2023-01-31 |  | 2/16/2023 - complete | 2/16/2023 - complete | 4/12/2023 -complete | 4/26/2023 - complete | 2/20/2024-Complete | 2/21/2024-Complete | [7 empty] | Title block updates. Request sent to Stephen 5/11 | Get address and find cell towers
CLT10 | North Carolina | Olsson | Design | Meg Plank | mplank@olsson.com |  | A | X |  | 6/30/2023 - Complete | 7/06/2023 - Complete | 8/25/2023 - complete | 8/31/2023-Complete | 2/20/2024-Complete | 2/21/2024-Complete | [7 empty] | Site Plans & Floor Plans | Project Kick off June 1st.
CLT11 |  | Olson | Design | David Barber | dbarber@olsson.com | Bram Wathen | P
CLT17 |  | Olson | Design | David Barber | dbarber@olsson.com | Bram Wathen | P | X |  | 2023-11-10 | 11/16/2023-complete | 2023-12-20 | 1/3/2024-Complete |  | 2/14/2024-Complete | [8 empty] | Not doing the CADs for this one
CPQ03 | BRAZIL | Deerns | Design | Gabriel Pereira | gabriel.pereira@deerns.com |  | C | [8 empty] | 2023-10-16
CPQ07 | BRAZIL | Deerns | Design | Gabriel Pereira | gabriel.pereira@deerns.com |  | C | X |  | 2/17/2023 - complete | 1/11/2023 - Complete | [11 empty] | Need updated IFR Date, if we're doing the CAD's | 1/25: emailed Kelwin asking for info
CPQ08 | [10 empty] | 1/8/2024-Complete
CPQ11 | BRAZIL | Deerns | Design | Gabriel Pereira | gabriel.pereira@deerns.com |  | C | X |  | Complete
CYS17 | Cheyanne | Jacobs | Design | Kristin McCue | Kristin.McCue@jacobs.com |  | C |  |  |  |  | Complete | 1/24/2023-complete | complete | complete | [7 empty] | IFP from WT | 2/6/2023: WT indicates a 2/13 delivery date. 2/6/2023: emailed WT requesting IFP update 1/24: recieved updated design fromWT, uploaded 1/20: recieved design from David. Emailed AE the drawing list and uploaded files to AE and S2 1/19: This is a 'WT' site, emailed Davide requesting design update 1/18: sent philip design pkg 4 email 1/13/23: emailed Kristen requesting update
DFW20 | [15 empty] | 3/8/2024-complete
DSM12 | DES MOINES | Burns & McDonnell | Design | Kylie Hornbeck | khornbeck@burnsmcd.com |  | C | [15 empty] | Nick coordinating with AE
DSM14 | DES MOINES | Burns & McDonnell | Design | Kylie Hornbeck | khornbeck@burnsmcd.com |  | C | [15 empty] | Nick coordinating with AE
DSM15 | DES MOINES | Burns & McDonnell | Design | Kylie Hornbeck | khornbeck@burnsmcd.com |  | C | [15 empty] | Need Floorplans & Schedule - Nick to follow up with AE
DSM40 | DES MOINES | Burns & McDonnell | Design | Kylie Hornbeck | khornbeck@burnsmcd.com |  | C | [8 empty] | 5/8/2024-Complete | [6 empty] | Nick coordinating with AE
DSM41 | DES MOINES | Burns & McDonnell | Design | Kylie Hornbeck | khornbeck@burnsmcd.com |  | C | [15 empty] | Nick coordinating with AE
EAT04 | WEANATCHEE, WA | ESD | Design | Chad Mendell | cmendell@esdglobal.com |  | C |  |  | Complete | 12/1/2022 - Complete | Complete | 1/12/2023 - Complete | 1/19/23-complete | 1/26/2023-complete | 5/31/2023-Complete | [7 empty] | 2/6/23: IFC is TBD no update1/25: recieved updated design from Philip, uploaded to AE and S2 1/19: recieved updated design from Philip, uploaded to BIM and S2 1/19: uploaded specs, requested IFP design from Philip 1/18: sent IFP instructions to Notora
EAT05 | WEANATCHEE, WA | ESD | Bid | Chad Mendell | cmendell@esdglobal.com |  | A | 2023-04-17 |  | 5/3/2023 - complete | 4/20/2023 - complete | 5/19/2023 - complete | 5/25/2023 - complete | complete | 6/13/2023 - complete | 3/5/2024-Complete | [6 empty] | Notora Internal review return 5/1-5/2 | May
EAT06 | [6 empty] | A |  |  | 8/9/2023--Complete | 8/1/2023-Complete |  | 9/7/2023 - complete |  | 9/26/2023-Complete
EAT09 | [6 empty] | A | 8/16/2023? |  |  |  |  | 9/7/2023 - complete |  | 9/26/2023-Complete
EAT12 | WEANATCHEE, WA | ESD | Design | Chad Mendell | cmendell@esdglobal.com |  | A |  |  | 2/20/2023-complete | 2/23/2023-complete | 3/20/2023 - complete | 3/9/2023 - complete | complete | 4/6/2023 - complete | 3/21/2024 Complete | [6 empty] | Change notes in the Public Safety. Cover the L1 containment unless AHJ approves alternate means and methods. Pull box detail | 2/15: in internal review 2/15: requested update from Notora 2/3/23: floor plan delivered to Notora 2/1: Harold got floorplans today; 1/18: Design is resuming with meeting 1/30
EAT13 | WEANATCHEE, WA | ESD | Design | Chad Mendell | cmendell@esdglobal.com |  | A | X |  | 6/14/2023 - complete | 6/15/2023 - complete | 7/18/2023-Complete | 7/20/2023-Complete | 8/1/2023-Complete | 8/2/2023-Complete | 4/9/2024-complete | [7 empty] | Starting the week of 5/8
EAT14 | WEANATCHEE, WA | [5 empty] | A | X |  | 9/27/2023 - complete | 9/21/2023 - Complete | 10/27/2023-complete | 11/28/2023-Complete |  | 12/14/2023 - Complete | 2024-05-15 | [6 empty] | Battery backups, near far, L1 containement?
FTY01 | [15 empty] | 4/25/2024-Complete
FTY02 | GEORGIA | Morrison Hershfield | Bid | Lee Percy | LPercy@morrisonhershfield.com |  |  |  | 2023-08-01 | 8/15/2023-Complete | 2023-08-22 | 9/8/2023 - complete | 9/12/2023 - complete | 10/10/2023 - Complete | 10/12/2023- Complete | [7 empty] | Need to update the BOM to comba unit.
FTY03 | [10 empty] | 5/9/2024-Complete |  | 2024-06-03 |  | 2024-07-01
IAD05 | [15 empty] | TBD
IAD12 | LEESBURG, VA | Syska | Design | Liam Wall | lwall@syska.com |  | A |  |  | Complete | 2/22/2023 - Complete |  | 3/29/2023 - Complete |  | 2023-04-26 | 2023-05-30
IAD13 | LEESBURG, VA | Syska | Design | Liam Wall | lwall@syska.com |  | A |  |  | Complete | Complete | Complete | 2/9/2023 - Complete | Complete | 3/24/2023 - Complete | 2023-05-04 | [6 empty] | Riser Info - no IFR yet
IAD14 | LEESBURG, VA |  | Bid | TBD |  |  | A
LVL06 | Drawing Review |  | Design | Fran Carlos | fclaros@swansonrink.com |  | A | 2023-03-02 |  | 3/17/2023 - complete | 3/21/2023 - complete |  | 2023-04-25 | 2023-01-05 | 2023-01-05 | [7 empty] | 4/26/2023: Need to adjust to keep equipement in cells 1-3. See email. | Meet with Preston - make sure he updated prints with S2A changes
LVL07 | [6 empty] | A |  |  | Complete | 8/21/2023-Complete | No Notora | 9/29/2023--Complete | No Notora | 10/19/2023-Complete | 2/19/2024-Complete
LVL11 | BOYDTON, VA | Swanson Rink | Design | Ryan Sims | RSims@swansonrink.com |  | C |  |  | Complete | 1/23/2023 - Complete | 2/20/2023 - Complete | 2/27/2023 - Complete |  | 2023-03-22 | 2023-05-15 | [7 empty] | 2/1: Emailed James for desgin review & emailed Preson for titleblock, etc
LVL12 | [7 empty] | X |  |  | 12/21/2023-Complete |  | 2/5/2024-Complete |  | 2024-02-23 | [7 empty] | Need to provision for off-air as a backup if needed. Need antenna structure to support it.
LVL13-14 | [8 empty] | 2024-03-25 | 3/28/2024-Complete | 2024-04-15 | 2024-05-13 | 2024-05-14 |  | 2024-06-10 | [5 empty] | Loop clark into dicusscion. We will go back to LVL08
LYH03 | BOYDTON, VA | Highland Associates | BID | Hector Hernandez | hhernandez@ha-ny.com |  | C | [15 empty] | Need Floorplans & Schedule
LYH10 | BOYDTON, VA | Highland Associates | Design | Hector Hernandez | hhernandez@ha-ny.com | Bram Wathen | P |  |  | Complete | 11/29/2022 - Complete | Complete | complete | Complete | 2023-03-16 | 6/28/2023 - complete | [6 empty] | IFC Pushed to mid july--Will follow up later 04/28/2023 | 4/18 Specs updated and sent to Paul Duffy for upload. Need to upload to BIM360
MNZ01 | MANASSAS, VA | Sysksa | Design | Christopher Lay | clay@syska.com |  | A | X | [15 empty] | 1/26: emailed Chris asking for info
MNZ03 | MANASSAS, VA | Sysksa | Design | Christopher Lay | clay@syska.com |  | A | [7 empty] | 3/3/2023 - Complete | Mid June
MNZ04 | [10 empty] | 4/23/2024-Complete |  | 2024-06-13 |  | 2024-07-03
MNZ05 | [8 empty] | 2024-05-02 |  | 2024-05-23 |  | 2024-07-11
MWH08 | Quincy | [5 empty] | A | X |  |  | 1/19/2024-Complete |  | 3/24/2024-complete
PHX14
PHX16 | PHOENIX, AZ | [6 empty] | X
PHX17 | PHOENIX, AZ | [6 empty] | X
PHX15 | PHOENIX, AZ | [6 empty] | X | 2024-05-28 | Rough Date | 2024-06-18
PHX61 | [9 empty] | 11/9/2023-Complete |  |  | 11/16/2023-Complete
PHX71 | PHOENIX, AZ | Jacobs | Design | Blake Giles | Blake.Giles@jacobs.com |  | C | X | [14 empty] | Repackaging Site
PHX72 | PHOENIX, AZ | Jacobs | Design | Blake Giles | Blake.Giles@jacobs.com |  | A |  | 2023-02-28 | Complete | 2023-03-21 |  |  |  | 2023-06-12 | [7 empty] | QA Form, SPEC, Review A/E Sumittal | IFP Pushed back to 5/23
PHX73 | PHOENIX, AZ | [7 empty] | 2023-08-03 | 8/11/2023 - complete | 2023-08-24 | No Notora | 2023-09-21 | No Notora | 10/17/2023-Complete
PHX74 | PHOENIX, AZ | [5 empty] | A | X |  | 10/20/2023-Complete | 11/9/2023-Complete | SPEC Needed | 2023-12-08 | No Notora | 2024-01-10
PHX81 | PHOENIX, AZ | Jacobs | Design | Blake Giles | Blake.Giles@jacobs.com |  | C |  |  | Complete | 11/10/2022 - Complete | Complete | 12/9/2022 - Complete | 1/25/2023-complete | 1/30/2023-complete | 3/11/2024-Complete |  |  |  |  | No Notora |  | Notora Needs IFC Date | 1/26: recieved package from WT, uploaded. 1/20: emailed David at WT requesting package 1/19: specs sent to PM
PHX82 | PHOENIX, AZ |  | Design |  |  | Bram Wathen | A |  | 2023-04-06 |  | 2023-04-27 | 2023-06-02 | 2023-06-06 |  | 2023-06-29 | [7 empty] | 4/18 Harold to Review Design. SPECS due June 1 | We need to review 50% set
PHX83 | PHOENIX, AZ
SAT14 | [15 empty] | 2024-05-16
SAT15 | SAN ANTONIO, TX | Page Southerland Page Inc. | Design | Lauren Alexander | lalexander@pagethink.com |  | A | X |  | Complete | Complete | Complete | 12/14/2022 - Complete | No NT | 2024-05-16 | 2023-04-03 | [6 empty] | IFC date determined after permitting
SAT17 | [7 empty] | X |  |  | 3/27/2024-Complete |  | 5/9/2024-Complete |  | 2024-06-06
SAT16 | [7 empty] | X |  | 10/26/2023 - complete | 11/29/2023-Complete |  | 1/9/2024-Complete |  | 2/15/2024-Complete
SAT40 | SAN ANTONIO, TX | Page Southerland Page Inc. | Design | Lauren Alexander | lalexander@pagethink.com |  | A |  |  | Complete | 11/30/2022 - Complete | Complete | 1/20/2023 - Complete | 2/15/2023 - Complete | 2023-02-03 | 8/2/2023--Complete | [6 empty] | Notora Needs Updated IFP Titleblock
SAT80/81 | SAN ANTONIO, TX | Page Southerland Page Inc. | Design | Alan McClung | amcclung@pagethink.com |  | A |  |  | Complete | Complete | Complete | 7/11/2023--Complete | [9 empty] | Notora Needs Floorplans & IFC Dates
SAT82 | [7 empty] | X |  | 10/31/2023 - complete | 12/4/2023-Complete |  | 1/16/2024-Complete |  | 2/6/2024-Complete | 2023-02-23
SAT90 | [7 empty] | X | [6 empty] | 2/15/2024-Complete
SAT89 | SAN ANTONIO, TX | [5 empty] | A | X |  | 10/25/2023 - complete | 11/15/2023-Complete | Stephen To deliver | 1/4/2024-Complete |  | 2/15/2024-Complete
SJC02 | SAN JOSE, CA | Jacobs | Design | Kristin McCue | Kristin.McCue@jacobs.com |  | A |  |  | Complete | Complete | 9/8/2023 - complete | 9/14/2023 - complete | 10/20/2023-Complete | 2024-06-15 | [8 empty] | Project is on hold while "they" are working through the IFP comments
SJC04 | SAN JOSE, CA | Jacobs | Bid | Kristin McCue | Kristin.McCue@jacobs.com |  | P |  | 2024-06-27 |  | 2024-07-18 |  | 2024-09-12
YQB01/02 | QUEBEC CITY |  |  |  |  | Bram Wathen | A | X |  |  |  |  | 7/11/2023-Complete | 8/7/2023 - Complete | 10/4/2023 - complete | 2/27/2024-complete
YQB04 | QUEBEC CITY |  |  |  |  | Bram Wathen | A | X |  | 3/3/2023 - complete | 3/3/2023 - complete | 3/16/2023- complete | 3/20/2023 - complete | 6/9/2023 - complete | 6/15/2023 - complete | 11/15/2023-complete
YQB06 | QUEBEC CITY | [5 empty] | A | X |  | 5/1/2023 - complete | 4/24/2023 - complete | 6/22/2023--Complete | 6/27/2023--Complete | No Notora | 9/25/2023 - Complete | 2/2/2024-Complete | [6 empty] | Site Plans email sent.
YQB11 | QUEBEC CITY | [5 empty] | A | X |  | 5/8/2023 - complete | 5/12/2023 - complete | 7/1/2023 - complete | 7/25/2023--Complete | 2023-09-29 | 12/12/2023-Complete | 4/9/2024-Complete
YTO10 | Toronto |  | Bid | Saeed Akbari | SAkbari@morrisonhershfield.com |  | A
YTO11 | Toronto | Morrison Hershfield | Design | Saeed Akbari | SAkbari@morrisonhershfield.com |  | A | X |  | Complete | 9/26/2022 - Complete | Complete | 2/3/2023 - Complete | Complete | 8/8/2023 - Complete | 2024-02-16 |  |  |  |  | Need to update note & Site plan |  | Just the Drawings-Update Dates (7-10) | We will not be submitting a 50% design (or 100% draft as they call it); once we get comments back from Microsoft on YTO40, then they will have us make the same changes to YTO11 and then we will submit YTO11
YTO14 | Toronto | Morrison Hershfield | Design | Saeed Akbari | SAkbari@morrisonhershfield.com | Bram Wathen | A | X |  | 5/3/2023 - complete | 8/26/2023- Complete | 6/13/2023 - complete | tbd |  |  | TBD |  |  |  |  | Need to update note & Site plan |  | Set up meeting w Jim + Harold to discuss the Colo 5 Elec 3 Riser room for fiber. | Guard house is the same as YTO11 & YTO40. Talk to Mianna for updated plans. 100 % changed to October 16
YTO40 | Toronto | Morrison Hershfield | Design | Saeed Akbari | SAkbari@morrisonhershfield.com |  | A | X |  | Complete | Complete | Complete | 1/5/2023 - Complete | 2/14/2023 - Completed | 2024-05-23 | TBD |  |  |  |  | Need to update antenna note & Site plan |  | Need IFC Dates | AE should receive comments back from Microsoft on 1/16 and then we will have 5 days to make changes and issue 100% design
Formulas:
Floor Plans Needed = IFERROR(WORKDAY(Table145[[#This Row],[50% IFR - AE]],-15), " ")
Note on E23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FYI... per emails in March, I think Brandi Sauter took over as PM.

## Design-formattingv1 (hidden)
NAME | LOCATION | A/E | Phase (Design or CA) | AE-PM Name | AE-PM Contact | S2 PM | Project Status | Floorplans Received | Floor Plans Needed | 50% IFR - Notora | 50% IFR - AE | 100% IFR - Notora | 100% IFR - AE | IFP - Notora | IFP - AE | IFC | Project Start | Submittal | Substantial Completion | Issue For Record | Completion | Commissioning | Action Item Needed | Comments
ATL06 | Atlanta | Highland Associates | Design | Christopher Ritchie | critchie@ha-ny.com |  | A | Supposed to be 4/7/2023 |  | Complete |  | No Notora | 10/3/2023- Complete | No Notora | 10/24/2023-Complete | 2/12/2024-complete | [6 empty] | Need to track down: Floor Plans, AHJ (Authorities having jurisdiction contact), enforced code | Location: East Point GA Lat Long: 33*38'30"N, 84*30'59"W FloorPlans to be updated Friday the 7th
ATL07 | [6 empty] | A |  | 5/13/2024-complete | 2024-05-23 | 2024-05-24 |  | 2024-06-25
AVC02 | [6 empty] | A |  |  |  | 3/25/2024-Complete |  | 4/29/2024-complete |  | 2024-05-15 | [5 empty] | Need as-builts/testing for AVC01. Some weirdness w AVC01 |  | DAS and Public safety Proposal needed.
AVC17 | SOUTH HILL, VA | Highland Associates | Design | Hector Hernandez | hhernandez@ha-ny.com | Bram Wathen | A | 2023-02-24 |  | 3/8/2023 - complete | 3/20/2023- complete | 4/17/2023 - complete | 4/24/2023 - complete | 6/2/2023 - complete | 6/5/2023 - complete | 8/3/2023-Complete | [6 empty] | Update the IFC Date | 3 Different Issues. Need to confrim if power supply for fiber optical master is required. Need ROIP specs, Site Heat map.
AVC18 | SOUTH HILL, VA | Highland Associates | Design | Hector Hernandez | hhernandez@ha-ny.com | Bram Wathen | A | 2023-03-03 |  | 3/15/2023 - complete | 3/20/2023 - complete | 4/17/2023 - complete | 4/24/2023 - complete | 6/2/2023 - complete | 6/5/2023 - complete | 8/3/2023-Complete | [6 empty] | Update the IFC Date | Review Drawings prior to IFP
AVC43 | SOUTH HILL, VA | Swanson Rink | Design | Ryan Sims | RSims@swansonrink.com |  | C | 2022-11-09 |  | Complete | 11/21/2022 - Complete | Complete |  |  | Complete | [7 empty] | 2x2 cabinet
CCO07 | [6 empty] | A |  |  | 8/23/2023 - complete | 9/7/2023 - complete | No Notora | 10/19/2023-Complete | No Notora | 11/7/2023-Complete
CHI05 | Chicago | [6 empty] | 2023-05-19 |  | 5/26/2023 - complete | [5 empty] | 2024-04-02 |  |  |  | No Notora |  |  |  | We need NT proposal
CHI11 | Chicago | [6 empty] | X |  | 5/26/2023 - complete |  |  |  |  | 3/11/2024-Complete | [8 empty] | We need NT proposal
CHI22 | Chicago | [5 empty] | A | [7 empty] | 1/11/2024-COMPLETE | 1/19/2024-complete | [7 empty] | IFP DRB17 Print
CLT04 | North Carolina | Olson | Design | David Barber | dbarber@olsson.com | Bram Wathen | A | 2023-01-31 |  | 2/16/2023 - complete | 2/16/2023 - complete | 4/12/2023 -complete | 4/26/2023 - complete | 2/20/2024-Complete | 2/21/2024-Complete | [7 empty] | Title block updates. Request sent to Stephen 5/11 | Get address and find cell towers
CLT10 | North Carolina | Olsson | Design | Meg Plank | mplank@olsson.com |  | A | X |  | 6/30/2023 - Complete | 7/06/2023 - Complete | 8/25/2023 - complete | 8/31/2023-Complete | 2/20/2024-Complete | 2/21/2024-Complete | [7 empty] | Site Plans & Floor Plans | Project Kick off June 1st.
CLT11 |  | Olson | Design | David Barber | dbarber@olsson.com | Bram Wathen | P
CLT17 |  | Olson | Design | David Barber | dbarber@olsson.com | Bram Wathen | P | X |  | 2023-11-10 | 11/16/2023-complete | 2023-12-20 | 1/3/2024-Complete |  | 2/14/2024-Complete | [8 empty] | Not doing the CADs for this one
CPQ03 | BRAZIL | Deerns | Design | Gabriel Pereira | gabriel.pereira@deerns.com |  | C | [8 empty] | 2023-10-16
CPQ07 | BRAZIL | Deerns | Design | Gabriel Pereira | gabriel.pereira@deerns.com |  | C | X |  | 2/17/2023 - complete | 1/11/2023 - Complete | [11 empty] | Need updated IFR Date, if we're doing the CAD's | 1/25: emailed Kelwin asking for info
CPQ08 | [10 empty] | 1/8/2024-Complete
CPQ11 | BRAZIL | Deerns | Design | Gabriel Pereira | gabriel.pereira@deerns.com |  | C | X |  | Complete
CYS17 | Cheyanne | Jacobs | Design | Kristin McCue | Kristin.McCue@jacobs.com |  | C |  |  |  |  | Complete | 1/24/2023-complete | complete | complete | [7 empty] | IFP from WT | 2/6/2023: WT indicates a 2/13 delivery date. 2/6/2023: emailed WT requesting IFP update 1/24: recieved updated design fromWT, uploaded 1/20: recieved design from David. Emailed AE the drawing list and uploaded files to AE and S2 1/19: This is a 'WT' site, emailed Davide requesting design update 1/18: sent philip design pkg 4 email 1/13/23: emailed Kristen requesting update
DFW20 | [15 empty] | 3/8/2024-complete
DSM12 | DES MOINES | Burns & McDonnell | Design | Kylie Hornbeck | khornbeck@burnsmcd.com |  | C | [15 empty] | Nick coordinating with AE
DSM14 | DES MOINES | Burns & McDonnell | Design | Kylie Hornbeck | khornbeck@burnsmcd.com |  | C | [15 empty] | Nick coordinating with AE
DSM15 | DES MOINES | Burns & McDonnell | Design | Kylie Hornbeck | khornbeck@burnsmcd.com |  | C | [15 empty] | Need Floorplans & Schedule - Nick to follow up with AE
DSM40 | DES MOINES | Burns & McDonnell | Design | Kylie Hornbeck | khornbeck@burnsmcd.com |  | C | [8 empty] | 5/8/2024-Complete | [6 empty] | Nick coordinating with AE
DSM41 | DES MOINES | Burns & McDonnell | Design | Kylie Hornbeck | khornbeck@burnsmcd.com |  | C | [15 empty] | Nick coordinating with AE
EAT04 | WEANATCHEE, WA | ESD | Design | Chad Mendell | cmendell@esdglobal.com |  | C |  |  | Complete | 12/1/2022 - Complete | Complete | 1/12/2023 - Complete | 1/19/23-complete | 1/26/2023-complete | 5/31/2023-Complete | [7 empty] | 2/6/23: IFC is TBD no update1/25: recieved updated design from Philip, uploaded to AE and S2 1/19: recieved updated design from Philip, uploaded to BIM and S2 1/19: uploaded specs, requested IFP design from Philip 1/18: sent IFP instructions to Notora
EAT05 | WEANATCHEE, WA | ESD | Bid | Chad Mendell | cmendell@esdglobal.com |  | A | 2023-04-17 |  | 5/3/2023 - complete | 4/20/2023 - complete | 5/19/2023 - complete | 5/25/2023 - complete | complete | 6/13/2023 - complete | 3/5/2024-Complete | [6 empty] | Notora Internal review return 5/1-5/2 | May
EAT06 | [6 empty] | A |  |  | 8/9/2023--Complete | 8/1/2023-Complete |  | 9/7/2023 - complete |  | 9/26/2023-Complete
EAT09 | [6 empty] | A | 8/16/2023? |  |  |  |  | 9/7/2023 - complete |  | 9/26/2023-Complete
EAT12 | WEANATCHEE, WA | ESD | Design | Chad Mendell | cmendell@esdglobal.com |  | A |  |  | 2/20/2023-complete | 2/23/2023-complete | 3/20/2023 - complete | 3/9/2023 - complete | complete | 4/6/2023 - complete | 3/21/2024 Complete | [6 empty] | Change notes in the Public Safety. Cover the L1 containment unless AHJ approves alternate means and methods. Pull box detail | 2/15: in internal review 2/15: requested update from Notora 2/3/23: floor plan delivered to Notora 2/1: Harold got floorplans today; 1/18: Design is resuming with meeting 1/30
EAT13 | WEANATCHEE, WA | ESD | Design | Chad Mendell | cmendell@esdglobal.com |  | A | X |  | 6/14/2023 - complete | 6/15/2023 - complete | 7/18/2023-Complete | 7/20/2023-Complete | 8/1/2023-Complete | 8/2/2023-Complete | 4/9/2024-complete | [7 empty] | Starting the week of 5/8
EAT14 | WEANATCHEE, WA | [5 empty] | A | X |  | 9/27/2023 - complete | 9/21/2023 - Complete | 10/27/2023-complete | 11/28/2023-Complete |  | 12/14/2023 - Complete | 2024-05-15 | [6 empty] | Battery backups, near far, L1 containement?
FTY01 | [15 empty] | 4/25/2024-Complete
FTY02 | GEORGIA | Morrison Hershfield | Bid | Lee Percy | LPercy@morrisonhershfield.com |  |  |  | 2023-08-01 | 8/15/2023-Complete | 2023-08-22 | 9/8/2023 - complete | 9/12/2023 - complete | 10/10/2023 - Complete | 10/12/2023- Complete | [7 empty] | Need to update the BOM to comba unit.
FTY03 | [10 empty] | 5/9/2024-Complete |  | 2024-06-03 |  | 2024-07-01
IAD05 | [15 empty] | TBD
IAD12 | LEESBURG, VA | Syska | Design | Liam Wall | lwall@syska.com |  | A |  |  | Complete | 2/22/2023 - Complete |  | 3/29/2023 - Complete |  | 2023-04-26 | 2023-05-30
IAD13 | LEESBURG, VA | Syska | Design | Liam Wall | lwall@syska.com |  | A |  |  | Complete | Complete | Complete | 2/9/2023 - Complete | Complete | 3/24/2023 - Complete | 2023-05-04 | [6 empty] | Riser Info - no IFR yet
IAD14 | LEESBURG, VA |  | Bid | TBD |  |  | A
LVL06 | Drawing Review |  | Design | Fran Carlos | fclaros@swansonrink.com |  | A | 2023-03-02 |  | 3/17/2023 - complete | 3/21/2023 - complete |  | 2023-04-25 | 2023-01-05 | 2023-01-05 | [7 empty] | 4/26/2023: Need to adjust to keep equipement in cells 1-3. See email. | Meet with Preston - make sure he updated prints with S2A changes
LVL07 | [6 empty] | A |  |  | Complete | 8/21/2023-Complete | No Notora | 9/29/2023--Complete | No Notora | 10/19/2023-Complete | 2/19/2024-Complete
LVL11 | BOYDTON, VA | Swanson Rink | Design | Ryan Sims | RSims@swansonrink.com |  | C |  |  | Complete | 1/23/2023 - Complete | 2/20/2023 - Complete | 2/27/2023 - Complete |  | 2023-03-22 | 2023-05-15 | [7 empty] | 2/1: Emailed James for desgin review & emailed Preson for titleblock, etc
LVL12 | [7 empty] | X |  |  | 12/21/2023-Complete |  | 2/5/2024-Complete |  | 2024-02-23 | [7 empty] | Need to provision for off-air as a backup if needed. Need antenna structure to support it.
LVL13-14 | [8 empty] | 2024-03-25 | 3/28/2024-Complete | 2024-04-15 | 2024-05-13 | 2024-05-14 |  | 2024-06-10 | [5 empty] | Loop clark into dicusscion. We will go back to LVL08
LYH03 | BOYDTON, VA | Highland Associates | BID | Hector Hernandez | hhernandez@ha-ny.com |  | C | [15 empty] | Need Floorplans & Schedule
LYH10 | BOYDTON, VA | Highland Associates | Design | Hector Hernandez | hhernandez@ha-ny.com | Bram Wathen | P |  |  | Complete | 11/29/2022 - Complete | Complete | complete | Complete | 2023-03-16 | 6/28/2023 - complete | [6 empty] | IFC Pushed to mid july--Will follow up later 04/28/2023 | 4/18 Specs updated and sent to Paul Duffy for upload. Need to upload to BIM360
MNZ01 | MANASSAS, VA | Sysksa | Design | Christopher Lay | clay@syska.com |  | A | X | [15 empty] | 1/26: emailed Chris asking for info
MNZ03 | MANASSAS, VA | Sysksa | Design | Christopher Lay | clay@syska.com |  | A | [7 empty] | 3/3/2023 - Complete | Mid June
MNZ04 | [10 empty] | 4/23/2024-Complete |  | 2024-06-13 |  | 2024-07-03
MNZ05 | [8 empty] | 2024-05-02 |  | 2024-05-23 |  | 2024-07-11
MWH08 | Quincy | [5 empty] | A | X |  |  | 1/19/2024-Complete |  | 3/24/2024-complete
PHX14
PHX16 | PHOENIX, AZ | [6 empty] | X
PHX17 | PHOENIX, AZ | [6 empty] | X
PHX15 | PHOENIX, AZ | [6 empty] | X | 2024-05-28 | Rough Date | 2024-06-18
PHX61 | [9 empty] | 11/9/2023-Complete |  |  | 11/16/2023-Complete
PHX71 | PHOENIX, AZ | Jacobs | Design | Blake Giles | Blake.Giles@jacobs.com |  | C | X | [14 empty] | Repackaging Site
PHX72 | PHOENIX, AZ | Jacobs | Design | Blake Giles | Blake.Giles@jacobs.com |  | A |  | 2023-02-28 | Complete | 2023-03-21 |  |  |  | 2023-06-12 | [7 empty] | QA Form, SPEC, Review A/E Sumittal | IFP Pushed back to 5/23
PHX73 | PHOENIX, AZ | [7 empty] | 2023-08-03 | 8/11/2023 - complete | 2023-08-24 | No Notora | 2023-09-21 | No Notora | 10/17/2023-Complete
PHX74 | PHOENIX, AZ | [5 empty] | A | X |  | 10/20/2023-Complete | 11/9/2023-Complete | SPEC Needed | 2023-12-08 | No Notora | 2024-01-10
PHX81 | PHOENIX, AZ | Jacobs | Design | Blake Giles | Blake.Giles@jacobs.com |  | C |  |  | Complete | 11/10/2022 - Complete | Complete | 12/9/2022 - Complete | 1/25/2023-complete | 1/30/2023-complete | 3/11/2024-Complete |  |  |  |  | No Notora |  | Notora Needs IFC Date | 1/26: recieved package from WT, uploaded. 1/20: emailed David at WT requesting package 1/19: specs sent to PM
PHX82 | PHOENIX, AZ |  | Design |  |  | Bram Wathen | A |  | 2023-04-06 |  | 2023-04-27 | 2023-06-02 | 2023-06-06 |  | 2023-06-29 | [7 empty] | 4/18 Harold to Review Design. SPECS due June 1 | We need to review 50% set
PHX83 | PHOENIX, AZ
SAT14 | [15 empty] | 2024-05-16
SAT15 | SAN ANTONIO, TX | Page Southerland Page Inc. | Design | Lauren Alexander | lalexander@pagethink.com |  | A | X |  | Complete | Complete | Complete | 12/14/2022 - Complete | No NT | 2024-05-16 | 2023-04-03 | [6 empty] | IFC date determined after permitting
SAT17 | [7 empty] | X |  |  | 3/27/2024-Complete |  | 5/9/2024-Complete |  | 2024-06-06
SAT16 | [7 empty] | X |  | 10/26/2023 - complete | 11/29/2023-Complete |  | 1/9/2024-Complete |  | 2/15/2024-Complete
SAT40 | SAN ANTONIO, TX | Page Southerland Page Inc. | Design | Lauren Alexander | lalexander@pagethink.com |  | A |  |  | Complete | 11/30/2022 - Complete | Complete | 1/20/2023 - Complete | 2/15/2023 - Complete | 2023-02-03 | 8/2/2023--Complete | [6 empty] | Notora Needs Updated IFP Titleblock
SAT80/81 | SAN ANTONIO, TX | Page Southerland Page Inc. | Design | Alan McClung | amcclung@pagethink.com |  | A |  |  | Complete | Complete | Complete | 7/11/2023--Complete | [9 empty] | Notora Needs Floorplans & IFC Dates
SAT82 | [7 empty] | X |  | 10/31/2023 - complete | 12/4/2023-Complete |  | 1/16/2024-Complete |  | 2/6/2024-Complete | 2023-02-23
SAT90 | [7 empty] | X | [6 empty] | 2/15/2024-Complete
SAT89 | SAN ANTONIO, TX | [5 empty] | A | X |  | 10/25/2023 - complete | 11/15/2023-Complete | Stephen To deliver | 1/4/2024-Complete |  | 2/15/2024-Complete
SJC02 | SAN JOSE, CA | Jacobs | Design | Kristin McCue | Kristin.McCue@jacobs.com |  | A |  |  | Complete | Complete | 9/8/2023 - complete | 9/14/2023 - complete | 10/20/2023-Complete | 2024-06-15 | [8 empty] | Project is on hold while "they" are working through the IFP comments
SJC04 | SAN JOSE, CA | Jacobs | Bid | Kristin McCue | Kristin.McCue@jacobs.com |  | P |  | 2024-06-27 |  | 2024-07-18 |  | 2024-09-12
YQB01/02 | QUEBEC CITY |  |  |  |  | Bram Wathen | A | X |  |  |  |  | 7/11/2023-Complete | 8/7/2023 - Complete | 10/4/2023 - complete | 2/27/2024-complete
YQB04 | QUEBEC CITY |  |  |  |  | Bram Wathen | A | X |  | 3/3/2023 - complete | 3/3/2023 - complete | 3/16/2023- complete | 3/20/2023 - complete | 6/9/2023 - complete | 6/15/2023 - complete | 11/15/2023-complete
YQB06 | QUEBEC CITY | [5 empty] | A | X |  | 5/1/2023 - complete | 4/24/2023 - complete | 6/22/2023--Complete | 6/27/2023--Complete | No Notora | 9/25/2023 - Complete | 2/2/2024-Complete | [6 empty] | Site Plans email sent.
YQB11 | QUEBEC CITY | [5 empty] | A | X |  | 5/8/2023 - complete | 5/12/2023 - complete | 7/1/2023 - complete | 7/25/2023--Complete | 2023-09-29 | 12/12/2023-Complete | 4/9/2024-Complete
YTO10 | Toronto |  | Bid | Saeed Akbari | SAkbari@morrisonhershfield.com |  | A
YTO11 | Toronto | Morrison Hershfield | Design | Saeed Akbari | SAkbari@morrisonhershfield.com |  | A | X |  | Complete | 9/26/2022 - Complete | Complete | 2/3/2023 - Complete | Complete | 8/8/2023 - Complete | 2024-02-16 |  |  |  |  | Need to update note & Site plan |  | Just the Drawings-Update Dates (7-10) | We will not be submitting a 50% design (or 100% draft as they call it); once we get comments back from Microsoft on YTO40, then they will have us make the same changes to YTO11 and then we will submit YTO11
YTO14 | Toronto | Morrison Hershfield | Design | Saeed Akbari | SAkbari@morrisonhershfield.com | Bram Wathen | A | X |  | 5/3/2023 - complete | 8/26/2023- Complete | 6/13/2023 - complete | tbd |  |  | TBD |  |  |  |  | Need to update note & Site plan |  | Set up meeting w Jim + Harold to discuss the Colo 5 Elec 3 Riser room for fiber. | Guard house is the same as YTO11 & YTO40. Talk to Mianna for updated plans. 100 % changed to October 16
YTO40 | Toronto | Morrison Hershfield | Design | Saeed Akbari | SAkbari@morrisonhershfield.com |  | A | X |  | Complete | Complete | Complete | 1/5/2023 - Complete | 2/14/2023 - Completed | 2024-05-23 | TBD |  |  |  |  | Need to update antenna note & Site plan |  | Need IFC Dates | AE should receive comments back from Microsoft on 1/16 and then we will have 5 days to make changes and issue 100% design
Formulas:
Floor Plans Needed = IFERROR(WORKDAY(Table14[[#This Row],[50% IFR - AE]],-15), " ")
Note on E23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FYI... per emails in March, I think Brandi Sauter took over as PM.

## Design
NAME | LOCATION | A/E | Phase (Design or CA) | AE-PM Name | AE-PM Contact | S2 PM | Project Status | Floorplans Received | Floor Plans Needed | 50% IFR - Notora | 50% IFR - AE | 100% IFR - Notora | 100% IFR - AE | IFP - Notora | IFP - AE | IFC | Project Start | Submittal | Substantial Completion | Issue For Record | Completion | Commissioning | Action Item Needed | Comments
ATL06 | Atlanta | Highland Associates | Design | Christopher Ritchie | critchie@ha-ny.com |  | C | Supposed to be 4/7/2023 |  | Complete |  | No Notora | 10/3/2023- Complete | No Notora | 10/24/2023-Complete | 2/12/2024-complete | [6 empty] | Need to track down: Floor Plans, AHJ (Authorities having jurisdiction contact), enforced code | Location: East Point GA Lat Long: 33*38'30"N, 84*30'59"W FloorPlans to be updated Friday the 7th
ATL07 | [6 empty] | C |  | 5/13/2024-complete | 5/23/2024-complete | 5/24/2024-complete | [12 empty] | Work completed, assigned to another contractor
AVC01-DRB13 | SOUTH HILL, VA | [5 empty] | C |  | no |  |  | 1/3/2025-complete | 4/24/2025-Complete |  | 1/24/2025-complete | 1/28/2025-complete
AVC02 | SOUTH HILL, VA | [5 empty] | C |  |  |  | 3/25/2024-Complete |  | 4/29/2024-complete |  | 5/15/2024-complete | No S2A - DayWireless |  |  |  |  | Need as-builts/testing for AVC01. Some weirdness w AVC01 |  | DAS and Public safety Proposal needed. | Given to DWS. Highland associates
AVC09-DRB10 | SOUTH HILL, VA | [5 empty] | C |  | no |  |  | 12/31/2024-Complete | 4/25/2025- Complete |  | 1/24/2025-complete | 1/28/2025-complete
AVC11 | SOUTH HILL, VA | Highland Associates | Design | Paul Duffy (Bim Manager) | pduffy@ha-ny.com |  | C |  | 6/26/24-complete |  | 7/16/2024-Complete |  | 8/21/2024-Complete |  | 9/10/2024-complete | 1/16/2025-completed | [6 empty] | Add note to drawings: Carrier coordination must occur at the beginning of the project. As soon as they are awarded contract. | 8/29: Bram emailed NT: next AVC11 Issuance (IFP) we will need to add a few items. See email thread.
AVC17 | SOUTH HILL, VA | Highland Associates | Design | Hector Hernandez | hhernandez@ha-ny.com | Bram Wathen | C | 2/24/2023 - complete |  | 3/8/2023 - complete | 3/20/2023- complete | 4/17/2023 - complete | 4/24/2023 - complete | 6/2/2023 - complete | 6/5/2023 - complete | 8/3/2023-Complete | [6 empty] | Update the IFC Date | 3 Different Issues. Need to confrim if power supply for fiber optical master is required. Need ROIP specs, Site Heat map.
AVC18 | SOUTH HILL, VA | Highland Associates | Design | Hector Hernandez | hhernandez@ha-ny.com | Bram Wathen | C | 3/3/2023 - complete |  | 3/15/2023 - complete | 3/20/2023 - complete | 4/17/2023 - complete | 4/24/2023 - complete | 6/2/2023 - complete | 6/5/2023 - complete | 8/3/2023-Complete | [6 empty] | Update the IFC Date | Review Drawings prior to IFP
AVC17/18-DRB | SOUTH HILL, VA | Highland Associates | Design | Hector Hernandez | hhernandez@ha-ny.com | Bram Wathen | A |  |  | 11/25/2024-complete | 12/3/2024-complete |  | 4/17/2025-complete | 12/13/2024-complete |  | 12/18/2024-Complete | [6 empty] | 5/6: Waiting on Commscope for ROM. Proposal received from Andrews 4/30 Waiting on OneCell BOM pricing - Wesco Note-need benchmark | 5/6: Waiting on Commscope for ROM. Proposal received from Andrews 4/30 Waiting on OneCell BOM pricing - Wesco Note-need benchmark
AVC19 | SOUTH HILL, VA | Highland Associates | Design | Hector Hernandez | hhernandez@ha-ny.com | Bram Wathen | C |  | 12/16/24-complete | 1/13/2025-complete | 1/22/2025-complete | 3/11/2025-cancelled | 3/12/2025-cancelled |  | 3/25/2024-cancelled
AVC20 | SOUTH HILL, VA | Highland Associates | Design | Hector Hernandez | hhernandez@ha-ny.com | Bram Wathen | C |  | 2/26/25-complete | 3/10/2025-cancelled | 3/12/2025-cancelled
AVC21 | SOUTH HILL, VA | Highland Associates | Design | Hector Hernandez | hhernandez@ha-ny.com | Bram Wathen | C |  | cancelled | 4/21/2025-cancelled | 4/24/2025-cancelled
AVC43 | SOUTH HILL, VA | Swanson Rink | Design | Ryan Sims | RSims@swansonrink.com |  | C | 2022-11-09 |  | Complete | 11/21/2022 - Complete | Complete |  |  | Complete | [7 empty] | 2x2 cabinet
AVC43_DRB07 | SOUTH HILL, VA | Swanson Rink | Design | Ryan Sims | RSims@swansonrink.com |  | C |  | no |  |  | 12/31/2024-complete | 4/25/2025-Complete |  | 1/24/2025-complete | 1/27/2025-complete
BN_Campus | BOYDTON,VA | [5 empty] | C | [6 empty] | 4/28/2025-complete | 4/4/2025-complete | [7 empty] | BW – schedule meeting for Thursday 5/7 KP invoice after delivered.
BN7-8Rev | BOYDTON,VA | [5 empty] | C | [6 empty] | 5/1/2025-complete | [8 empty] | BW – schedule meeting for Thursday 5/7 KP invoice after delivered.
CCO06DRB13 | [6 empty] | C |  |  |  |  | 5/1/2025-completed | 5/6/2025-Completed |  |  | 5/8/2025-complete
CCO07 | PALMETTO, GA | [5 empty] | C |  |  | 8/23/2023 - complete | 9/7/2023 - complete | No Notora | 10/19/2023-Complete | No Notora | 11/7/2023-Complete
CCO07DCN07 | PALMETTO, GA |  |  |  | Steve.Baum@jacob.com |  | C | [6 empty] | 5/23/2025-complete | 5/23/2025-Complete | 6/6/25-complete
CCO08 | PALMETTO, GA | Jacobs | Design | Michael Mcloone | Michael.Mcloone@jacobs.com |  | C | 7/10/2024-Complete | 7/10/2024-Complete | 7/19/2024-Complete | 7/29/2024-Complete | 8/23/24-complete | 9/3/2024-Complete | 9/16/2024-complete | 9/18/2024-complete | TBD |  |  |  |  | Launch(Admin&Colo1) & PKG3-6 Fitout. Separate packages |  | 8/8/24: NT requests 50%s by 8/13 in order to make the 8/22 date for 100%'s. 8/6/24 HS – agree on a standard PSDAS approach – 4 or 3 antennas per COLO, 1 or 2 FBDAs per DC - no opinion from S2A side other than we want a uniform approach across all our projects. Verify Centerline calculated, not guessed at, the potential of near far. One option to calculate: Steps to Calculate Determine the Power Levels: Measure the power levels of the signals from both the near and far transmitters (radios). Calculate Path Loss: Use the path loss formula to determine how much the signal strength decreases over distance. The path loss ( L ) can be calculated using: L=10⋅n⋅log10​(d)+C where ( n ) is the path loss exponent, ( d ) is the distance, and ( C ) is a constant. Evaluate Interference: Assess the interference caused by the stronger signal on the weaker one. This can be done using the Signal-to-Interference Ratio (SIR): SIR= ​Pfar​​/ Pnear , where ( P_{\text{far}} ) is the power of the far signal and ( P_{\text{near}} ) is the power of the near signal.
CCO08DCN | PALMETTO, GA | [5 empty] | A |  |  | 5/12/2025-complete |  |  |  | 7/17/25-complete | 8/5/2025-complete | [7 empty] | 7/28: IFP due date changed to 8/5 per email from BW. 7/21: Draft IFP delivered to A/E, final due 8/11.
CHI05 | Chicago | [5 empty] | C | 5/19/2023 - complete |  | 5/26/2023 - complete | [5 empty] | 4/2/2024-complete |  |  |  | No Notora |  |  |  | We need NT proposal
CHI11 | Chicago | [5 empty] | C | X |  | 5/26/2023 - complete |  |  |  |  | 3/11/2024-Complete | [8 empty] | We need NT proposal
CHI22 | Chicago | [5 empty] | C | [7 empty] | 1/11/2024-COMPLETE | 1/19/2024-complete | [7 empty] | IFP DRB17 Print
CLT04 | North Carolina | Olson | Design | David Barber | dbarber@olsson.com | Bram Wathen | C | 1/31/2023 - complete |  | 2/16/2023 - complete | 2/16/2023 - complete | 4/12/2023 -complete | 4/26/2023 - complete | 2/20/2024-Complete | 2/21/2024-Complete | 1/3/2025-complete | [6 empty] | Title block updates. Request sent to Stephen 5/11 | Get address and find cell towers
CLT05 | North Carolina | [5 empty] | C |  | 1/8/25-complete | 1/17/2025-completed | 1/21/2025-Complete | 2/10/2025-complete | 2/13/2025-Complete | [10 empty] | 9/17/24: Unclear if S2A got contract or not.
CLT10 | North Carolina | Olsson | Design | Meg Plank | mplank@olsson.com |  | C | X |  | 6/30/2023 - Complete | 7/06/2023 - Complete | 8/25/2023 - complete | 8/31/2023-Complete | 2/20/2024-Complete | 2/21/2024-Complete | 1/3/2025-complete | [6 empty] | Site Plans & Floor Plans | Project Kick off June 1st.
CLT11 | North Carolina | [5 empty] | C |  | 1/23/25-complete | 2/3/2025-complete | 2/4/2025-Complete | 3/14/2025-cancelled | 3/18/2025-cancelled |  | 4/8/2025-cancelled
CLT17 | North Carolina | Olson | Design | David Barber | dbarber@olsson.com | Bram Wathen | C | X |  | 11/10/2023 - complete | 11/16/2023-complete | 12/20/2023 - complete | 1/3/2024-Complete |  | 2/14/2024-Complete | 1/3/2025-complete | [7 empty] | Not doing the CADs for this one
CLT18 | North Carolina | [5 empty] | C |  | 2/17/25-completed | 2/25/2025-completed | 2/27/2025-complete | 4/11/2025-cancelled | 4/15/2025-cancelled |  | 5/6/2025-cancelled
CPQ03 | BRAZIL | Deerns | Design | Gabriel Pereira | gabriel.pereira@deerns.com |  | C | [8 empty] | 10/16/2023-complete
CPQ04 | BRAZIL | [5 empty] | C |  | 9/13/2024-complete | 9/19/24-complete | 9/24/2024-complete | 10/7/2024-complete | 10/14/2024-complete | [10 empty] | 8/29/24: added to list. project coming up.
CPQ07 | BRAZIL | Deerns | Design | Gabriel Pereira | gabriel.pereira@deerns.com |  | C | X |  | 2/17/2023 - complete | 1/11/2023 - Complete | [11 empty] | Need updated IFR Date, if we're doing the CAD's | 1/25: emailed Kelwin asking for info
CPQ08 | BRAZIL | [5 empty] | C |  |  |  | 1/8/2024-Complete
CPQ11 | BRAZIL | Deerns | Design | Gabriel Pereira | gabriel.pereira@deerns.com |  | C | X |  | Complete
CYS13 | Cheyanne | [5 empty] | C | [12 empty] | 9/10/2024-completed |  |  | 7/29/24: Bram follow up with Kristin McCue for details/confirmed schedule | 7/17/24: CYS13 Record Drawings (Admin and COLOs 1 through 5) to close out the project. The latest federated model is available in Navisworks and all disciplines should have final approved redlines (with the exception of Mechanical, where we are tracking down some last info). Please begin working on Record Drawings with the idea to submit as early as possible in August (date TBC once we receive final Mech info). The client has asked us to submit these as soon as possible, so we’re being asked to advance what we can.
CYS17 | Cheyanne | Jacobs | Design | Kristin McCue | Kristin.McCue@jacobs.com |  | A |  |  |  |  | Complete | 1/24/2023-complete | complete | complete |  |  |  |  | 7/11/2025-complete |  |  | 6/10/25: Redlines expected end of June(?) | 2/6/2023: WT indicates a 2/13 delivery date. 2/6/2023: emailed WT requesting IFP update 1/24: recieved updated design fromWT, uploaded 1/20: recieved design from David. Emailed AE the drawing list and uploaded files to AE and S2 1/19: This is a 'WT' site, emailed Davide requesting design update 1/18: sent philip design pkg 4 email 1/13/23: emailed Kristen requesting update
DFW20 | Irving, TX | [5 empty] | C | [8 empty] | 3/8/2024-complete
DSM12 | DES MOINES | Burns & McDonnell | Design | Kylie Hornbeck | khornbeck@burnsmcd.com |  | C | [15 empty] | Nick coordinating with AE
DSM14 | DES MOINES | Burns & McDonnell | Design | Kylie Hornbeck | khornbeck@burnsmcd.com |  | C | [15 empty] | Nick coordinating with AE
DSM15 | DES MOINES | Burns & McDonnell | Design | Kylie Hornbeck | khornbeck@burnsmcd.com |  | C | [15 empty] | Need Floorplans & Schedule - Nick to follow up with AE
DSM40 | DES MOINES | Burns & McDonnell | Design | Kylie Hornbeck | khornbeck@burnsmcd.com |  | C | [8 empty] | 5/8/2024-Complete |  |  |  | 9/4/2024-Complete |  |  | Nick coordinating with AE
DSM41 | DES MOINES | Burns & McDonnell | Design | Kylie Hornbeck | khornbeck@burnsmcd.com |  | C | [15 empty] | Nick coordinating with AE
DSM44 | DES MOINES | Burns & McDonnell | Design | Andrew Kalaani | akalaani@burnsmcd.com |  | A |  |  | N/A | N/A | No NT | 9/18/2024-Complete | No NT | 10/7/2024-Complete | [7 empty] | 8/5/24: HS – we will want to look at the campus layout as part of the evaluation. | No Notora. S2A engaged to review designs.
EAT04 | WENATCHEE, WA | ESD | Design | Chad Mendell | cmendell@esdglobal.com |  | C |  |  | Complete | 12/1/2022 - Complete | Complete | 1/12/2023 - Complete | 1/19/23-complete | 1/26/2023-complete | 5/31/2023-Complete | [7 empty] | 2/6/23: IFC is TBD no update1/25: recieved updated design from Philip, uploaded to AE and S2 1/19: recieved updated design from Philip, uploaded to BIM and S2 1/19: uploaded specs, requested IFP design from Philip 1/18: sent IFP instructions to Notora
EAT05 | WENATCHEE, WA | ESD | Bid | Chad Mendell | cmendell@esdglobal.com |  | C | 4/17/2023 - complete |  | 5/3/2023 - complete | 4/20/2023 - complete | 5/19/2023 - complete | 5/25/2023 - complete | complete | 6/13/2023 - complete | 3/5/2024-Complete | [6 empty] | Notora Internal review return 5/1-5/2 | May
EAT06 | WENATCHEE, WA | [5 empty] | C |  |  | 8/9/2023--Complete | 8/1/2023-Complete |  | 9/7/2023 - complete |  | 9/26/2023-Complete | 9/24/2024-complete
EAT09 | WENATCHEE, WA | [5 empty] | C | 8/16/2023 - complete |  |  |  |  | 9/7/2023 - complete |  | 9/26/2023-Complete | 9/24/2024-complete
EAT06-09Revision | WENATCHEE, WA | Stantec |  | Michael Clements | Michael.Clements@stantec.com |  | A | 2025-05-27 | YES |  | 8/29/2025?
EAT12 | WENATCHEE, WA | ESD | Design | Chad Mendell | cmendell@esdglobal.com |  | C |  |  | 2/20/2023-complete | 2/23/2023-complete | 3/20/2023 - complete | 3/9/2023 - complete | complete | 4/6/2023 - complete | 3/21/2024 Complete | [6 empty] | Change notes in the Public Safety. Cover the L1 containment unless AHJ approves alternate means and methods. Pull box detail | 2/15: in internal review 2/15: requested update from Notora 2/3/23: floor plan delivered to Notora 2/1: Harold got floorplans today; 1/18: Design is resuming with meeting 1/30
EAT12Revision | [6 empty] | A | [15 empty] | Per Call 5/6: Survey scheduled for Friday. Waiting on DW benchmark; waiting on Stantec approval. Covered by CA.
EAT13 | WENATCHEE, WA | ESD | Design | Chad Mendell | cmendell@esdglobal.com |  | C | X |  | 6/14/2023 - complete | 6/15/2023 - complete | 7/18/2023-Complete | 7/20/2023-Complete | 8/1/2023-Complete | 8/2/2023-Complete | 4/9/2024-complete | [7 empty] | Starting the week of 5/8
EAT14 | WENATCHEE, WA | [5 empty] | C | X |  | 9/27/2023 - complete | 9/21/2023 - Complete | 10/27/2023-complete | 11/28/2023-Complete |  | 12/14/2023 - Complete | 9/3/2024-Complete | [6 empty] | Battery backups, near far, L1 containement?
FTY01 | Douglassville, GA | [5 empty] | C | [8 empty] | 4/25/2024-Complete
FTY02 | GEORGIA | Morrison Hershfield | Bid | Lee Percy | LPercy@morrisonhershfield.com |  | C |  |  | 8/15/2023-Complete | 8/22/2023 - complete | 9/8/2023 - complete | 9/12/2023 - complete | 10/10/2023 - Complete | 10/12/2023- Complete | 5/23/2024-complete | [6 empty] | Need to update the BOM to comba unit.
FTY03 | Atlanta, GA | [5 empty] | C |  |  |  | 5/9/2024-Complete |  | 6/6/2024-Complete |  | 7/1/2024-Complete
FTY04 | Atlanta, GA | [5 empty] | C |  | 7/22/24-complete | 8/5/2024-complete | 8/5/2024-complete | 8/28/2024-Complete | 9/5/2024-Complete | 9/24/2024-complete | 9/27/2024-Complete | [7 empty] | 8/5/24: HS – LINX has installed a ONECELL – we need to make sure that the FTY04 design captures fiber requirements. | 8/23: NT target delivery 8/26.
IAD04DRB | LEESBURG, VA | [5 empty] | A | [8 empty] | 6/27/2025-complete
IAD05 | LEESBURG, VA | [5 empty] | C | [7 empty] | No Notora | 5/20/2024-complete | [6 empty] | Bram requesting CAD contact @ sysksa
IAD11 | LEESBURG, VA | [5 empty] | C | [5 empty] | 7/8/2025-complete | [6 empty] | 10/18/2024-completed |  |  | Bram to do AS Builds
IAD12 | LEESBURG, VA | Syska | Design | Liam Wall | lwall@syska.com |  | C |  |  | Complete | 2/22/2023 - Complete |  | 3/29/2023 - Complete |  | 4/26/2023-complete | 5/30/2023-complete
IAD11DRB-DCN08 | LEESBURG, VA | [5 empty] | A |  | complete |  | 7/2/2025-complete | 7/14/2025-complete | 7/18/2025-complete
IAD12-13Descope | LEESBURG, VA | [5 empty] | A |  |  | 5/7/2025-complete |  |  |  | 5/23/25-complete |  | 5/23/2025-complete
IAD12-13-DCN06
IAD13 | LEESBURG, VA | Syska | Design | Liam Wall | lwall@syska.com |  | C |  |  | Complete | Complete | Complete | 2/9/2023 - Complete | Complete | 3/24/2023 - Complete | 5/4/2023-complete | [6 empty] | Riser Info - no IFR yet
IAD14 | LEESBURG, VA |  | Bid | TBD |  |  | C
LVL01-07-DRB | BOYDTON, VA | [5 empty] | C |  |  |  |  | 12/31/2024-complete | 1/13/2025-complete |  | 1/24/2025-complete | 1/27/2025-complete
LVL05 | BOYDTON, VA | [5 empty] | C | [12 empty] | 5/14/2025-complete
LVL06 | BOYDTON, VA |  | Design | Fran Carlos | fclaros@swansonrink.com |  | C | 3/2/2023 - complete |  | 3/17/2023 - complete | 3/21/2023 - complete |  | 4/25/2023 - complete | 1/5/2023 - complete | 1/5/2023 - complete | [7 empty] | 4/26/2023: Need to adjust to keep equipement in cells 1-3. See email. | Meet with Preston - make sure he updated prints with S2A changes
LVL06_EXT | [6 empty] | C | [5 empty] | 4/25/2025-complte
LVL07 | BOYDTON, VA | [5 empty] | C |  |  | Complete | 8/21/2023-Complete | No Notora | 9/29/2023--Complete | No Notora | 10/19/2023-Complete | 2/19/2024-Complete |  |  |  | 7/28/2025-complete
LVL07DRB03 | BOYDTON, VA | [5 empty] | A
LVL08-14-DRB | BOYDTON, VA | [5 empty] | C |  |  |  |  | 12/31/2024-complete | 1/13/2025-complete |  | 1/24/2025-complete | 1/27/2025-complete |  |  |  | 7/28/25?
LVL09_RecordSets | BOYDTON, VA | [5 empty] | A | [12 empty] | 7/28/2025-complete |  |  | drawing list due 7/15.
LVL11 | BOYDTON, VA | Swanson Rink | Design | Ryan Sims | RSims@swansonrink.com |  | C |  |  | Complete | 1/23/2023 - Complete | 2/20/2023 - Complete | 2/27/2023 - Complete |  | 3/22/2023-complete | 5/15/2023-complete | [7 empty] | 2/1: Emailed James for desgin review & emailed Preson for titleblock, etc
LVL12 | BOYDTON, VA | [5 empty] | C | X |  |  | 12/21/2023-Complete |  | 2/5/2024-Complete |  | 2/23/2024-complete | 6/28/2024-Complete | [6 empty] | Need to provision for off-air as a backup if needed. Need antenna structure to support it.
LVL11Rev | BOYDTON, VA | [5 empty] | C |  |  |  | 4/16/2025-Complete
LVL12DRB01 | BOYDTON, VA | [5 empty] | C |  |  |  |  | 1/27/2025-complete | 4/15/2025 - Complete | 2/14/2025-complete | 5/6/2025-complete | 2025-08-12
LVL13-14 | BOYDTON, VA | [5 empty] | C |  |  | 3/28/2024-Complete | 4/15/2024-Complete | 5/13/2024-complete | 5/14/2024-complete |  | 6/5/2024-Complete | 9/09/2024-Complete |  |  |  |  | Loop clark into dicusscion. We will go back to LVL08 |  |  | 12/19/24: per email, 13 & 14 construction are cancelled and 12 will be a stand alone data center.
LYH03 | BOYDTON, VA | Highland Associates | BID | Hector Hernandez | hhernandez@ha-ny.com |  | C | [15 empty] | 7/29/24: S2A not awarded bid. See email from HS.
LYH10 | BOYDTON, VA | Highland Associates | Design | Hector Hernandez | hhernandez@ha-ny.com | Bram Wathen | C |  |  | Complete | 11/29/2022 - Complete | Complete | complete | Complete | 3/16/2023-complete | 10/31/2024-Complete | [6 empty] | IFC Pushed to mid july--Will follow up later 04/28/2023 | 4/18 Specs updated and sent to Paul Duffy for upload. Need to upload to BIM360
LYH10_DRB | [6 empty] | C |  |  |  |  | 4/25/2025-Complete | 4/25/2025-Complete
MNZ01 | MANASSAS, VA | Sysksa | Design | Christopher Lay | clay@syska.com |  | C | X | [15 empty] | 1/26: emailed Chris asking for info
MNZ03 | MANASSAS, VA | Sysksa | Design | Christopher Lay | clay@syska.com |  | C | [7 empty] | 3/3/2023 - Complete | mid june-Complete
MNZ03DRB | MANASSAS, VA | [5 empty] | A | [8 empty] | 6/6/25-complete
MNZ04 | MANASSAS, VA | Syska | Design | Christopher Lay | clay@syska.com |  | C |  |  |  | 4/23/2024-Complete |  | 6/18/2024-Complete | 7/15/2024-complete | 7/16/2024-complete
MNZ05 | MANASSAS, VA | Syska | Design | Christopher Lay | clay@syska.com |  | C |  |  |  | 5/30/2024-complete |  | 7/11/2024-Complete
MWH08 | Quincy, WA | [5 empty] | C | X |  |  | 1/19/2024-Complete |  | 3/24/2024-complete
PHX12 | PHOENIX, AZ | [5 empty] | A | [12 empty] | TBD
PHX14 | PHOENIX, AZ | [5 empty] | ?
PHX16 | PHOENIX, AZ | [5 empty] | ? | X
PHX17 | PHOENIX, AZ | [5 empty] | ? | X
PHX15 | PHOENIX, AZ | [5 empty] | C | X |  | Rough Date | 6/19/2024-Complete | 7/25/2024-complete | 7/26/2024-complete | 8/23/2024-complete | 8/28/2024-Complete | 3/31/2025-completed
PHX61 | PHOENIX, AZ | [5 empty] | C |  |  | 11/9/2023-Complete |  |  | 11/16/2023-Complete
PHX71 | PHOENIX, AZ | Jacobs | Design | Andrea Frazier-Sanchez | Andrea.FrazierSanchez@jacobs.com |  | A | X | [11 empty] | TBD |  |  | Repackaging Site
PHX72 | PHOENIX, AZ | Jacobs | Design | Andrea Frazier-Sanchez | Andrea.FrazierSanchez@jacobs.com |  | C |  |  | Complete | 3/21/2023 - complete |  |  |  | 6/12/2023 - complete | 6/13/2024-complete | [6 empty] | QA Form, SPEC, Review A/E Sumittal | IFP Pushed back to 5/23
PHX72DRB08 | [6 empty] | C |  | 4/28/2025-complete |  |  | 5/5/2025 - Complete | 5/2/2025-complete |  |  | 6/9/2025-complete
PHX82DRB11 | [6 empty] | C |  |  |  |  | Complete | 5/2/2025-complete |  |  | 6/9/2025-complete
PHX72-Rescope | [6 empty] | A
PHX82-Rescope | [6 empty] | A
PHX73 | PHOENIX, AZ | [5 empty] | C |  |  | 8/11/2023 - complete | 8/24/2023 - complete | No Notora | 9/21/2023 - complete | No Notora | 10/17/2023-Complete | 10/26/2024-Jacobs-complete
PHX74 | PHOENIX, AZ | [5 empty] | C | X |  | 10/20/2023-Complete | 11/9/2023-Complete | SPEC Needed | 12/8/2023-complete | No Notora | 1/10/2024-complete | 12/2/2024 - Jacobs did CADS - complete
PHX81 | PHOENIX, AZ | Jacobs | Design | Blake Giles | Blake.Giles@jacobs.com |  | C |  |  | Complete | 11/10/2022 - Complete | Complete | 12/9/2022 - Complete | 1/25/2023-complete | 1/30/2023-complete | 3/11/2024-Complete |  |  |  |  | No Notora |  | Notora Needs IFC Date | 1/26: recieved package from WT, uploaded. 1/20: emailed David at WT requesting package 1/19: specs sent to PM
PHX82 | PHOENIX, AZ |  | Design |  |  | Bram Wathen | C |  |  |  | 4/27/2023 - complete | 6/2/2023 - complete | 6/6/2023 - complete |  | 6/29/2023 - complete | 8/26/2024-Complete |  |  |  |  | Jacobs to Deliver. QA/QC done already. |  | 4/18 Harold to Review Design. SPECS due June 1 | We need to review 50% set
PHX83 | PHOENIX, AZ | [5 empty] | ?
QRO01 | MEXICO CITY, MX | Burns & McDonnell | Design Phase 2 | Charlie Ussery? |  |  | H |  | 8/21/24-completed | 8/20/2024-Complete | 8/22/2024-Complete | 9/15/2024-Complete | 9/19/2024-Complete | 9/30/2024-Complete | 10/8/2024-completed | 4/18/2025-cancelled |  |  |  | TBD |  |  | 7/29/24: Harold reaching out to Alma regarding meeting/schedule.
QRO02 | Queretaro, MX | [5 empty] | H |  | 8/29/24-completed | 9/10/2024-complete | 9/19/2024-complete | 10/3/2024-Complete | 10/11/2024-Complete | 10/25/2024-Complete | 10/30/2024-Complete | 5/2/2025-cancelled |  |  |  |  | Deliver to A.E on 10/09.
QRO06 | Queretaro, MX | [5 empty] | H |  | 9/23/24-complete | 10/2/2024-complete | 10/4/2024-Complete | 10/16/2024-complete | 10/16/2024-Complete | 11/5/2024-Complete | 11/12/2024-Complete | 7/22/2025-complete
SAT14 | SAN ANTONIO, TX | Page Southerland Page Inc. | Design | Lauren Alexander | lalexander@pagethink.com |  | C | [8 empty] | 5/16/2024-complete | [7 empty] | 8/14/24: submittals pertaining to the Red Line Drawings. These must be submitted as one complete and final package
SAT15 | SAN ANTONIO, TX | Page Southerland Page Inc. | Design | Lauren Alexander | lalexander@pagethink.com |  | H | X |  | Complete | Complete | Complete | 12/14/2022 - Complete | No NT | 5/16/2024-complete | Phase 2 - TBD? | [6 empty] | IFC date determined after permitting | 8/14/24: submittals pertaining to the Red Line Drawings. These must be submitted as one complete and final package
SAT17 | SAN ANTONIO, TX | [5 empty] | C | X |  |  | 3/27/2024-Complete |  | 5/9/2024-Complete |  | 9/12/2024-complete
SAT16 | SAN ANTONIO, TX | [5 empty] | C | X |  | 10/26/2023 - complete | 11/29/2023-Complete |  | 1/9/2024-Complete |  | 2/15/2024-Complete
SAT40 | SAN ANTONIO, TX | Page Southerland Page Inc. | Design | Lauren Alexander | lalexander@pagethink.com |  | C |  |  | Complete | 11/30/2022 - Complete | Complete | 1/20/2023 - Complete | 2/15/2023 - Complete | 2023-02-03 | 8/2/2023--Complete | [6 empty] | Notora Needs Updated IFP Titleblock | 8/14/24: submittals pertaining to the Red Line Drawings. These must be submitted as one complete and final package
SAT40Rev | SAN ANTONIO, TX | Page Southerland Page Inc. | Design | Lauren Alexander | lalexander@pagethink.com |  | C | [8 empty] | 4/11/2025-Complete
SAT80/81 | SAN ANTONIO, TX | Page Southerland Page Inc. | Design | Alan McClung | amcclung@pagethink.com |  | C |  |  | Complete | Complete | Complete | 7/11/2023--Complete |  |  | 1/9/2025-complete |  |  |  |  | Follow up with A.E on whether we want to add in VHF or not. |  | Notora Needs Floorplans & IFC Dates | 8/14/24: submittals pertaining to the Red Line Drawings. These must be submitted as one complete and final package
SAT82 | SAN ANTONIO, TX | [5 empty] | C | X |  | 10/31/2023 - complete | 12/4/2023-Complete |  | 1/16/2024-Complete |  | 2/6/2024-Complete
SAT89 | SAN ANTONIO, TX | [5 empty] | C | X | [6 empty] | 4/7/2025-completed | 2/28/2025-complete
SAT90 | SAN ANTONIO, TX | [5 empty] | C | X |  | 10/25/2023 - complete | 11/15/2023-Complete |  | 1/4/2024-Complete |  | 4/7/2025-completed | 2/28/2025-complete
SJC02 | SAN JOSE, CA | Jacobs | Design | Kristin McCue | Kristin.McCue@jacobs.com |  | H |  |  | Complete | Complete | 9/8/2023 - complete | 9/14/2023 - complete | 10/20/2023-Complete | 2025-08-26 | TBD | [6 empty] | A/E Schedule: over the shoulder 8/12 - IFP Rev 4 8/26. | Project is on hold while "they" are working through the IFP comments
SJC04 | SAN JOSE, CA | Jacobs | Bid | Kristin McCue | Kristin.McCue@jacobs.com |  | H |  | Complete |  | 7/18/2024-complete | 9/10/2024-Complete | 9/12/2024-Complete | 10/2/2024-complete | 10/2/2024-Complete | [7 empty] | 8/8/24: Need to revisit PS design for the seismic area underneath building. Bram to provide floor plans to NT.
YQB01/02 | QUEBEC CITY |  |  |  |  | Bram Wathen | C | X |  |  |  |  | 7/11/2023-Complete | 8/7/2023 - Complete | 10/4/2023 - complete | 2/27/2024-complete
YQB04 | QUEBEC CITY |  |  |  |  | Bram Wathen | C | X |  | 3/3/2023 - complete | 3/3/2023 - complete | 3/16/2023- complete | 3/20/2023 - complete | 6/9/2023 - complete | 6/15/2023 - complete | 11/15/2023-complete
YQB06 | QUEBEC CITY | [5 empty] | C | X |  | 5/1/2023 - complete | 4/24/2023 - complete | 6/22/2023--Complete | 6/27/2023--Complete | No Notora | 9/25/2023 - Complete | 2/2/2024-Complete
YQB11 | QUEBEC CITY | [5 empty] | C | X |  | 5/8/2023 - complete | 5/12/2023 - complete | 7/1/2023 - complete | 7/25/2023--Complete | 9/29/2023-complete | 12/12/2023-Complete | 4/9/2024-Complete
YQB01/02DRB11 | [6 empty] | C | [5 empty] | 4/30/2025-complete |  |  | 5/22/2025-Complete | [6 empty] | Follow up: after IFC – contact contractor to have updated ibWave sent via RFI.
YQB04DRB13 | [6 empty] | C |  | 2024-04-18 |  | 2024-05-09 |  | 5/5/2025-complete | 5/9/2025-Complete |  | 5/21/2025-complete | [6 empty] | Follow up: after IFC – contact contractor to have updated ibWave sent via RFI.
YQB06DRB14 | [6 empty] | C | [5 empty] | 5/7/2025-complete | 5/9/2025-Complte |  | 5/28/2025-complete | [6 empty] | ibWave updates to be delivered in IFC package.
YTO10 | Toronto |  | Bid | Saeed Akbari | SAkbari@morrisonhershfield.com |  | ?
YTO11 | Toronto | Morrison Hershfield | Design | Saeed Akbari | SAkbari@morrisonhershfield.com |  | C | X |  | Complete | 9/26/2022 - Complete | Complete | 2/3/2023 - Complete | Complete | 8/8/2023 - Complete | 10/11/2024-Complete |  |  |  |  | Need to update note & Site plan |  | Just the Drawings-Update Dates (7-10) | We will not be submitting a 50% design (or 100% draft as they call it); once we get comments back from Microsoft on YTO40, then they will have us make the same changes to YTO11 and then we will submit YTO11
YTO11Rev | Toronto |  | Design_Revision |  |  |  | A | [6 empty] | 5/23/2025-complete |  | TBD
YTO14 | Toronto | Morrison Hershfield | Design | Saeed Akbari | SAkbari@morrisonhershfield.com | Bram Wathen | C | X |  | 5/3/2023 - complete | 8/26/2023- Complete | 6/13/2023 - complete | 9/16/2024-Complete |  |  | Complete |  |  |  |  | Need to update note & Site plan |  | Project Cancelled. | Guard house is the same as YTO11 & YTO40. Talk to Mianna for updated plans. 100 % changed to October 16
YTO40 | Toronto | Morrison Hershfield | Design | Saeed Akbari | SAkbari@morrisonhershfield.com |  | C | X |  | Complete | Complete | Complete | 1/5/2023 - Complete | 2/14/2023 - Completed | 5/23/2024-complete | 5/7/2025-Complete |  |  |  |  | Need to update antenna note & Site plan |  | Need IFC Dates | AE should receive comments back from Microsoft on 1/16 and then we will have 5 days to make changes and issue 100% design
YTO40Rev | Toronto |  | Design_Revision |  |  |  | A | [6 empty] | 5/23/2025-complete |  | TBD
Formulas:
Floor Plans Needed = IFERROR(WORKDAY(Table1[[#This Row],[50% IFR - AE]],-15), " ")
Note on A6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: see emailed NTP from Hector 12/6. Per Bram 12/6 this is still in proposal stage (?).
Note on Q7: KP 1/14/25: Refer to the following emails with requirements. Paul Duffy email 1/8 with requirements. Chistopher Ritchie email 1/13 with requirements.
Note on A10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11/18: NTP from A/E and NT po received/sent
Note on A11: Kristen Pearcy: project cancelled March 2025.
Note on A12: Kristen Pearcy: project cancelled March 2025.
Note on A13: Kristen Pearcy: project cancelled March 2025.
Note on A14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11/7: AVC43 Boydton Area ISP changes requested - need to confirm how to reflect dates on tracker. 12/6: AVC43DRB07 agreement signed with A/E. need to confirm how to reflect this in tracker
Note on N15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: updated from 4/21 to 4/25
Note on A16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: added 11/7 - Boydton Area ISP changes coming.
Note on A17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added 4/21/25 and PO sent to CL Reply: Design revisions to be billed to MS PO 101207897
Note on A18: Kristen Pearcy: 4/18: Update to PSDAS needed.
Note on A20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PSDAS Code update -
Note on Q20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DRB 06 IFC (PSDAS Code Update)
Note on A21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4/15/25 - IFC put on hold. Project being descoped. Date TBD
Note on M21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: was due 8/28. NT delivered 8/23.
Note on A22: Kristen Pearcy: design revision - ‘shell space’ that will essentially be a steel shell with exposed beams. requires fully functional ERRCS system in place, with addressing near-far concerns. CADS required
Note on A27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: project cancelled March 2025
Note on A29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12/19 - waiting on contract from A/E Reply: All contracts in place Reply: Project cancelled March 2025
Note on K29: Kristen Pearcy: 1/23/25: Per email from JHussey, NT confirmed date delivery date of 2/3.
Note on L29: Kristen Pearcy: 1/23/25: A/E QC period starts 1/28 but we'll miss that delivery due to floor plans being provided so late. Target to deliver 2/4. A/E issues 50% IFR on 2/5.
Note on A31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: project cancelled March 2025
Note on L33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 09/24: BW to follow up with Deens to confirm date.
Note on U38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: first round delivered 9/10/24 - per email from Kristin McCue 4/23 - targeting to have redline drawings available by 5/8 and final Issue for Record drawing sets delivered by end of May Reply: Per Brandon Gilyard, redlines ETA by 5/9/25
Note on E41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FYI... per emails in March, I think Brandi Sauter took over as PM.
Note on A50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Redesign to Fremont Design kick off meeting 5/19 - proposal requested from CL
Note on I50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kick Off Meeting 5/19
Note on A52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Move PS Antenna - bill to CA
Note on A59: Kristen Pearcy: 2/13/25: ISP Headend Mod
Note on A63: Kristen Pearcy: 2/13/25: ISP Headend Mod DCN08
Note on A64: Kristen Pearcy: AHJ requiring occupancy. PSDAS/ERRCS required. CADS required.
Note on A68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: on project tracker/shared folders as LVL06DRB06
Note on U69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: LVL04/05 - see email from Mira 4/17 with requirements.
Note on A73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kick off meeting 8/12/25
Note on A74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: on project tracker/shared drive as LVL11DRB04
Note on A78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: LVL11 to be updated to match LVL08 update to Ericsson unit. - no billing expected from Centerline side
Note on A79: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1/7/25 - budget remaining on original LVL12-14 Design contract. Use that to cover revisions. Reply: A/E canceled IFP for 2/19. On hold pending scope revisions from MSFT. Reply: A/E confirmed IFP still on hold. Reply: Email from Mira Lammers advising IFC date 4/28/25 noon.
Note on A86: Kristen Pearcy: 2/13/25: ISP Headend Mod
Note on A90: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HS requested update on redline drawing due date from A/E 4/7.
Note on U90: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Brandon Gilyard - email 5/6 approval to work ahead on record set drawings.
Note on Q96: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Per A/E, Andrea Frasier-Sanchez: schedule will be advised.
Note on U96: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Per A/E, Andrea Frasier-Sanchez: schedule will be advised.
Note on A98: Kristen Pearcy: Descope to shell space. requires full functional ERRCS system in place, with addressing near-far concerns. CADS required.
Note on K98: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: BW reached out to Michael Dale at Jacobs requesting updated floor plans.
Note on A99: Kristen Pearcy: Descope to shell space. requires full functional ERRCS system in place, with addressing near-far concerns. CADS required.
Note on A107: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Phase 2 - need to design remaining COLOS
Note on N107: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 90% per HS email
Note on U107: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1/16/25: S2A will not issue until commissioning has been completed. BW communicated this to Fernando. Reply: 01/29/25: Date pushed out to a week. Due to end client 2/7. Reply: Email thread - Bram requesting details on Record Set needs
Note on O108: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Bram Wathen - Hi Bram, this cell was blank. I plugged in the Friday before the A/E due date. (3 days would have been a Sunday). Let me know if any concerns. Thanks! KP
Note on K109: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: per 09/26 call: shooting for 10/3/24 delivery
Note on Q109: Kristen Pearcy: 3/20/25: project scope downgraded to Colo2 FitOut only - proposal requested by 3/28 - delivery schedule TBD. 6/23/25: descope revisions and IFC delivery requested for 7/22
Note on A114: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12/10/24: Estimated online October 2025.
Note on Q116: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12/17/24: BW confirmed target 1/9/25. 12/13/24: A McClung Email - fogot to loop in S2A on IFC pkg and requesting call to discuss deliverable date
Note on A117: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12/20: A/E advised project likely not to proceed to IFC stage . To be redesigned to 2 store Fremont design.
Note on O121: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Bram Wathen Hi Bram, sorry but my notes from yesterday's call are not clear on what delivery date NT is working towards for the SJC04 IFP. I put 10/1 in as place holder but did they commit to something sooner? Thanks for confirming. Reply: Bram confirmed Stephen to delivery 10/2
Note on Q131: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DRB09 - IFC submission date TBD. A/E target to have MS SME input by 6/6. Probably earliest will be mid June.
Note on Q133: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: IFC date for A/E was 5/1. Bram has been in communication

## Site Visit Schedule
Site | Status | S2 Advisors | Date | Test Data Received/Location | Confirmed/Not Confirmed | Notes
ATL06 | Complete | Bram | 2025-11-25 |  | Confirmed
CC006 | Complete | Bram | 2025-11-25 |  | Confirmed
CHI05 | Complete | Harold | Late April | After March 20th | Not Confirmed | 4/13: Katie asked Harold for specific dates 3/17: See the upcoming timeline for CHI05 DAS Commissioning: - March 10th & 11th – Day Wireless will be onsite to repair the current DAS antenna run and fix any open issues with the systems functionality - March 12th & 13th – Day Wireless will be onsite to complete the commissioning of COLO 2-5 DAS system - March 20th – Walsh plans to have all DAS testing and documentation sent into the AE for review and approval CHI05 is turned over and actively operating under MSFT Ops. Following the submission of test reports, your team can review and you are more than welcome to come to site for a final walk (most likely week of March 30th, from our discussion).3/6: Walsh DAS contractor says DAS repairs are happening on the 10th, then CX-ing a couple days after. They expect to get test data to S2A by the 20th. 2/18: We have not heard anything further from the CHI05 Contractor beyond the attached. We understand S2A’s recommendation to hold off on DAS/PS/RoIP Record Drawings at this time. 1/16: AK said there is a Verizon issue. HS asked for submittals and a site visit. 1/5: Waiting to hear back from Andrew Kreb. Back in office today. CHI05 campus turned over on 12/16
YTO11 | Completed | Harold | 2025-12-11 |  | Confirmed | Same visit: CHI05, YTO11 - 8am (7:30am safety meeting) if possible, the preference is to have you take the site safety training which happens at 7:30AM, this will allow you permanent site access and also allow you access to YTO40 in the future, site safety training is approximately 1 hour long. fill out the QR code per the second email when convenient.
YQB04 | Completed | Harold | 2025-12-15 |  | Confirmed | Meet at the site at 8am
AVC43 | Completed | Bram | 2025-12-17 |  | Confirmed | Same visit: IAD05, MNZ03, AVC43
IAD05 | Completed | Bram | 12/15-12/19 |  | Confirmed | Same visit: IAD05, MNZ03, AVC43
MNZ03 | Completed | Bram | 12/15-12/19 |  | Confirmed | Same visit: IAD05, MNZ03, AVC43
EAT04 | On Hold | Harold | Week of March 2-6? |  | Not Confirmed | 2/18: I don’t believe we have been awarded the EAT04 install yet, so this hasn’t been schedule. I’ve forwarded your email on to our account manage who will have better visibility into current status.1/5: No RFIs or submittals. Site not ready, BW to chat with Michael about EAT04 and 12.
EAT12 | Completed | Harold | Week of March 2-6? |  | Not Confirmed | 2/20: PSDAS Cx in progress - ETA finish: 3/2-3/6 Cell DAS Cx in progress - ETA finish: 3/2-3/6 2/18: Katie reached out to Grant Potter about status of the passive layer testing. punch walk COLO 3 and COLO 4 during the EAT12 punch walk
SAT14 | Not Needed | Harold | Early January |  | Not Confirmed | 1/5: Katie reached out to David L. and Jerry B.
SAT40 | On Hold | Harold | Early January |  | Not Confirmed | 2/18: MSFT has not approved the CO. 1/5: Katie reached out to Kevin Shirley "Still waiting for MSFT to provide our dedicated fiber circuit for ISP connection" Kevin will update S2A when ready.
CHI11 | Complete | Harold | Late April | 3/2, CHI11_Test Data (SP folder) | Not Confirmed | 4/13: Katie asked Harold for specific dates 3/17: Ron Swiercz sent full closeout package 3/3: Bram to review test data 2/26: Katie met with DAS contractor. He is sending the test data reports from the subcontractor to S2A. 2/11: Katie sent an email to Sultan Katrangi asking for update. Issues with the functionality of the DAS/Public safety systems at CHI10 which are preventing completion of CHI11 systems.
CCO07 | Not Needed | TBD | Mid-January |  | Not Confirmed | 1/13: HS response to Steve: Until DAS scopes are fully installed and tested, a site visit would be premature. At this time we are not going to schedule a visit 1/5: Katie reached out to Steve Baum. "The last word I had from S2 Advisors (possibly from Bram) was that no on site view was practical until the system was operational. If we need to have someone on site for a punch walk, we are planning on being on site the week of Jan 19 with Electrical/Mechanical being the first two days, Architectural, Security and LSS the last two days. Either group has room for S2 to join."
YTO11/YTO40 | Complete | Harold | July 23rd YTO11: Time: 8:30AM – Location project trailers YTO40: Time: 12:30PM – Location project trailers |  | Confirmed | 7/8: Harold will go to YTO11 first and then YTO40 6/26: Harold to complete DCAT form 6/16: Bell has completed installation and is ready for a site visit. Folders will be populated with test data at the end of the week. 6/10: Bell is currently on site and has not completed their scope as of today. ED will confirm with Bell and send us a heads up of when the work will be complete and ready for a site review, could be late June – stay tuned. 4/27: Expected site ready for a visit in early June. In anticipation of your eventual site visit to close out the Bell scope of work please see attached and fill out so we can get you security access into the turned over space. You can see my information filled out as a template, let me know if you have any questions or concerns, thanks.1/19: I’ve been told that the carrier (bell) has not proceeded with any work, and that they have not given any timeline on commencement. 1/5: Peter asked, "is the Bell Installation complete and should S2A be preparing to come out soon"
PHX81 | Rescheduled | Bram | March 23rd, 2026 |  | Confirmed | 3/3: Brian Gailfus sent pre-site visit instructions 2/18: Katie reached out to Sebastian Arias for DAS test and commissioning data. 1/26: Said this will most likely occur in March during leads meeting. 1/26: HP has pushed PHX82 punch to mid-February. More to come. I still haven’t heard if DAS testing will be complete. Let’s discuss in the leads meeting next Monday. 1/23: Waiting for Brian Gailfus to confirm second week of February. 1/12: Brian Gailfus: HP is asking to finish up PHX81 punch walks for Telecom, DAS/RoIP and Security.
PHX82 | On Hold | Bram | TBD (as of 3/17) |  | Not Confirmed | 2/20: Jesse B. said: PHX82 is still under construction at this time. Aiming to have Admin/COLO1/COLO2 install finished by mid to late March. 2/18: Visit the same time as PHX81? 1/26: Said this will most likely occur in March during leads meeting. 1/26: HP has pushed PHX82 punch to mid-February. More to come. I still haven’t heard if DAS testing will be complete. Let’s discuss in the leads meeting next Monday. 1/23: Waiting for Brian Gailfus to confirm second week of February. 1/12: Brian Gailfus said in the PHX81/82 leads meeting PHX82 would be ready for a site visit in early Feb
PHX72 | On Hold | Bram | March 25th, 2026 (can reschedule to March 24th) | Receiving test data 3/17 | Confirmed | 3/6: Commissioning and the testing is supposed to be completed by March 16th. If so, that should be enough time to submit and review the needed information. Since zBeta schedules are as full as the rest of us, I recommend that we keep the March 25th date 2/20: Do not yet have test data. Ideally same trip at PHX81 and PHX82
SAT80/81 | On Hold | Harold | Mid June | ProCore Portal | Not Confirmed | 6/10: Jesse replied: we have been on hold due to the VHF donor cable pathway out of the building, its not ready. 6/10: Katie followed up with Jesse B for test reports 4/27: the last time you all had representation on site for an Inspection was on 4/4/25 and at that time, SAT80 Admin & Colo1 were looked at. We have turned over to MS Colo2 and will be turning over Colo3 today. If you all need to get into the “Turned Over” areas then you all need to submit the names of the folks who will be going in the building under a DCAT, an MSOW may need to be submitted as well. Whoever goes in will also need to go through a MS Security Orientation. 4/23: E2 sent test data for SAT80/81 4/22: Katie reached out for GC contract 3/4: S2A needs to hold on a site visit until Mid to late April – that’s when E2Opitics will have completed the PSDAS.
SAT15 | Completed | Harold | 3/30-4/13 | 3/2, SAT15_Test Data (SP folder) | Not Confirmed | 4/8: No longer needed. BW said we can sign off with accurate test results. 3/7: I can probably include COLO 4 as well in this walk, but early April is what we need to shoot for COLO 3. 3/4: Asking for next week
SAT14 | On Hold | Harold |  |  |  | 3/17: Asking for 3/23
SAT14 | Not Needed | TBD | Last week of May | Requested | Not Confirmed | 4/27: Rene Palencia said: I just spoke with our superintendent and we are aiming to be ready for a walk the last week of May. 4/22: Katie reached out to Rene for DAS/ROIP test data report progress
LYH10 / AVC43 / AVC01 / AVC09 | Open | Harold |  |  | Not Confirmed | BIR to use change order to look at public safety
SAT40 | Open | Harold |  |  | Not Confirmed | 9/8: Katie reached out to KS for update. 6/16: Katie reached out to Kevin Shirley for ISP update
FTY02 | Open | Bram |  |  | Not Confirmed
PHX72 | Complete | Harold | July 7th |  | Confirmed | 6/22: Test report submittals complete
YQB06 | Complete | Harold | August 10th |  | Confirmed | 7/6: Vincent will also be there if technical questions arise.
CCO07 | On Hold | Harold |  |  | Not Confirmed | 7/30: Check if Cx-ing is done
CCO06 | Open | Bram | Week of (or after) Sept 21 |  | Not Confirmed | 8/26: Currently cx is tracking for completion by 9/14. If these dates change. AHJ would would follow the next week 9/21. 7/14: Installation and Cx-ing should be done 17-21 Aug
ATL06 | On Hold |  |  |  | Not Confirmed | 7/30: Go to again? COLO turn-ups?
IAD12-13 | On Hold |  |  |  | Not Confirmed | 7/30: Check on status
SAT80/81 | Open |  |  |  | Not Confirmed | 9/8: Emailed Jesse Brierly for PSDAS update
MNZ03 | Open | Bram | End of Sept |  | Not Confirmed

## 2026 Meeting Schedule
| Monday |  |  | Tuesday |  |  | Wednesday |  |  | Thursday |  |  | Friday
| HS | BW | KC | HS | BW | KC | HS | BW | KC | HS | BW | KC | HS | BW | KC
7AM
7:30AM
8AM
8:30AM
9AM |  |  | QRO01 EXP Mtg
9:30AM
10AM | QRO01 Design Meeting |  |  |  |  | AVC17/18 RFI/SUB Review | Verizon MSFT Weekly Touchpoint |  |  | MSFT OneCell Andrew Meeting
10:30AM
11AM | SJC02 - RFI MTG |  | CCO7CA Leads Mtg | [8 empty] | YQB04 Weekly Meeting
11:30AM | [9 empty] | S2 Weekly CL Call
12PM |  |  | PHX80 Leads Mtg
12:30PM
1PM |  |  | CCO08CA Leads Mtg
1:30PM
2PM | [5 empty] | EAT12 OAC Mtg
2:30PM |  |  |  | Weekly Touch Base
3PM
3:30PM
4PM
4:30PM
5PM

## Delivereable_Tracker
Projects | Priority/Status | Scope | AE Due Date | CL Due Date | S2A/CL Due Date | Status | AE Contract | CL Contract
CPQ11 | 5.Completed | Add in Colo 4 to ibwaves | 2025-09-05 |  | 2025-09-08 | 9/25: HS responded that he has issued the deliverables. | 9/25: Contract amendment received. | OpenPO
CCO07 | 5.Completed | Set Up Call with DAS team - submitting permits | Completed |  | Completed | 7/31: Based on RFI #265 for CCO07 | CA | NA
CCO08 | 5.Completed | Descoped colos 3-5. ERRCS design/BOM | 7/21/2025-complete |  | 7/16-complete | 7/14: Final IFP 8/11 6/23: Draft IFP due 7/21. CL work needs to be reviewed against MS scope and confirm all is descoped. | NTP | OpenPO
IAD13 | 5.Completed | IFC Issuance | 8/6/25-completed |  | NA | 7/23: A/E emailed schedule. No CL | CA | NA - Bram to do CAD work
QRO06 | 5.Completed | QRO06 EXP 100% IFR Submittal Print | 8/7/25-completed |  | NA | 8/7: BW delivered files. | CA | NA - Bram to do CAD work
SAT PROJECTS | 5.Completed | Lessons Learned Logs required for SAT 14, 15, 40, 80/81 Projects | Complete 7/29 |  | NA | 7/28: BW - note complete. Not planning on taking any action until PM pushes the issue. | NA | NA
LVL12 | 5.Completed | LVL12 DRB01 REV 1 IFC | 8/15/2025-Completed |  | 8/11/2025-Completed |  | LVL12-14DS | OpenPO
BOYDTON AREA? | 5.Completed | T-Mobile/At&T contracts | TBD |  | TBD | Sounds like TMO will be included. Communicate with Andrews for TMO addition.
CCO08 | 5.Completed | PSDAS Updates to reflect City of Palmetto comments - includes CADS | 7/21/2025-complete |  | Complete | 7/17: A little bit of rework needed. Trey working on it. 7/16: Cads delivered. 7/14: Final IFP 8/11 draft ifp 7/21. CL working on incorporating in comments. 7/10: iBwaves delivered. S2A to review and then give CL OK to proceed with CADS. | NTP | OpenPO
CCO08 | 5.Completed | Final IFP | 8/11/25-completed July |  | Completed | 7/25: Draft IFP was delivered 8/5 | CCO08DS | NA
IAD12-13CA | 5.Completed | submit anticipated monthly hours for the CA associated with descoping only, September forward. | 2025-09-12 |  | 2025-09-12 | 9/24: See email from See email from Chris Kruger about pausing all work on descoping. Chris Kruger 9/10 with spreadsheet link. | CA | NA
CCO08 | 5.Completed | DCN08 IFP Reprint PS Update to remove COLOs 3-5 | 9/29/2025-completed |  | 9/24/2025-completed | 9/29/2025: CCO08 IFC Complete 9/25: Stephen Wright is submitting this afternoon. 9/22: Stephen Wright working on CAD drawings. 8/26: HS working on budget, same as CCO06. CL will be engaged, waiting on quote. | CCO08DS? (confirm we have enough budget) | OpenPO
LVL12-14 | 5.Completed | 100% IFR (lesson learned from LVL12 and update to IFC 2021)10/14: Update floor plan layout and public safety code update | 2025-11-05 |  | 10/27-Completed | 11/04: Katie to mark status completed once invoice is sent to AE 10/27: S2A received Cline work. 10/24: BW gave Stephen go ahead to start updating the CDs 10/23: CL sent over design for BW to review. Then Stephen will begin work. 10/17: CL will get started on this design revision late next week 10/8: Updated to reflect 75 calendar days for AHJ review. IFC: 3/4/26 – Pending DEQ approval 9/30: HS to review public safety to make sure compliant with Virgina state code 8/25: Proposal discussed 8 hours, no CL, BW to work | LVL12-14DS | OpenPO
PHX72 | 5.Completed | Reverse of descope work done in May | 10/31-Completed |  | 10/31-Completed | 11/04: Katie to mark status completed once invoice is sent to AE 10/30: BW set clouded drawings and revisions to Jacobs to cont. in Revit. 10/29: 10/29: BW to send clouded sets and mark-ups to Jacobs telecomm by EOD 10/29. 10/28: BW to talk with Carrie 10/29, morning 10/27: HS completed the change tracker for PHX72 and PHX82 full buildout 10/22: Project back to life. CL to do CAD drawings. (CL did original drawings) 10/21:NTP Received 10/14: BW Confirm budget and scope 9/30: Sent proposal end of august, BW follow up with Jacobs 8/28: CL estimate received for CADS only | TBD | NA
LVL07 | 5.Completed | LVL07 RFI 96.3/96.4 - Issue Drawings | 2025-07-28 |  | NA | 7/30: BW completed | CA | NA
LVL08 | 5.Completed | Consolidate LVL09,10,11 into LVL08 Drawings | 2025-07-29 |  | 7/23-complete | 7/30: BW delivered as part of LVL09 Record Set | Bill to LVL10CA | OpenPO
LVL09 | 5.Completed | Record Set | 2025-07-29 |  | Complete | 7/30: BW delivered. A/E confirmed receipt | CA | OpenPO
QRO06 | 5.Completed | Descope-COMM /ROIP Design Revisions/CADS | 7/18/25-complete |  | Complete | 6/23: Redline drawings sent to S2A; issue record set by 7/22. | CA | N/A
CYS17 | 5.Completed | Issue for Record Set DWG-R1 Record ¦ 7/15/2025 | Complete |  | Complete | 7/10: CL due date 7/10 confirmed on weekly call. | CA | OpenPO
PHX72 | 5.Completed | PHX72 Descope IFC submission | 7/17/2025-complete |  | Complete | 7/10: CL delivered files to S2A | CA | OpenPO
IAD11DCN08 | 5.Completed | DRB - New Headend Mod - 100% IFR | 7/18/25-complete |  | Complete | 7/15: CL delivered files. In S2A court to hand off to A/E | NTP | OpenPO
CCO08 | 5.Completed | IFP Reprint Package for Bidding | 8/14/2025-Completed |  | 8/14/2025-Completed | 8/14: CL to deliver IFP set. | CCO08DS
CCO08 | 5.Completed | CCO08 Design ¦ PKG06-R1 IFP ¦ 8/7/2025 | 8/5/25-completed |  | NA | 7/28: Added to list. No CL | CCO08DS | NA
PHX82 | 5.Completed | Reverse of descope work done in May | 2025-10-30 |  | TBD | 11/04: Katie to mark status completed once invoice is sent to AE 10/30: BW set clouded drawings and revisions to Jacobs to cont. in Revit. 10/29: BW to send clouded sets and mark-ups to Jacobs telecomm by EOD 10/29. 10/28: BW to talk with Carrie 10/29, morning 10/27: HS completed the change tracker for PHX72 and PHX82 full buildout 10/22: Project back to life. CL to do CAD drawings. (CL did not do original drawings and has questions) 10/21: NTP Received 10/14: BW Confirm budget and scope 9/30: Sent proposal end of august, BW follow up with Jacobs 8/28: CL estimate received for CADS only | TBD | NA
QRO02 | 5.Completed | Descope-COMM /ROIP Design Revisions/CADS | Cancelled |  | Cancelled | 7/14: HS confirmed no further aciton. 6/16: HS touch base with Alma. | TBD | ?
IAD11DCN08 | 5.Completed | DRB - New Headend Mod - 50% IFR | Complete |  | Complete | 6/23: CL files delivered - S2A to hand off to A/E. Bill proposal 100% complete after 7/18 deliverable. | TBD | OpenPO
PHX82 | 5.Completed | CAD drawing date/title updates | Complete |  | Complete | 7/16: Proposal was billed 100% complete already. No further invoicing for these efforts at this time. 7/7: we need CAD files - BW did not upload to OneDrive? We only have PDFs on file. 7/2: Need invoice from CL for the CAD updates - apply toward Open PO | CA | OpenPO
BN Campus | 5.Completed | BN Campus Design Revisions | TBD |  | Complete | 6/4: Invoice sent.
BN Campus | 5.Completed | BN7/BN8 Updates | TBD |  | Complete | invoice to be submitted via BN Campus
BN Campus | 5.Completed | LVL08DRB - Spidercloud/OneCell | TBD |  | Complete | invoice to be submitted via BN Campus
CCO06 | 5.Completed | DRB13 – PSDAS & CAD updates. | TBD |  | Complete | 5/13: Kp confirming hours/rate to bill - emailed HS. - completed client invoiced May. | TBD
CCO07DCN07 | 5.Completed | PSDAS updates | TBD |  | Complete | 6/10: Revisions/updates requested from A/E. invoice sent July. | CCO07CA | completed
EAT03 | 5.Completed | Colo 4 did not pass AHJ test | TBD |  | Complete | invoiced in July. 6/23,6/16: Waiting for data from contractor. 5/22: HS requested solution from CL for colo 4 to present to GC - apply towards retainer PO. | CA | OpenPO
EAT12 | 5.Completed | Moving PS Antenna | TBD |  | Complete | invoiced July cycle. 6/10: Trey provided updated response as requested from HS | CA | OpenPO
IAD05DRB10 | 5.Completed | Headend Mod to IAD04 | TBD |  | Complete | 6/23: CL files delivered - S2A to hand off to A/E. Billed in July | NTP | OpenPO
IAD12-13 | 5.Completed | Descoped Colos 3-5. Update design for ERRCS only. | TBD |  | Complete | 5/22: BW handed off files to client. | CA | Confirmed
LVL04-05 | 5.Completed | Record Set | TBD |  | Complete | 5/13: KP forwarded A/E email to BW | NA | NA
LVL09/10 | 5.Completed | ibwaves updates to reflect new dedicated signal source in LVL08 | TBD |  | Complete | 6/20: BW approved CL work to apply to retainer PO. - convert hours and bill A/E CA contract. | CA | OpenPO
MNZ03 | 5.Completed | DRB04 - New Headend Mod | TBD |  | Complete | delivered early June | TBD | OpenPO
PHX72/82DRB | 5.Completed | PHX72 and 82 Descope IFC packages | TBD |  | Complete | 6/5: Packaging info received | CA - contracts to be amended. | Proposal received
QRO01 | 5.Completed | Descope-COMM /ROIP Design Revisions/CADS | TBD |  | Complete | 6/24: BW requested info / way to deliver files to Fernando. | CA | NA
YQB01 | 5.Completed | Descope-Stand Alone Package for Admin+Colo 1. Design revision-minimal coverage in Colos 2-5 | TBD |  | Complete | Follow up: after IFC – contact contractor to have updated ibWave sent via RFI. | CA before IFC deliverables. Then Design PO | N/A
YQB04 | 5.Completed | Descope-Stand Alone Package for Admin+Colo 1. Design revision-minimal coverage in Colos 2-5 | TBD |  | Complete | Follow up: after IFC – contact contractor to have updated ibWave sent via RFI. | CA before IFC deliverables. Then Design PO | Delivered-Invoiced
YQB06 | 5.Completed | Descope - Stand Alone Package Admin+Colo 1. Updated design for min coverage in Colos 2-5 | TBD |  | Complete | ibWave updates to be delivered in IFC package. | CA before IFC deliverables. Then Design PO | Delivered-Invoiced
YTO11 | 5.Completed | DRB09 IFC | TBD |  | N/A | 6/16: BW requested SME contact to schedule review. 6/10: Still waiting on issuance date. Per email from: "If there are no changes, then the only action required will be to update the TTB revision block once we confirm the issuance date" | CA | N/A
YTO11DRB08 | 5.Completed | DRB08 Descope-ROIP revisions+CAD - IFC | TBD |  | Complete | 6/16: IFC date TBD | CA | requested 5/15
YTO40 | 5.Completed | IFC print due 5/1. | TBD |  | Complete | 5/5: Stephen handling. | CA | Delivered
YTO40DRB07 | 5.Completed | DRB-07 Descoping Page-Turn (ROIP, Security, & Structural) | TBD |  | Complete |  | CA | Contract
QRO06 | 5.Completed | QRO06 EXP 100% IFR Q-Print | 2025-07-30 |  | NA | 7/30: BW delivered | CA | NA - Bram to do CAD work
YTO11 | 5.Completed | YTO11- DRB-09 - COLO 3 Fit-out (Package 2) - Issued for Review | 9/12/2025-completed |  | completed | 09/12: BW uploaded docs | CA | YES - Stephen to submit $500 invoice via CL
QRO06 | 5.Completed | QRO06 EXP IFC Q-Print | 10/1/2025-Completed |  | TBD | 9/30: BW to do a print in BB. 7/14: Logged on project task list. | CA | TBD
EAT06-09 | 5.Completed | Redesign to Fremont - 50% IFR 8/29/25 - Invoice to 60% | 2026-01-14 |  | 2025-12-19 | 1/16: Invoice to 60% 1/5: CL (Trey) sent revised designs back to Harold. 12/22: Harold gave feedback to CL 12/9: S2A received floor plans. Trey to use these plans for Microsoft EAT06. CL will begin the model later this week and the design next week. 11/25: Floor plans are still in production, there is some that was associated with the 30% but I think we are still a few weeks away from all the floor plans being available. 11/24: KC asked for update on floor plans 11/17: 30% was pushed to 11/21. So we are actively working on the deliverable this week and will start on the 60% next week. 10/30: Design still on track to start the week of Nov 17-21st 10/29: Katie reached out to Chad Mendall at Stantec 10/28: Katie to reach out to check project status 10/10: S2A will not be starting their work during the 30% design phase. The 30% IFR started this Tuesday, 10/7, and will last six weeks. 10/9: Waiting on floor plans. 10/2: HS sent the revised DCN-01 proposal for EAT06 only. 10/1: Chad Mendal - Correction Needed. The second DCN for the full design will just be for the 2-Story 5-Colo EAT06 building (2.5 Colos over 2.5 Colos). Your DCN is indicating EAT09, so I will need you to amend your DCN to remove any reference to EAT09. 9/30: HS to resubmit pricing 9/30 7/30: Kick off did not happen 8/4 - TBD, 8/14: BW asked to take off list | TBD - contract revision pending | PO from October for $6,750.00
YQB Projects | 5.Completed | Create S2A Org Chart | 11/21/2025-Completed |  | NA | 11/4: First draft sent to HS for review KC to create S2A org chart | ? | NA
LVL12-14 | 5.Completed | LVL13 BOD Updates & Colo Shifts | 11/14/2025-Completed |  |  | 11/17: BW asked CL to implement comments from the A.E/MSFT regarding the LVL13 set | LVL12-14CA | OpenPO
PHX82 | 5.Completed | PHX82 CA Construction DRB13 IFP (COLO 3-5 full scope) | 11/18-Completed |  | NA | 11/18: BW to send in QA form after reviewing designs. 11/17: Ball in Jacobs court. BW to send in QA form after reviewing drawings. | PHX82CA | NA
LVL12-14 | 5.Completed | LVL13 100% IFR Production Deadline: 11/21 – Delivery Due to SRI for QC and posting | 11/21/2025-Completed |  | 2025-11-20 | 11/24: BW to send the DAS drawings and model for the 11/25 deliverable. Please also complete the drawing list, answer all related BIM 360 issues and confirm that the deviations log is up to date. Bram forwarded print instructions to Stephen so he can print the final set. | LVL12-14CA | OpenPO
PHX12 | 5.Completed | Record Drawings | 1/29/2026-Completed |  | NA | 1/26: BW sent markups to Bart Spencer of Jacobs to update the Revit files. 1/23: Carrie Wright gave access to IFC and asked Jacobs team to implement S2A markups. Stephen engagsed as backup in case we need to redo the CADs. 12/11: Howard Way sent the as-builts 12/9. Katie to complete as-builts with assistance from Bram. 12/3: Howard Way will let the Team know when all Contractor As-builts have been received and approved, to begin Record Drawing preparation. 12/1: BW reached out to Howard Way and Brandon Gilyard. 10/30: S2 Advisors still needs to receive and approve the PHX12 COLOs 2-5 ERRCs as-builts. The General Contractor has not yet submitted all as-builts for the PHX12 Project to begin Record Drawing preparation. 5/13: A/E to schedule call with S2A to review drawings once they are ready. | CA | TBD
PHX71 | 3.In Queue | Redlines/Record Drawings | TBD |  | Complete | 10/30: Andrea gave update that installation and testing are completed. Did not give carrier agreement update. 09/15: BW emailed Andrea requesting status update. 5/27: CADS delivered from Stephen. Submission date to A/E TBD. Andrea Frazier-Sanches to advise, 9/22 - BW has reached out for direction on how to submit deliverables, has not received direction. | CA | Contract
YTO11 | 5.Completed | YTO11 - IFC Refresh for Package 3 & 4 (COLOs 2 and 3) | Complete-10/03/25 |  | Complete-10/03/2025 | 11/04: Did CL bill for work on this deliverable? Once confirmed, move to Completed. 9/25: Stephen Wright is working on this. 6/27: A/E requests estimate of hours and timeline to complete. | CA | N/A
IAD12 | 5.Completed | IFC Issuance | TBD |  | TBD | 9/3: BW advised to close. No action needed.8/12: IFC date TBD, AE update ETA week of 8/18 | CA | NA - Bram to do CAD work
LVL07DRB03 | 5.Completed | IFR Issance | 9/9/2025-completed |  | 2025-09-10 | 9/9: BW email to Mira confirming delivery for afternoon 9/10. BW forwarded email thread confirming CA contract to be billed for effort. | CA | NA - Bram doing the work.
YTO40DCN03 | 5.Completed | DCN03 Colo 3,4,5 De-Scoping Efforts | TBD |  | Complete | 6/23: CL given approval to proceed. | CA | N/A
LVL06 | 5.Completed | LVL06 - as-builts | 10/2/2025-Completed |  | N/A | 9/30: BW to send markups. 9/22: SwansonRink to do CAD drawings, BW to confirm 9/19: S2A to verify that we have redlines | CA | N/A
SJC02 | 5.Completed | SJC02 - IFP REV4 | 10/8/2025-Completed |  | Complete, need to print | 11/04: Is this new work, or is this covered by the $6,810 that was billed to completion in September? 10/7: Jacobs sent the upload folder 9/22: Stephen Wright to incorp ROIP revisions and CAD package, 9/19: S2A to reivew the status of the drawings | DS | OpenPo
SAT89 | 5.Completed | SAT89 S2 Advisors CA Contract | N/A |  | 2025-09-26 | 10/7: WSP sent contract. HS to sign contract. 10/6: WSP updated COI insurance amounts to reflect S2A coverage. Still waiting on corrected contract. 10/2: WSP to correct SAT89 & 90 CA contract. Waiting on approval of COI insurance coverage. 9/24: Contract needed to complete RFIs. KC reached out to Garr DiSalvo. Garr is traveling this week. | N/A | N/A
AVC43 | 5.Completed | Benchmark Data Email Thread- Ask GC for a BM status report | N/A |  | N/A | 10/2: BW has LYH10 BM status report but still waiting on AVC43. 9/24: BW to ask GC for BM status report | N/A | N/A
LYH10 | 5.Completed | Benchmark Data Email Thread- Ask GC for a BM status report | N/A |  | N/A | 9/24: BW to ask GC for BM status report | N/A | N/A
BOYDTON AREA | 5.Completed | Send access requirements | N/A |  | N/A | 9/25: Refer to email chain with Joshua Moore 9/25 | N/A | N/A
BOYDTON AREA | 5.Completed | Update hardware quotes so MSFT can process PO | N/A |  | N/A | 9/25: BW refer to email chain with Clark Martin | N/A | N/A
YTO11 | 5.Completed | YTO11 - DCN-11 - Package 4 & Specification Refresh (COLO 5 Fit-Out) | TBD |  | TBD | 11/13: Wayne confirmed 80 hours for each discipline, DAS and ROIP equal to $36,320 10/28: HS sent in hours request for 60 hours 10/22: Hours estimate request from Stantec. BW estimates it will take of 15 hours to review, print, and attend meetings.
CLT04/10/17 | 5.Completed | FInalize contracts and insurance coverage amounts | TBD |  | TBD | 10/30: Megan sent clarification on contract amounts. 10/29: KC reached out to Megan and asked for clarity on contract amounts and insurance coverage. | CA | TBD
PHX72 | 5.Completed | DRB14 (not 13) Full Buildout | 11/5/2025-Completed |  | NA | 10/31: Mahima requests QA firms to make the IFP submission on 11/5. BW: Wait until Jacobs confirms the drawing updates are completed. | PHX72CA
LVL12-14 | 5.Completed | 100% IFR (lesson learned from LVL12 and update to IFC 2021) | 11/5/2025-Completed |  | 2025-11-05 | 11/7: Mira said drawings looked good. 11/5: BW to send spec section # 275019 on Monday, 11/10 11/5: Comments from ML: (SW to work on this) - We are missing spec 275019. Please provide. - Please update the PS DAS drawing list. - Please update the TB on all drawing sets & re-upload. 11/4: Waiting to hear back confirmation from Mira Lammers if changes are needed/QA form completion | LVL12-14DS | OpenPO
SAT89 | 5.Completed | Vertical Construction IFC | 11/7/2025-Completed |  | 2025-11-06 | 11/7: Still need to update CAD title blocks and upload to WSP Sharepoint. SW uploading updated files to SAT89 project folder. Waiting on access from Garr to upload to AE folder. | SAT89CA | OpenPO
PHX72 | 5.Completed | PHX72 CA COLOS 3-5 Restart of CA | 2025-11-14 |  | NA | 11/12: Harold send hours to Andrea. Waiting on AFS response. Andrea Frazier-Sanchez asks HS that he adjust the time and relook at the proposal. Looking at a total of 50 weeks. She asks if HS can return proposal by 11/14. | PHX72CA | NA
PHX82 | 5.Completed | PHX82 CA Construction DRB13 IFP (COLO 3-5 full scope) | 2025-11-17 |  | 2025-11-14 | 11/17: Ball in Jacobs court. BW to send in QA form after reviewing drawings. 11/13: Send in QA form 11/12: BW sent markups and instructions. In Jacobs court now.Jacobs is doing the CAD and S2A is doing the QAQC. We will be re-issuing all drawings from PKG04-06 in this package. All drawings have been marked as REF. We will also need to issue and changes to revert scope back from the descope DRB10-IFC. | PHX82CA | OpenPO
PHX13/14 | 5.Completed | 11/6 Site Visit Reports | 11/10/2025-Completed |  | NA | HS to complete reports 11/12 or 11/13 | PHX13CA
SAT14 | 3.In Queue | SAT14/15 RFQ Clarifications | ? |  | ? | 12/1: Stuck in MSFT approval 11/17: BW to follow-up 11/13: SW asked for original CADS. CL sent proposals. Need to know scope, if a DS contract is coming, when project will start. | ? | Proposal received
SAT15 | 3.In Queue | SAT14/15 RFQ Clarifications | ? |  | ? | 12/1: Stuck in MSFT approval 11/17: BW to follow-up 11/13: SW asked for original CADS. CL sent proposals. Need to know scope, if a DS contract is coming, when project will start. | ? | Proposal received
LVL12-14 | 5.Completed | Issue #2400 was assigned to you | 11/18/2025-Completed |  | NA | Matt Benson assigned BW issue #2400. | LVL12-14DS | NA
CHI11 | 5.Completed | Troubleshooting for CHI10 DAS headend issue | NA |  | NA | 12/3: S2A to provide a high level technical review of proposal.
LVL12-14 | 5.Completed | LVL13 Redesign IFB Delivery Guidelines | 12/18/2025-Completed |  | NA | 12/12: IFB is postponed and will likely be at the end of January. 12/3: Bram to print set | LVL12-14DS
SJC02 | 5.Completed | SJC02 Building CA Proposal | 2025-12-16 |  | NA | 12/12: Updates pricing
IAD12-13 | 5.Completed | Design DCN for IAD12&13 Restart | 2/5/2026-Completed |  | 2026-02-03 | 2/10: Bram, was this uploaded successfully on 2/5? 2/1: This note shall be placed on all drawings: “DRB06 drawings shall supersede DRB04 documents. Any items previously installed under DRB04 shall be re-installed per the DRB06 documents” . 1/30: Stephen to deliver 2/3 1/23: Stephen working on CAD floorplans 1/16: Reliant on IAD11. Contractor who installs IAD11 signal source must install IAD12/13 expansion/commissioning. Whoever installs the headend in 11 owns it, they need to introduce any changes to the carriers. 1/5: Propose moving to a DSS 1/5: Same direction. MSFT may have additional items that may come up but for now get drawings back to point when descope was announced. 12/22: Katie asked for deliverables schedule. 12/18: Stephen to work on CADs. 12/16: Work with Matt McCarthy and Jack O'Brien to determine if reverting models to March of 25 is the best approach or just undoing Descope items from the current set.Please commence to get your drawing sets back to the point when descope was announced. (Approx. 3/25) Please be sure to include any changes made for QA/QC purposes and any SME comments that are to stay in the final build. | IAD12-13DS | Open PO
CLT04 | 5.Completed | DRAFT DRB01 Drawings | 1/8/2026-complete |  | 1/7/2026-complete | 1/5: CL (Stephen) confirmed 1/8 delivery date and asked to set up time with Bram today or tomorrow. 12/24: Please upload CLT04 Draft DRB01 Drawings HERE by EOD 1/8/2026. Please make sure all changes have been clouded and the ​DRB01 Narrative​ has been completed for your discipline. Due for DAS/ROIP: -BOM Updates -Rack elevation and requirement update -Update to ISP circuits | CLT04CA | CLT04CA
CLT04 | 5.Completed | FINAL DRB01 Drawings | 1/16/2026-Completed |  | ? | 1/16 CADs/Drawings are complete. We are waiting on any MSFT comments. Bill to MSFT on Friday. 1/5: Meg Plank sent delivery instructions and folder 12/24: Please upload CLT04 Draft DRB01 Drawings HERE by EOD 1/8/2026. Please make sure all changes have been clouded and the ​DRB01 Narrative​ has been completed for your discipline. Due for DAS/ROIP: -BOM Updates -Rack elevation and requirement update -Update to ISP circuits | CLT04CA | CLT04CA
LVL11 | 5.Completed | LVL11 Record Sets | 1/20/2025-Completed |  |  | This isn’t due until 1/20 12/29: CAD exports for backgrounds need to be shared with the team (1/13) | LVL11CA
YTO40 | 5.Completed | Updated IFC print/refresh: DCN-11/DRB-13 - Packages 2, 3 & 4 with Specifications Refresh (COLOs 3, 4 & 5 Fit-Out) | 1/9/2026-complete |  | NA | 1/6: No major changes | YTO40CA
LVL12-14 | 5.Completed | LVL13 Redesign Issue for MSFT Review Delivery | 2026-02-11 |  | NA | 2/11: Bram will update title block in BlueBeam. 1/30: The SME’s would like to have a formal review period before IFC is released for LVL13. We only need to issue launch and buildout drawing packages, but at the point of issue, these backages should be complete and essentially ready for IFC. There will be no admin QC for this deliverable. Please complete and engineering QC and admin QC of your drawings before delivery. | LVL12-14DS
SAT89 | 5.Completed | Vertical Construction of SAT89 Slides | 1/8/2026-complete |  |  | Recycle slides that Bram sent Clark | SAT89
FYT01/02 | 5.Completed | Combine FTY01/02 iBwaves | 1/23/26-completed |  | 1/23/26-completed | 1/23: Trey sent the link to the combined FTY01/02 design for Verizon to review. 1/20: AE approved CL revision. CL waiting for Benchmark reports. 1/12: CL is requesting $2000 for revision | FTY01? | Open PO
FTY03 | 5.Completed | FTY03 DRAFT IFC QC | 2/6/2026-Completed |  | NA | 2/10: Bram, was this uploaded successfully on 2/6? 2/3: Bram working on this week 1/30: Bram to submit. Still waiting on title block instructions. 1/29: Stephen to update TB. Add note to title page about rebroadcast agreements must be amended by the owner of the sisnal source equipment (Linx). No other contractor is permitted to work on signal source except for the owner. 1/26: Katie + Bram to meet to discuss 1/15: Assigned to Katie. | FTY03DS additional funds, see 1/29 email | NA
CLT10 | 5.Completed | CLT10 DRB01 QC Sets | 2026-02-27 |  | NA | Email from Meg Plank 2/10: Please upload CLT10 DRB01 QC Sets HERE by EOD 2/27/2026. | CLT10CA | Open PO
CLT04 | 5.Completed | FINAL DRB01 Drawings | 1/21/2026-completed |  | NA | Please upload CLT04 Final DRB01 Drawings ​​HERE​​​​​​ by EOD 1/21/2026. Please make sure all changes have been clouded and the ​​​DRB01 Narrative​​​ has been completed for your discipline. | CLT04CA | NA
CLT17 | 5.Completed | CLT17 DRB01 IFC | 2026-03-05 |  | NA | 3/2: Set is complete, waiting on comments from MSFT 3/2: Confirmation from Meg Plank: Please have drawings and CAD files uploaded by EOD 3/5. 2/25: As a reminder, please upload the CLT17 DRB01 IFC drawings and specs (if needed) HERE by EOD 3/5/26. 2/10: Please update the revision block accordingly and make sure all changes are clouded! Please also make sure the ​​​CLT17 DRB01 Narrative.docx​​ has been updated for your discipline! Please upload CLT17 DRB01 QC Sets ​HERE​ by EOD 2/13/26. | CLT17CA | Open PO
CLT10 | 5.Completed | CLT10 DRB01 IFC | 3/19/2026-completed |  | ? | 2/10: Please upload CLT10 DRB01 IFC Drawings ​ HERE EOD 3/12/26. Please update the revision block accordingly and make sure all changes are clouded! Only revised sheets need to be issued! Please also make sure ​the ​CLT10 DRB01 Narrative.docx​ has been updated for your discipline! | CLT10CA | Open PO
FTY03 | 3.In Queue | FTY03 DRAFT IFC QC | 2026-02-17 |  | NA | 2/11: Resubmit for the 2/17 submission | FTY03CA | NA
EAT06 | 5.Completed | New 2-Story Design Fremont | 2/6/2026-Completed |  | NA | Bram, can I mark this as completed and invoice? 2/5: QA-QC process contines with Stantec 2/3: Stephen delivered QA-QC set. Bram to submit. | EAT06CA | EAT06 contract
LVL10 | 5.Completed | Record Docs | 2026-02-23 |  | TBD | 1/30: ML sent delivery guidelines. Please note, record docs need to be updated to include all RFIs and the received As-builts. | LVL10CA
CLT17 | 5.Completed | CLT17 DRB01 IFR - Submit to PM | 2026-02-19 |  | ? | 2/10: Please upload CLT17 DRB01 Drawings ​​HERE​​​​​ by EOD 2/19/26. Please update the revision block accordingly and make sure all changes are clouded! Only revised sheets need to be issued! | CLT17CA | Open PO
CLT17 | 5.Completed | CLT17 DRB01 IFC | 2026-02-26 |  | ? | 2/10: Please upload CLT17 DRB01 IFC Drawings HERE by EOD 2/26/26. Please update the revision block accordingly and ensure all changes are clouded. Only the revised sheets need to be issued. These sets will need to be signed and sealed. Please also make sure ​the ​​​CLT17 DRB01 Narrative.docx​​ has been updated for your discipline! | CLT17CA | Open PO
Cherry Creek Garage | 3.In Queue | ? | ? |  | ? | ? |  | $14,250 in proposal for CAD drawings and iBwave designs
PHX82 | 3.In Queue | DRB13 - ISSUED FOR CONSTRUCTION | 2026-03-05 |  | ? | 3/5: No follow-up since January email 1/14: This package is no longer issuing on 1/20. This IFC date has been pushed back to 3/5. DAG will send new emails 2 weeks prior that issuance date. 1/13: May want QA-QC form but Jacobs will have to send drawings. 1/12 Jacobs will print the set as they did the CADs. BW coordinated yesterday. 1/6: Refer to 1/6 email from Carrie Wright. | PHX82CA | NA
CLT10 | 5.Completed | CLT10 DRB01 IFR - Submit to PM | 2026-03-05 |  |  | Please update the revision block accordingly and make sure all changes are clouded! Only revised sheets need to be issued! | CLT10CA | Open PO
EAT06 | 5.Completed | EAT06 IFP | 2026-03-02 |  | ? | 3/2: QA-QC set was uploaded 2/25: Draft Set Posted to ACC0 (for QA-QC Review), Including Draft Reports / Calculations (Katie to help) | EAT06-09REV | EAT06 CL Proposal
LVL12-14 | 5.Completed | Title Block Update - Katie | 2026-02-27 |  | ? | 2/25: ML sent email with instructions on 2/24 | LVL12-14DS
MNZ04 | 4.Completed | 90% IFR | 5/6/2026 -complete | TBD | 4/20: BW to markup drawings and coordinate with Telecom. | 5/5: BW Completed. 5/4: BW Done with CADs. Need Title block info 4/20: BW to markup drawings and coordinate with Telecom.4/8: Bram to do redlines. Still have not received confirmation from PM. 4/3: HS/BW need to review and mark up the set. We likely will not have to include centerline—just not sure yet. 3/30: Look into meetings 3/9: Katie to cont. to follow-up 2/25: project kicked off today—here is a proposed schedule. There will be some site changes which is the reason for the delayed start. | MNZ04DS | Open PO
MNZ04 | 3.In Queue | 100% IFR | 2026-05-05 | TBD | TBD | 2/25: project kicked off today—here is a proposed schedule. There will be some site changes which is the reason for the delayed start. | MNZ04DS | Open PO
MNZ04 | 3.In Queue | IFP | 2026-05-13 | TBD | TBD | 2/25: project kicked off today—here is a proposed schedule. There will be some site changes which is the reason for the delayed start. | MNZ04DS | Open PO
MNZ04 | 3.In Queue | IFC | TBD | TBD | TBD | 2/25: project kicked off today—here is a proposed schedule. There will be some site changes which is the reason for the delayed start. | MNZ04DS | Open PO
EAT06 | 5.Completed | Drawing Index for the IFP | 2025-02-27 |  | ? | 2/25: Drawing Index for IFP (Katie to help)
EAT06 | 5.Completed | EAT06 Final Drawing | 2026-03-05 |  | ? | 2/25: All Final drawings (PDF, Revit, CADD) posted to ACC, including separate packages. All specifications (PDF, Word) posted to ACC (Katie to help) | EAT06-09REV | EAT06 CL Proposal
CHI11 | 3.In Queue | Test Data prior to site visit - Bram | 2026-03-04 | NA | NA | 3/30: Reschedule site visit, maybe 4/22 or 4/14 3/2: Ron sent DAS test data ahead of site visit | CHI11 | NA
EAT12 | 5.Completed | Test Data prior to site visit - Harold | 2026-03-04 |  | NA | 3/2: Chandler sent DAS test data ahead of site visit | EAT12
LVL12-14 | 5.Completed | LVL13 Redesign IFC | 3/6/2026-completed |  | ? | 3/2: IFC deliverable due date was pushed back to 3/11/26 | LVL12-14DS
LYH10 | 3.In Queue | Tranche 1 Record Documents Issuance | ? | TBD |  | 4/3: BW asked Trey to include contractor benchmark in deliverable 3/30: Still waiting on quote from Stephen 3/19: SW meeting with BW to discuss proposal 3/18: Stephen Wright putting together a proposal | LYH10CA | ?
FTY03 | 5.Completed | FINAL IFC - FINAL UPLOAD | 2026-04-01 | TBD |  | 3/10: Please upload FTY03 IFC Final Drawings and Specs ​​HERE​​ by EOD 4/1/2026. We will issue clean and clouded sets. Please note that the clean sets must be signed | FTY03DS | ?
FTY03 | 5.Completed | FTY03 FINAL IFC - QC | 2026-03-25 | TBD |  | 3/10: Please upload FTY03 Final IFC QC Drawings ​HERE​ by EOD 3/25/26. QC Review: 3/26 - 3/31 | FTY03DS | ?
CCO07 | 5.Completed | Both PSDAS ROUs will move to the FCR | ASAP | 2026-03-27 |  | 3/18: Begin the design next week for CCO07 and you will receive on 3/27. If we can bring this in any then I will let you know right away. | CCO07 | Open PO
MNZ03 | 5.Completed | Part 20 Update | ? | ? |  |  | MNZ03 | Open PO
CCO07 | 5.Completed | CAD Update: DRB09 IFC AHJ ROU Relocation | 2026-04-06 | 2026-04-01 |  | 4/6: BW uploading to SP today Stephen sending drawings on Wednesday, 4/1 | CCO07CA | Open PO
YTO11 | 5.Completed | Update the DRB-13 drawing sheet and specification section lists for the DAS and ROIP disciplines | 4/16/26-Completed | NA |  | 4/14: TB update, need due date and packaging update 4/6: The change log entries can wait until the Package 4 refresh effort is ready for review. | YTO11CA | NA-BW to do CAD work
LYH10 | 5.Completed | Verizon Package creation with benchmark. | 4/13/2026-completed | 2026-04-09 |  | 4/9: Trey completed 4/9 4/9: Trey sent the design for LYH10 that has the benchmark data and Verizon predictions added. | LYH10CA | Open Po
CCO08 | 5.Completed | update this design to follow the CCO07/CCO06 design | Completed | 2026-04-17 |  | 4/14: BW to reach out to Howard for update/due date 4/13: Trey sent revised design for CCO08 with the remotes moved into the FCR. and the passive network rebalanced 4/10: Stephen to work on this next week | CCO08DS | Open PO
QRO01 | 5.Completed | QRO01 COLO3/4 Cold Shell | 4/27/2026 | 4/23/20 |  | 4/13: I updated the BOM pages in the PDF to match the excel breakouts, added the heat maps for the ROIP with only COLO2 connected, and printed the PDFs with the antenna layout page added. 4/9: CL has scheduled | QRO01 | Open PO
YTO40 | 5.Completed | DRB-07 Cancellation: Review Change Log | 2026-04-15 | NA |  | 4/14: BW to submit change log 4/14: We’ve been asked by MSFT to review the attached change log and highlight any “quality of life” changes that were included in DRB-07, unrelated to descoping, that should remain in GC scope. | YTO40CA | NA
PHX73 | 5.Completed | DAS Package Support - IFP | 4/16/26-completed | NA |  | 4/14: Katie to revise proposal, only 24 hours for QA-QC and support 4/14: Jacobs did this set, waiting to see if anything is needed from S2A. | No Contract | NA
PHX73 | 5.Completed | DAS Package Support - IFC | 2026-04-20 | NA | 4/14: Katie to revise proposal, only 24 hours for QA-QC and support 4/14: Jacobs did this set, waiting to see if anything is needed from S2A. | 4/17: Submit QA-QC form | NA
CCO08 | 5.Completed | ISSUE DRB01 to AHJ and DCE | 5/15/2026-completed | NA |  | 5/11: Katie get update from BW 4/28: This is a reprint. | CCO08CA | Open PO
CCO08 | 5.Completed | DRB01 Review Set | 4/20-Completed
CHI05 | 5.Completed | Site Visit Report | 2026-04-24 | NA |  | 4/22: Site visit report due after site visit on 4/22 | CHI05CA | NA
CHI11 | 5.Completed | Site Visit Report | 2026-04-24 | NA |  | 4/22: Site visit report due after site visit on 4/22 | CHI11CA | NA
LVL11 | 3.In Queue | ON HOLD: Record docs for PSDAS | TBD | NA |  | 5/7: Mira L. said, these are on temporary hold 4/28: BW to work on 4/23: Microsoft has requested that we issue RoIP, DAS, and PSDAS record docs for LVL06 and LVL11 even though there are likely to need updates in September. | LVL11CA | NA
LVL06 | 3.In Queue | ON HOLD: Record docs for ROIP, DAS, PSDAS | TBD | NA |  | 5/7: Mira L. said, these are on temporary hold 4/28: BW to work on. DAS and PSDAS needs an update 4/23: Microsoft has requested that we issue RoIP, DAS, and PSDAS record docs for LVL06 and LVL11 even though there are likely to need updates in September. | LVL06CA | NA
FTY01 | 2.Open | Record Drawings | Postponed until further notice | TBD |  | 8/17: Katie spoke on the phone with Lee. No new updates, other than saying he would put us in touch with the contractors. He said he would just need a PDF of the record drawings. 7/27: Katie spoke with Lee on the phone, Lee said we won't be getting as-builts but we should set up a time to connect with the contractor to compare models. Still aiming for 8/3 record drawing due date. Lee is sending Katie contacts and said to hold tight on record drawings until we have print instructions. 6/30: Lee said the game plan is a 6-week record set drawings from 6/23-8/3. However we do not have as-builts. "Last week Skanska seem to think that can be done. I will formally make a request this week. These milestones were created by us so if we need to adjust or if the GC holds us up we can reset expectations." 6/23: Lee Percy sent out a first coorespondence about Record Drawings. No due date yet. 6/9: Katie reached out to Lee Percy for update as Peter Ngo is no longer with Stantec 5/13: Record drawings currently delayed 5/11: Funding secured. Katie reached out to Stantec to ask about deliverables schedule and meeting schedule. 5/1: Katie left a vociemail with Carol Lusby asking about funding and sent a follow-up email. 4/28: Wait until additional funding is secured. | FTY01 | TBD
CHI11 | 5.Completed | Record Drawing Issuance | 5/21/2026-completed | 2026-05-08 |  | 5/19: Katie followed up with Sultan to ask about due date and title block. 5/11: Katie to review and submit. Reached out to Syska for folder access. 5/4: Stephen working on set. 4/30: Please track to have final PDF’s, Models, CAD files and NWC Exports by COB Tuesday. May 12th Issuance Date: 05.14.2026 | CHI11 | Open PO
PHX71 | 5.Completed | Record doc for All systems | 5/5/2026-Completed | NA | 4/30: BW Completing CADs | 5/1/2026: BW Finished Record set. 4/30: BW added, and working on this deliverable 4/30: BW added, and working on this deliverable
CPQ04 | 3.In Queue | Commercial DAS design updates and CADs | TBD | TBD |  | 7/17: Leticia sent contract 7/6: Leticia said they are currently working on the 30% and DAS will be later in the project 6/3: Leticia send she would send the contract to us the week of the 22nd 6/1: Katie followed up with Leticia. 5/26: Katie followed up with Leticia. Will set up mtg tomorrow if we don't hear back. 5/22: Leticia will have an update for us next week 5/21: Katie reached out again 5/13: Katie reached out again 5/11: Katie reached out again 5/1: Katie reached out to full Deerns team about floor plan and schedule. 4/30: Stephen to help with design and CADS. Waiting on Deerns to send schedule and updated floor plans. | CPQ04DS | OpenPO
YTO11 | 5.Completed | IFC Submmission | 5/6/2026-completed |  | BW to print | 5/11: Katie to double check completed with BW 5/11: Checking with Bram if this was submitted
LVL10 | 5.Completed | Headend Redesign | TBD | 5/13/2026-complete |  | 5/15: Trey sent revised drawings to Harold 5/11: Trey begins work and will have back to S2A on Wednesday, 5/13. Just updating the last package we submitted, but not the CADs. Please cloud the changes. | LVL10CA | OpenPO
LVL11 | 5.Completed | ROU Update | TBD | 5/13/2026-complete |  | 5/15: Trey sent revised drawings to Harold 5/11: Trey begins work and will have back to S2A on Wednesday, 5/13. Just updating the last package we submitted, but not the CADs. Please cloud the changes. | LVL11CA | OpenPO
CHI05 | 5.Completed | Record Drawings | 2026-07-08 | 2026-07-02 |  | 7/8: Katie getting folder access from Andrew K 6/26: Stephen to have back to S2A on 7/2 6/17: Katie getting quote from Stephen/CL. 6/16: S2A received as-built drawings 6/9: Katie reached out to Tadgh Spillane (Walsh) for as-builts timeline 6/3: Andrew Krebs asked up for a schedule of when the contractor should have as-builts to us for record drawings 5/26: Katie asked Andrew Krebs and Yolanda Taylor for deliverables schedule
SAT40 | 3.In Queue | Record Drawings | TBD | TBD |  | 7/27: Ericsson signal source was installed this week for Verizon and the integration/Cx will start next week. 6/8: Katie reached back out to Cris 6/3: Katie reached back out to Cris 5/26: Katie asked Cris Landfeld for deliverables schedule
PHX13 | 5.Completed | Record Drawings | 2026-06-17 | TBD |  | 6/16: Katie met with Jacobs team. 6/10: Katie to complete 6/8/: Katie will send markups to Bart Spencer's team to create record set. 5/26: Katie to work on this 5/26: S2A confirmed we had redlines. Katie asked Andrea for deliverables schedule. Jacobs did the CADs. S2A will need to: - Download the Redlines & let the Jacobs team know that they did the CAD drawings. S2A will provide redlines on what needs to change from the IFC issuance. - Compare Asbuilds/Redlines to the IFC set which was used for construction. (look at Record Drawings TB to get the right issuance) - Cloud each change on the IFC set and explain what needs to be changed on each page. - Create a table with each drawing name and a description of what needs to be addressed on each page. | PHX13 | Open PO
CCO08 | 5.Completed | DRB-01 IFC | 6/11/2026-Complete | 2026-06-11 |  | -Stephen to complete EOD 5/10, or 5/11 With the City having approved CCO08 DRB-01 IFP, I have scheduled CCO08 DRB-01 IFC for June 16th so we can issue this last AE deliverable and begin project close-out. | CCO08 | Open PO
YQB04 | 2.Open | Record Drawings | 2026-09-28 | TBD |  | 8/10: Received as-builts. 8/6: Katie reached out to Bruno for second time about as-builts expected this week 8/4: Should receive as-builts from contractor 7/27: Still have not received as-builts 7/7: Grace confirmed on 6/26 that there are no as-builts yet 6/9: Katie asked Harold if we can assign/schedule record drawings | YQB04 | Open PO
PHX14 | 4.Invoice | Record Drawings | 8/26/2026-complete | 2026-08-20 |  | 8/20: Stephen updating title block, S2A has specs 7/17: Will receive print instructions two weeks before due date 6/26: Stephen to have back to S2A on 7/2 6/17: Katie getting quote from Stephen/CL. | PHX14 | Open PO
PHX73 | 5.Completed | Review Record Drawings | 2026-06-19 | TBD |  | 6/17: Katie asked Mahima for due date
PHX13 | 4.Invoice | Record Drawings | 2026-08-06 | NA |  | 7/7: S2A meeting with Jacobs, unless postponed to Wednesday 7/3: Katie sent markups to Jacobs 6/22: Katie send PHX13 markups to Bart Spencer
IAD05 | 3.In Queue | Record Drawings | TBD | TBD
QRO01 | 5.Completed | Well House - QRO01 Colo EXP Design | 7/8/2026-Complete |  |  | 7/8: Harold to answer questions about well house/DAS
QRO01 | 5.Completed | Well House - QRO01 Colo EXP Design | 7/24/2026-completed | 2026-07-17 |  | 7/21: Katie to update DAS IFR TB in BB and submit 7/17: Stephen to upload today 7/14: **GET PRINT INSTRUCTIONS BEFORE STEPHEN LEAVES** Harold to ask Stephen to do CADs, edited scope incorporated into the design to add DAS/ROIP to well house, will most likely not make peer review but will make 100% deadline on 7/24
PHX13 | 4.Invoice | Record Drawings | 2026-08-17 |  |  | 8/13: Received print instructions 8/12: Bram reviewed Katie's markups. Bram to match markups to RFI/submittals. 7/15: In MSFT court, may receive comments
PHX81 | 2.Open | Record Drawings | TBD | 2026-09-20 |  | 9/10: Reached out to Howard Way again for record drawings 7/22: Stephen to complete | PHX81 | Open PO
QRO01 | 2.Open | QRO01 IFC Package - Peer Review | 8/24/2026-Postponed until further notice | NA |  | 8/28: Print for IFC 8/21: Print for peer review 7/27: DAS CADs need to be updated with correct TB information | QRO01 | NA
PHX73 | 4.Invoice | Drawing Specs | 2026-07-29 |  |  | 7/27: Submit specs by the EOD Wednesday 7/24: Katie sent specs to Bart and Nick
PHX73 | 4.Invoice | PHX73 IFC Package | 8/5/2026-Completed |  |  | 7/29: Jacobs (Julie) confirmed they are submitting. Katie asked to review before final submission. 7/28: Katie to reach out to Jacobs to send packages to S2A ASAP for review before getting submitted on 8/5 7/24: Katie confirming with Jacobs they are to submit drawing packages
QRO01 | 2.Open | QRO01 IFC Package - Print for IFC | 8/28/2026-Postponed until furhter notice | NA | 8/28: Print for IFC 8/21: Print for peer review 7/27: DAS CADs need to be updated with correct TB information | 8/28: Print for IFC 8/21: Print for peer review 7/27: DAS CADs need to be updated with correct TB information | QRO01 | NA
YQB01 | 2.Open | Record Drawings | TBD | TBD |  | 9/10: Katie met with Rosa, still awaiting DAS as-builts. Stephen to do record drawings | YQB01 DCN | Open PO
YQB06 | 2.Open | Record Drawings | TBD | TBD |  | 9/10: Katie met with Rosa, still awaiting DAS as-builts. Stephen to do record drawings | YQB06 DCN | Open PO
Note on I23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Kristen Pearcy Do I typically put OpenPO for CL's work? Reply: If the deliverable is being tracked against the open po then yes. Did you add anything to the open po tab? Reply: @Katie Choate Let's cover this tomorrow and make sure column H gets filled in.

## RFI_Submitals
Notes: | Morrison Hershfield (Stantec) | requests a follow up email when answering. Said BlueBeam doesn't always send a notification when something is answered.
| SAT Projects: | FOLLOW PAGE GUIDELINES!!! - And add 'S2A' to the file name when responding.
| Swanson Rink | Send a follow up email confirming responded to in BB. LVL / AVC, etc.
| YTO40CA | Refer to YTO40CA guidelines PDF.
Added | Project | Description | Due | Status | Completed Date | Comments
2024-01-23 | MNZ03 | RFI266.1 Voltage types for ROIP | 2025-01-27 | Completed |  | BW completed 1/27
2024-07-12 | AVC01 | AVC01: Action Required for Submittal (#663.0: MC Dean - DAS COLO 3 As-Builts) | 2024-07-19 | Completed 7/23 |  | 7/23: Hector Hernandez sent reminder
2024-07-12 | AVC43 | AVC43 due 7/12: AVC 43 RFI 27.012.0 - FCR PDAS Cabinet Location - 22-60846 - due 7/12. | 2024-07-12 | Completed
2024-07-12 | IAD03 | 275019-22.1 - NTI, IAD03 DAS Closeout | 2024-07-23 | Completed-7/19
2024-07-12 | IAD11 | IAD11 due 7/16: 275019-13.1 - RoIP, Cellular, & Public Safety DAS Final Closeout Package | 2024-07-16 | Completed
2024-07-12 | LVL11 | LVL11 due 7/22: LVL11-273241-007-R0 - (ComNet) - PSDAS System Des - 22-60853 | 2024-07-22 | Completed
2024-07-12 | PHX13 CA | PHX13 CA - D3127062 - Submittal 273241-001 - DAS System - due 7/23 | 2024-07-23 | Completed 7/21
2024-07-12 | PHX13 CA | PHX13 CA - D3127062 - Submittal 275019-002-00 - DAS System - due 7/23 | 2024-07-23 | Completed 7/21
2024-07-12 | QRO06? | QRO06? Due ?. Email from 7/9 at 12pm - 'LOTE 10 - Issue #7433' | ? | Completed
2024-07-12 | SAT40 | RFI #00136. PS DAS potential changes. Has this been picked up? | 2024-07-11 | Completed - 7/22 |  | Bram Responded 7/22
2024-07-12 | SAT40 | SAT40 overdue? Submittal SUM-01389 | ? | Completed
2024-07-22 | CYS13 | D3128083 - Submittal 273241-028-00 - ROIP CLOSEOUT PACKAGE | 2024-07-26 | Completed-7/23
2024-07-22 | SAT80 | RFI#20827 ERRCS frequences-in progress. | ? | Completed |  | 7/31 HS indicated he completed this one.
2024-07-23 | AVC01 | 647.1 MC Dean - COLO 3 DAS Warranty R1 | 2024-07-30 | Completed 7/23 |  | 7/23: Hector Hernandez sent reminder
2024-07-23 | SAT15 | RFI# 0350 TeamLinx - Signal Source Options | 2024-07-25 | Complete-7/23 |  | Harold completed 7/23.
2024-07-26 | IAD04 | 21-004233 - IAD04 Loudoun County VA - Submittal Forwarded: 275019-2.0 - PS-DAS SD | 2024-08-02 | Complete-7/26 |  | HS Note: need the Syska electrical team to confirm that they called for a dedicated electrical circuit for the PSDAS equipment
2024-07-29 | SAT40 | RFI-00136-R1 - PS DAS Potential Changes - Microsoft SAT40 Design | 2024-07-31 | Complete-7/30 |  | Bram responded
2024-07-30 | IAD04 | 21-004233 - IAD04 Loudoun County VA - RFI Forwarded: RFI 00551 - FCR Extra Rack R5 | 2024-07-30 | Complete
2024-07-30 | PHX61 | PHX2-DC1 Mercury Fit-Out: New RFI 171 (DAS Design Deficiencies *HOT*) | 2024-08-06 | Completed |  | Completed by bram 7/30
2024-07-30 | PHX71 | RFI #513 - DAS / Telecom - DAS Wall Rack conflict with air quality equipment has been reopened. | 2024-07-08 | Completed |  | Not for S2A
2024-07-31 | IAD04 | 21-004233 - IAD04 Loudoun County VA - RFI Forwarded: RFI 00555 - COLO Aisle Door 1100.1A Magnetic Holder | 2024-08-02 | Completed |  | Not for S2A
2024-08-01 | LVL09 | LVL09-273241-008-R0 - (IES) - COLO2 and 3 - DAS a - 21-60832 | 2024-08-15 | Completed 8/15,8/22
2024-08-05 | MNZ03 | 051200-19.0 - Shop Drawings - Phase 5 & 6 - Stair 3 Antenna Wall - mounting questions | ? | Complete
2024-08-06 | AVC17-18 | MSFT - AVC17/18: New RFI 47 (PDAS Locations) | 2024-08-09 | Completed 8/14
2024-08-06 | DFW20 | Submittal #27 32 41-1 Revision 0: ROIP Design Package - Radio over IP | 2024-08-13 | Completed |  | HS requested S2A to be removed.
2024-08-06 | DFW20 | Submittal #27 50 15-1 Revision 0: DAS Design Package - DAS Cabling | 2024-08-13 | Completed |  | Moved back to open status 8/13.
2024-08-06 | IAD03 | 273241-30.1 - NTI, IAD03 RoIP Closeout | 2024-08-13 | Completed - 8/8 BW
2024-08-06 | SAT15 | RFI 0319 - TeamLinx - RoIP E-House Coverage - MS SAT15 Design | 2024-08-08 | Completed - 8/8 BW
2024-08-09 | LVL09 | LVL09-273241-009-R0 - (IES) - ROIP As-Builts Draw - 21-60832 | 2024-08-23 | Completed
2024-08-12 | IAD04 | IAD04 Loudoun County VA 275019-1.1 - Cellular DAS SD | 2024-08-19 | Complete 8/13
2024-08-12 | LVL11 | RFI#00278 DAS Verizon RBA | 2024-08-14 | Completed 8/14
2024-08-13 | SAT14CA | 275019-012 - Comm Systems DAS - Cell DAS As-Builts - CLAB - MS SAT14 CA | 2024-08-08 | Completed
2024-08-14 | LVL10 | LVL10-270519-004-R1 - (ComNet) - PSDAS System Equ - 22-60848 | 2024-08-24 | Completed
2024-08-15 | AVC09 | AVC09 eFemto integration question regarding corp account login | ASAP | Completed 8/19
2024-08-15 | SAT14CA | RFI 1236 - Teamlinx - ERRCS Remote COLO1- Relocation - MS SAT14 CA | 2024-08-16 | Completed
2024-08-16 | AVC43 | AVC43 Submittal 27 50 19-2.0 - IES PS DAS Submitt - 22-60846 - Submittal # 272073-04 | 2024-08-20 | Completed 8/19
2024-08-16 | AVC43 | AVC43 Submittal 27 50 19-2.0 - IES PS DAS Submitt - 22-60846 - Submittal # 272073-05 | 2024-08-20 | Completed 8/19
2024-08-16 | SAT40 | RFI-00228 - ERRCS Active Equipment Nema Rating - Microsoft SAT40 Design | 2024-08-20 | Completed 8/19 |  | BW answered
2024-08-19 | QRO01 | QRO01 - PCO 117 DAS - FCR Cabinet Relocation per RFI 619 Response | ASAP | Completed |  | GC requesting change order - HS Responded 8/20
2024-08-22 | IAD11 | DAS Cell Coverage Issues. (Not S2A's issue but we want to track it.) - HS checking back with contractor week of 9/16. | ? | Complete |  | 10/22: Closed per HS 10/22 - in the owners court to resolve.
2024-08-23 | SAT40 | RFI-00241 - Carrier Signal Sources - Microsoft SAT40 Design | 2024-08-28 | Completed |  | Bram completed 8/25
2024-08-26 | PHX13 | Submittal 275019-001-00 - ERRCS Systems | 2024-08-30 | Completed 8/30 |  | BW
2024-08-26 | PHX13 | Submittal 275019-002-01 - DAS System (PSDAS Design) | 2024-08-30 | Completed 8/30 |  | BW
2024-08-27 | LVL06 | LVL06 RFI 357 - Antennae and Splitter Location Co - 23-60857 | 2024-08-29 | Completed 8/30 |  | BW
2024-08-28 | AVC11 | Issue #861 - OVERALL SITE PLAN | 2024-09-06 | Complete 8/30 |  | Bram answered - ok to mark complete?
2024-08-28 | AVC11 | Issue #862 - FCR REMOTE UNITS | 2024-09-06 | Complete 8/30 |  | Bram answered - ok to mark complete?
2024-08-28 | AVC11 | Issue #863 - SER EQUIPMENT | 2024-09-06 | Complete 8/30 |  | Bram answered - ok to mark complete?
2024-08-28 | AVC11 | Issue #864 - OVERALL SITE PLAN | 2024-09-06 | Complete 8/30 |  | Bram answered - ok to mark complete?
2024-08-29 | AVC11 | Issue #1027 - REMOTE UNIT LOCATION | 2024-09-06 | Complete 8/30
2024-08-29 | AVC11 | Issue #1028 - EQUIPMENT IN SER | 2024-09-06 | Complete 8/30
2024-08-29 | AVC11 | Issue #962 - TWO DRAWING PACKAGES | 2024-09-06 | Complete 8/30 |  | Mouna answered - ok to mark complete?
2024-08-29 | AVC11 | Issue #964 - AVC11 COLO3 | 2024-09-06 | Complete 8/30 |  | Mouna answered - ok to mark complete?
2024-08-29 | AVC11 | Issue #965 - 1x BASE STATION FOR SECURITY OFFICE | 2024-09-06 | Complete 8/30 |  | Mouna answered - ok to mark complete?
2024-08-29 | AVC11 | Issue #966 - SITE COVERAGE | 2024-09-06 | Complete 8/30 |  | Mouna answered - ok to mark complete?
2024-08-29 | AVC11 | Issue #967 - COVERAGE | 2024-09-06 | Complete 8/30 |  | Mouna answered - ok to mark complete?
2024-08-29 | AVC11 | Issue #968 - COVERAGE | 2024-09-06 | Complete 8/30 |  | Mouna answered - ok to mark complete?
2024-08-29 | AVC11 | Issue #969 - SECURITY OFFICE BASE STATION | 2024-09-06 | Complete 8/30 |  | Mouna answered - ok to mark complete?
2024-08-29 | AVC11 | Issue #970 - BASE STATION LOCATION | 2024-09-06 | Complete 8/30 |  | Mouna answered - ok to mark complete?
2024-08-29 | AVC11 | Issue #971 - CHARGER LOCATION | 2024-09-06 | Complete 8/30 |  | Mouna answered - ok to mark complete?
2024-08-29 | AVC11 | Issue #972 - POWER SUPPLY | 2024-09-06 | Complete 8/30 |  | Mouna answered - ok to mark complete?
2024-08-29 | AVC11 | Issue #973 - EXISTING VS. NEW | 2024-09-06 | Complete 8/30 |  | Mouna answered - ok to mark complete?
2024-08-29 | AVC11 | Issue #974 - SECURITY OFFICE BASE STATION | 2024-09-06 | Complete 8/30 |  | Mouna answered - ok to mark complete?
2024-08-29 | AVC11 | Issue #975 - SECURITY OFFICE BASE STATION | 2024-09-06 | Complete 8/30 |  | Mouna answered - ok to mark complete?
2024-08-29 | AVC11 | Issue #976 - RACK POWER | 2024-09-06 | Complete 8/30 |  | Mouna answered - ok to mark complete?
2024-08-30 | LVL09 | LVL09-273241-011-R1 - (IES)- Admin and COLO 1 to - 21-60832 | 2024-09-12 | Complete |  | HS
2024-09-04 | LVL07 | RFI 87 - PSDAS Archictecture. | 2024-09-09 | Complete
2024-09-05 | PHX14 | D3127072 - Submittal 273241-001-00 - ROIP System | 2024-09-11 | Complete
2024-09-05 | PHX14 | D3127072 - Submittal 275019-001-00 - DAS System | 2024-09-11 | Complete
2024-09-09 | EAT03 | RFI #404 - EAT03 - ERRCS Design Concerns | 2024-09-10 | Completed 9/9 |  | See email thread.
2024-09-10 | LVL06 | LVL06 RFI 362 - FCR DAS Cabinet Clarifications - 23-60857 | 2024-09-13 | Complete
2024-09-11 | AVC43 | AVC43 RFI 27.012.1 - FCR PDAS Cabinet Location - 22-60846 | 2024-09-13 | Complete
2024-09-11 | LVL07 | LVL07 RFI 96 - CDAS Verizon BDA - 23-60861 | 2024-09-16 | Complete
2024-09-12 | LVL11 | LVL11-270519-001-R1 - (ComNet)-Das System Equipme - 22-60853 | 2024-09-26 | Complete |  | HS 9/13 noted as responded to.
2024-09-16 | IAD12-13 | IAD12-13 ¦ Submittal 055000-2.0_Metal Fabrications_Sure Steel_Antenna Support_SD | 2024-09-18 | Completed |  | Not for S2A
2024-09-20 | CPQ03 | CPQ3 - 728 - 001-CPQ03-RFI-T-DAS-R01-202409201218 | ASAP | Completed 09/23
2024-09-20 | CPQ03 | CPQ3 - 739 - 003-CPQ03-RFI-T-DAS-R00 | ASAP | Completed 09/23
2024-09-20 | CPQ03 | CPQ3 - 741 - 004-CPQ03-RFI-T-DAS-R00 | ASAP | Completed 09/23
2024-09-20 | CPQ03 | CPQ3 - RFI 729 - 002-CPQ03-RFI-T-DAS-R00 | ASAP | Completed 09/23
2024-09-20 | QRO01 | WAMC QRO 01: New RFI 718 (RoIP - Connection between Head End equipment and outdoor antena) | 2024-09-20 | Complete-9/20
2024-09-20 | SAT15 | 275019-005 - DAS Communication Systems - Cell DAS Benchmark Study - TR | 2024-09-27 | Complete |  | 09/27: No reminder email received in the am so marking complete. 09/26: We got another reminder email! 09/25: HS re-uploaded
2024-09-23 | AVC43 | AVC43 RFI 27.025.0 - PSDAS Repeater Model Replace - 22-60846 | 2024-09-26 | Complete |  | BW completed 09/24
2024-09-23 | QRO01 | #27 32 41-11.0: Radio Over IP - Commissioning Document | 2024-09-27 | Complete |  | HS completed 09/25
2024-09-24 | LVL05 | LVL05 Record Docs - MSFT request for update | 2024-09-25 | Complete |  | HS responded 09/24
2024-09-24 | LVL11 | Submittal 270519-001-R1 (ComNet)-Das System Equipment | 2024-09-26 | Complete |  | HS reponsded 09/25
2024-09-24 | LVL11 | Submittal 273241-004-R1 (ComNet)-Roip System Design Equipment | 2024-09-26 | Complete |  | HS comment 09/26 - not for S2A: S2A – did not provide the RoIP design; unless the client wants our team to review the submittal, as an independent consultant, S2A is going to pass on this ask.
2024-09-25 | AVC43 | AVC43 RFI 27.018.0 - Cell DAS Design Clarificatio - 22-60846 - HOT! | 2024-09-25 | Completed |  | 09/25: BW emailed Kellee Bell and let her know completed.
2024-09-25 | FTY01 | Submittal #27 50 19-4.0: COMMUNICATION SYSTEM DISTRIBUTED ANTENNA SYSTEM (DAS) - Commissioning | 2024-09-25 | Complete
2024-09-25 | FTY01 | Submittal #27 50 19-5.0: COMMUNICATION SYSTEM DISTRIBUTED ANTENNA SYSTEM (DAS) - Commissioning | 2024-09-25 | Complete
2024-09-26 | CHI22 | MSF19010 275019-19.0 - Phase 2 Distributed Antena System | 2024-10-04 | Complete |  | 09/26: HS submitted.
2024-10-10 | LVL09 | LVL09-273241-012-R1 - (IES) - DAS As-Built Drawin - 21-60832 | 2024-10-24 | Complete |  | Session ID: 868-911-489 - Neither BW/KP can access anymore - KP emailed Kbell to confirm if open or not. 10/16: KBelll confirmed submitted 10/14.
2024-10-10 | QRO01 | WAMC QRO 01: (#27 32 41-2.0: Radio Over IP - Frequency License Documentation) | 2024-10-17 | Complete |  | HS completed 10/10.
2024-10-11 | LVL06 | LVL06 RFI 383 - Donor Antenna Placement - 23-60857 Session ID: 515-807-717 | 2024-10-16 | Complete |  | Session ID: 515-807-717 HS completed 10/21
2024-10-11 | LVL09 | LVL09-273241-013-R1 - (IES) - ROIP As-Built Drawi - 21-60832 | 2024-10-24 | Complete |  | Session ID: 455-748-724
2024-10-14 | CHI22 | CHI22 Franklin Park - MSF19010 - Design 275019-21.0 - Phase 2 Distributed Antenna System - PS SD | 2024-10-21 | Complete |  | HS emailed response 10/16
2024-10-14 | CHI22 | CHI22 Franklin Park - MSF19010 - Design275019-20.0 - Phase 2 Distributed Antenna System - Commercial SD | 2024-10-21 | Complete |  | HS emailed response 10/16
2024-10-15 | LVL11 | LVL11 RFI 330 - (ComNet) - FCR DAS RACK (CN).pdf - 22-60853 | 2024-10-18 | Complete |  | Session ID: 861-904-615 BW completed 10/16
2024-10-15 | SAT15 | 275019-014 - DAS Communication Systems - Comba Substitution - PD | 2024-10-22 | Complete |  | HS responded 10/15.
2024-10-16 | IAD12-13 | RFI 0511_COMM DAS & PS DAS IFC_Issue for Bid_Registration | 2024-10-18 | Complete |  | BW completed 10/16
2024-10-16 | LVL09 | LVL09-273241-013-R2 - (IES) - ROIP As-Built Drawi - 21-60832 Session ID: 293-421-015 | 2024-10-30 | Complete |  | Session ID: 293-421-015 HS completed 10/21
2024-10-17 | LVL11 | LVL11-273241-006-R1 - (ComNet) - DAS System Design - 22-60853 Session ID: 086-967-332 | 2024-10-31 | Complete |  | Session ID: 086-967-332 HS completed 10/21.
2024-10-21 | CHI22 | 273241-21.0 - Radio Over IP PD | 2024-10-28 | Completed |  | HS completed 10/22
2024-10-21 | CHI22 | 273241-22.0 - Phase 2 Radio Over IP - Block Diagrams SD | 2024-10-28 | Completed |  | HS completed 10/22
2024-10-21 | CHI22 | 273241-23.0 - Phase 2 Radio Over IP - Cable Route Diagrams SD | 2024-10-28 | Completed |  | HS completed 10/22
2024-10-21 | LVL09 | LVL09-270010-007-R1 - (IES) - Telecom COLO3 Warra - 21-60832 Session ID: 603-181-272 | 2024-10-23 | Complete |  | Session ID: 603-181-272 HS completed 10/21
2024-10-21 | LVL11 | LVL11-273241-006-R1 - (ComNet) - DAS System Desig - 22-60853 Session ID: 086-967-332 | 2024-10-23 | Complete |  | Session ID: 086-967-332 HS completed 10/21.
2024-10-21 | YTO11 | YTO11 RFI 412 - see email from Peter Ngo 10/25 re spare batteries. | 2024-10-23 | Complete |  | HS completed 10/23.
2024-10-21 | YTO11 | YTO11 RFI 413 | 2024-10-23 | Completed |  | HS completed 10/23.
2024-10-22 | MNZ03 | RFI 00267 - FCR Room EPMS-BAS Gateway Panel Location - A McClung arranging conf call to discuss | ? | Completed |  | BW working on 10/24
2024-10-22 | SAT15 | RFI 0447 - Teamlinx - Donor Cabling Supports In Admin | 2024-10-25 | Completed |  | HS completed 10/25
2024-10-22 | SAT15 | RFI 0449 - TeamLinx - Alternative Signal Source | 2024-10-28 | Completed |  | HS completed 10/25
2024-10-23 | IAD11-12 | RFI 0528_IAD 13 ROU Remote Quantity | 2024-10-28 | Completed |  | BW completed 10/24
2024-10-23 | SAT14CA | RFI 1303 - Teamlinx - Conduit for DAS Fiber in Colo1 & Colo2 | 2024-10-24 | Completed |  | HS completed 10/23.
2024-10-24 | LVL07 | LVL07 RFI 215 - Telecom Labeling CDAS - 23-60861 | 2024-10-28 | Completed |  | BW completed 10/24
2024-10-24 | LVL07 | LVL07 Submittal 216 - Telecom Labeling PSDAS - 23-60861 | 2024-10-28 | Completed |  | BW completed 10/24
2024-10-24 | MNZ03 | RFI 00266 - Voltage and Plug Types for ROIP Power | 2024-10-28 | Completed |  | BW working on 10/24
2024-10-24 | SAT15 | RFI 0441 - TeamLinx - CEI CE1-4 Rack Mounting and Door Orientation | 2024-10-28 | Completed |  | HS completed 10/25 - asked A/E to reroute - no scope for S2A
2024-10-29 | LVL06 | LVL06 Submittal 408 - IES O&amp;Ms - 23-60857 | 2024-10-31 | Completed |  | HS confirmed completed 10/30.
2024-10-30 | LVL09 | LVL09-270010-006-R1 - (IES) - Telecom COLO2 Warra - 21-60832 | 2024-11-01 | Completed |  | BW completed 10/30.
2024-10-30 | LVL09 | LVL09-270010-008-R1 - (IES) - Telecom COLO4 Warra - 21-60832 | 2024-11-01 | Completed |  | BW completed 10/30.
2024-10-31 | PHX14 | D3127072 - Submittal 275019-002-00 - ERRCS System - A/E provided guidance to return not approved. | 2024-11-06 | Completed |  | BW completed 11/7
2024-10-31 | SAT15 | RFI 0459 - TeamLinx - RoIP Recommendations | 2024-11-04 | Completed |  | HS completed 10/31
2024-11-04 | YQB04 | RFI-848 - DAS Outdoor antennas position | 2024-11-04 | Completed
2024-11-05 | LVL07 | Submittal 241 - PSDAS BOM - 23-60861 | 2024-11-07 | Completed
2024-11-06 | EAT12 | Submittal 275019-001-0 - Communication Systems Distributed Antenna Systems - Product Data | 2024-11-08 | Completed |  | BW completed 11/7
2024-11-06 | LHY10 | RFI LYH10 - 000408 - DRB08 Fiber Jumper Conduit Sizes. | 2024-11-08 | Completed |  | BW completed 11/7
2024-11-06 | LVL09 | LVL09-270010-022-R1 - (IES) - Telecom COLO5 Warra - 21-60832 | 2024-11-08 | Completed |  | K Belle confirmed BW responded.
2024-11-07 | CHI11 | Overdue RFI/Submittl Log Review | 2024-11-07 | Completed |  | HS completed 11/7
2024-11-07 | IAD12-13 | Review of Change Log | 2024-11-07 | Completed |  | BW completed 11/7
2024-11-07 | LVL06 | RFI 403 - LVL01 DAS Fiber Connection - 23-60857 | 2024-11-12 | Completed |  | HS completed 11/7
2024-11-07 | YTO11 | Submittal 252R1 | 2024-11-12 | Completed |  | HS completed 11/7
2024-11-08 | LVL06 | LVL06 RFI 403-REOPEN - LVL01 DAS Fiber Connection - 23-60857 | 2024-11-08 | Completed |  | BW completed 11/8
2024-11-11 | LVL07 | LVL07 RFI 129 - CDAS rPDU - 23-60861 - Session ID: 975-976-294 | 2024-11-14 | Complete |  | BW completed 11/13
2024-11-11 | YTO11 | MSFT YTO11 RFI 506 | 2024-11-18 | Completed |  | BW complete 11/12
2024-11-11 | YTO11 | MSFT YTO11 RFI 507 | 2024-11-18 | Completed |  | BW complete 11/11
2024-11-11 | YTO11 | MSFT YTO11 RFI 508 | 2024-11-18 | Complete
2024-11-11 | YTO11 | MSFT YTO11 Submittal 252R1 | 2024-11-18 | Complete |  | BW completed 11/12
2024-11-13 | SAT80 | RFI PH2-0968 - SAT 80 - TELE - Antenna Location at SAT 80 Admin | 2024-11-15 | Complete |  | BW completed 11/13
2024-11-14 | CHI22 | 275019-22.0 - Phase 2 Distributed Antenna System - DAS Benchmark Study | 2024-11-21 | Completed
2024-11-14 | IAD12-13 | 275019-1.0_Distributed Antenna System_IAD 12-13_SD | 2024-11-20 | Completed
2024-11-14 | LHY10 | LHY10 Submittal 321 Radio Over IP Product Data - <Need RFI details from A/E> | 2024-11-29 | Completed |  | 11/14: HS requested A/E send RFI to KP/BW
2024-11-14 | LVL11 | LVL11 RFI 365 - (ComNet) - MISSING DASROIP CONDUI - 22-60853 | 2024-11-19 | Complete |  | NOT S2A scope
2024-11-14 | PHX14 | PHX14 CA - D3127072 - Submittal 275019-002-01 - ERRCS System | 2024-11-20 | Completed |  | 11/20: BW completed.
2024-11-18 | LYH10 | Notification went to Bram, not to KP. Need details. | 2024-11-23 | Completed |  | 12/10: Bram emailed Jason confirming responded on 11/18 that it should be reaassigned to DW.
2024-11-18 | LYH10 | Notification went to Bram, not to KP. Need details. | 2024-11-23 | Completed |  | 12/10: Bram emailed Jason confirming responded on 11/18 that it should be reaassigned to DW.
2024-11-21 | IAD04 | RFI 00688 - Roof Antenna Coaxial Cable Grounding | 2024-11-25 | Completed |  | KP uploaded BW's response 11/26.
2024-11-21 | YTO11 | MSFT YTO11 RFI 535 | 2024-11-21 | Completed
2024-11-22 | SAT40 | RFI-00450 - Clarification on Backing for DAS Scope and TVs | 2024-11-26 | Complete |  | HS/BW completed 11/26
2024-11-22 | SAT80 | RFI PH2-0976 - SAT 80 PKG 2 - COMM/ELE - DAS remote locations & power | 2024-11-26 | Complete |  | HS/BW completed 11/26
2024-11-25 | AVC17-18 | AVC17/18: New RFI 168 (DAS iBwave Files) | 2024-11-27 | Complete
2024-11-26 | PHX12 | PHX12 CA - D3127052 - Submittal 270519-003-00 - Admin & COLO 1 ERRCS System As-Built Drawings | 2024-12-04 | Completed |  | BW completed 12/4
2024-11-26 | PHX71 | PHX71 CA - D3127032 - Submittal 273241-001-00 - Radio Over IP - O&M | 2024-12-04 | Completed |  | BW completed 12/3
2024-11-26 | PHX71 | PHX71 CA - D3127032 - Submittal 275019-008-00 - Distributed Antenna System - O&M's | 2024-12-04 | Completed |  | BW completed 12/3
2024-11-26 | YQB04 | YQB04 DATA CENTER: Response to RFI #848 | 2024-11-29 | Complete
2024-11-26 | YTO11 | MSFT YTO11 Substitution 32 | 2024-12-03 | Completed
2024-12-05 | CHI05 | CHI05 Hoffman - Design - Submittal Forwarded: 27 32 14-101.0_Radio Over IP - PD - Submittal - Bram emailed Y Taylor 12/10 that completed on Newforma but Newforma site not reflecting any updates. | 2024-12-12 | Complete |  | KP no email reminder received 12/13. Marking complete. BW confirmed completed 12/10.
2024-12-05 | CHI05 | CHI05 Hoffman - Design - Submittal Forwarded: 27 50 19-101.0_Distributed Antenna | 2024-12-12 | Completed |  | BW completed 12/5.
2024-12-05 | CHI11 | CHI11 Busse - Design - RFI Forwarded: CHI11 RFI 0126 - CHI11 DAS Wall Enclosure | 2024-12-12 | Completed |  | Not for S2A
2024-12-05 | IAD12-13 | RFI 0568_DAS Fiber Housing Discrepancy - Microsoft_Loudoun County IAD12 & IAD13 AE Design - see request from A/E 12/11 to review Hensel Phelps follow up for information. | 2024-12-09 | Completed |  | KP responded 12/11 to reroute to telecom team.
2024-12-05 | YTO11 | YTO11 Submittal 269R1 | 2024-12-12 | Completed |  | HS completed 12/5
2024-12-05 | YTO11 | YTO11 Submittal 270R1 - A/E requesting emailed copy of response. | 2024-12-12 | Completed |  | HS completed 12/5
2024-12-05 | YTO11 | YTO11 Submittal 559 - HS setting up call with contractor | 2024-12-12 | Completed |  | HS setting up call with contractor.
2024-12-09 | LVL10 | LVL10 RFI 351 - (WA) - Fire Rated Conduit and CAT - 22-60848 | 2024-12-12 | Completed |  | BW completed 12/9
2024-12-10 | IAD12-13 | PCO 106 - RFI 528 - IAD 13 ROU Remote Quantity - see email note from Bram 12/10 regarding the potential miss/potential cost. | 2024-12-13 | Complete |  | HS answered 12/12
2024-12-10 | QRO01 | ROIP Submittal - need details - KP reached out to Alma/Fernando 12/12 | ? | Complete
2024-12-10 | YQB04 | Submittal 27 50 19.1-1 - BW requests HS to answer. | 2024-12-16 | Complete
2024-12-12 | CHI05 | RFI 1179 - VHF BDA System Installation | 2024-12-13 | Complete |  | HS completed 12/12.
2024-12-12 | EAT12 | RFI 0222 - request for frequencies to be used. | 2024-12-13 | Completed |  | HS responded via email 12/12
2024-12-12 | LVL07 | LVL07 RFI 153 - CDAS AT&T - 23-60861 Session ID: 422-412-485 | 2024-12-17 | Complete
2024-12-13 | PHX71 | PHX71 CA - D3127032 - Submittal 273241-007-00 - E2 Optics, PHX71 - ROIP OSP Fiber, Test Report - | 2024-12-16 | Completed |  | HS completed 12/13, again on 12/17.
2024-12-16 | ATL06 | Submittal #27 32 41-2.0: Radio Over IP - Shop Drawings | 2024-12-30 | Completed |  | HS responded 12/20
2024-12-16 | PHX12 | PHX12 CA - D3127052 - Submittal 273241-003-00 - ROIP System As-Built - FOR YOUR REVIEW | 2024-12-20 | Complete
2024-12-16 | PHX12 | PHX12 CA - D3127052 - Submittal 275019-004-00 - Commercial DAS System As-Built | 2024-12-20 | Complete |  | HS completed 12/20
2024-12-17 | SAT14CA | P2 - 275019-013 - DAS - Equipment - SD_PD | 2024-12-24 | Complete |  | BW completed 12/24
2024-12-19 | LVL07 | LVL07 Submittal 277 - PSDAS Product Data - 23-60861 | ? | Completed |  | BW answered 12/19.
2024-12-19 | LVL07 | LVL07 Submittal 278 - CDAS BOM - 23-60861 | ? | Completed |  | BW answered 12/19.
2024-12-19 | LVL07 | LVL07 Submittal 279 - CDAS Product Data - 23-60861 | ? | Completed |  | BW answered 12/19.
2024-12-19 | QRO01 | WAMC QRO 01: Approver Jair Rangel Updated their Response for Submittal (#27 32 41-11.3: Radio Over IP - Commissioning Document) | 2025-01-02 | Completed |  | kp can't access BB link
2024-12-19 | SAT80 | 270010.01-004 - General Provisions for Communications Systems - Operation & Maintenance Data | 2024-12-17 | Completed |  | kp can't access BB link
2024-12-19 | SAT80 | PH2-1005 - SAT 80 to SAT 81 Intra building fiber | 2024-12-24 | Completed |  | BW answered 12/20
2024-12-19 | YTO11 | MSFT YTO11 RFI 609 | 2024-12-20 | Completed |  | Harold completed 12/19. And re-responded 1/10.
2024-12-19 | YTO11 | MSFT YTO11 RFI 610 | 2024-12-20 | Completed |  | kp can't access BB link
2024-12-20 | IAD04 | 21-004233 - IAD04 Loudoun County VA - RFI Forwarded: RFI 0716- Cellular DAS RBA Rejection | 2024-12-24 | Completed |  | BW answered 12/20.
2024-12-20 | PHX71 | 275019-014-0 E2 Optics, PHX71 - DAS ISP Fiber, Test Report | 2024-12-23 | Complete |  | HS completed 12/24
2024-12-20 | PHX81 | D3127042 - Submittal 273241-002-00 - Radio Over IP - Cable Alternative | 2024-12-31 | Complete |  | HS completed 12/27
2024-12-20 | PHX81 | D3127042 - Submittal 275019-002-00 - Distributed Antenna System (DAS) - Cable Alternative | 2024-12-31 | Complete |  | HS completed 12/27
2024-12-20 | YTO11 | Session ID 235-586-876 OO_CA Best Practices.PDF - KP reached out to inquire what's required on this one. | ? | Complete |  | Session was initiated just to provide access to Bram/myself for the YTO11 project. No action needed.
2024-12-23 | ATL06 | 27 32 41-1.0: Radio Over IP - Equipment and Product Data - not in S2A's court - visibility only | 2024-12-30 | Complete |  | 1/19/25: HS noted as done. 1/2/25: Still in IES's court. Timeline extended beyond 12/30.
2024-12-23 | ATL06 | 27 50 19-2.0: DAS - Equipment and Product Data - not in S2A's court - visibility only | 2024-12-30 | Complete |  | 1/19/25: HS noted as done. 1/2/25: Still in IES's court. Timeline extended beyond 12/30.
2024-12-23 | LVL07 | LVL07 Submittal 284 - CDAS Benchmark Study Test P - 23-60861 | 2024-12-30 | Complete |  | BW completed 12/27
2024-12-23 | LVL07 | LVL07 Submittal 282 - CDAS Coax Test Plan - 23-60861 | 2024-12-30 | Complete |  | BW completed 12/27
2024-12-23 | LVL07 | LVL07 Submittal 283 - PSDAS Coax Test Plan - 23-60861 | 2024-12-30 | Complete |  | BW completed 12/27
2024-12-23 | SAT80-81 | RFI PH2-1006 - SAT 80/81 - DAS PS - Donor Antenna Location (RFI PH2-0982) | 2024-12-27 | Complete |  | BW Completed 12/24
2024-12-29 | CCO06 | PSDAS Shop Drawings - Submittal | 2024-12-30 | Complete |  | BW - add to list 12/30
2024-12-30 | LVL10 | LVL10-273241-006-R1 - (ComNet) - ROIP Closeout Pa - 22-60848 - Session ID: 156-885-945 | ? | Complete |  | HS responded 1/2/25
2025-01-02 | YTO11 | MSFT YTO11 RFI 609R1 | 2025-01-04 | Complete |  | HS will respond 1/2/25.
2025-01-03 | LVL10 | LVL10 RFI 353 - (ComNet) - PSDAS-Equipment Detail - 22-60848 - NOT IN BB - emailed K Belle | 2025-01-07 | Closed |  | 1/7/25: Not showing up in BB - K Belle confirmed it was closed out. GC wanted more information and will resubmit later.
2025-01-03 | LVL10 | LVL10-273241-007-R1 - (ComNet) - DAS Closeout Pac - 22-60848 | 2025-01-10 | Completed |  | 1/7/25: Harold responded.
2025-01-03 | LVL10 | LVL10-273241-008-R1 - (ComNet) - PSDAS Closeout P - 22-60848 | 2025-01-10 | Completed |  | 1/7/25: Harold responded.
2025-01-03 | LVL11 | LVL11 RFI 404 - (ComNet) - PSDAS-Equipment Detail - 22-60853 - NOT in BB - emailed K Belle | 2025-01-07 | Closed |  | 1/7/25: Not showing up in BB - K Belle confirmed it was closed out. GC wanted more information and will resubmit later.
2025-01-03 | MNZ03 | MNZ03 iBwave RFI | ? | Completed |  | BW completed
2025-01-06 | LVL11 | LVL11 RFI 405 - (WA) - COLO 3 Cell 4 RoIP Cabinet - 22-60853 | 2025-01-08 | Closed |  | 1/7/25: Emailed A/E and told them to route to DCE
2025-01-07 | QRO06 | QRO06 RFI#689 Splitter Location | 2025-01-09 | Completed |  | 1/7/25: Harold responded.
2025-01-08 | AVC43 | AVC43 RFI 26.114.0 - RPDU Power Requirements at D - 22-60846 | 2024-01-13 | Completed |  | 1/8/25: BW- needs to be rerouted to Telecom EOR
2025-01-08 | SAT40 | RFI-00450-R1 - Clarification on Backing for DAS Scope and TVs - HS requested to have rerouted 1/9 but I think it's still assigned to S2A. | 2025-01-10 | Closed |  | 1/9/25: HS requested to have reassigned to architecture.
2025-01-09 | AVC17-18 | AVC17/18: Action Required for Submittal (#243.0: MC Dean - PS DAS Labeling Plan) | 2025-01-16 | Complete |  | 1/16/25: HS responded
2025-01-09 | AVC17-18 | AVC17/18: Action Required for Submittal (#244.0: MC Dean - Comm DAS Labeling Plan) | 2025-01-16 | Complete |  | 1/16/25: HS responded
2025-01-09 | LVL10 | LVL10 RFI 355 - (WA) - PSDAS Annunciator Panel (M - 22-60848 | 2025-01-14 | Completed |  | 1/13/25: HS responded
2025-01-09 | PHX12 | PHX12 CA - D3127052 - Submittal 273241-003-01 - Revised ROIP System As-Built | 2025-01-15 | Completed |  | 1/9/25: HS completed, reconfirmed. completed 1/14.
2025-01-09 | YQB04 | YQB04 DATA CENTER: Action required for submittal (#27 50 19.1-2.0: Distributed Antenna System (DAS) | 2025-01-13 | Completed |  | 1/9/25: HS completed
2025-01-09 | YTO11 | YTO11 Submittal 559R1 | 2025-01-16 | Complete |  | 1/10: HS responded.
2025-01-10 | ATL06 | ATL06: RFI #230 DAS Field Mock Up | 2025-01-15 | Completed |  | 1/13/25: HS responded.
2025-01-13 | LVL07 | LVL07 RFI 172 - PSDAS BDA - 23-60861 Session ID: 898-952-548 | 2025-01-16 | Completed |  | 1/14/25: HS responded.
2025-01-13 | MNZ03 | 270528-1.0 - Pathways for Communications Systems -PD | 2025-01-21 | Closed |  | 1/13/25: HS responded requesting to have S2A removed as outside of our scope.
2025-01-13 | PHX72 | PHX72 CA - D3127038 - Submittal 273241-001-00 - RoIP Package PD & SD | 2025-01-17 | Closed |  | 1/17: HS confirmed RoIP not in S2A's court. 1/28 HS email with pdf including stamp
2025-01-13 | PHX72 | PHX72 CA - D3127038 - Submittal 275019-001-00 - DAS Package PD & SD | 2025-01-17 | Completed |  | BW responded 1/17/25: contractor must resubmit with plan to obtain RBA.
2025-01-13 | SAT80/81 | RFI PH2-1016 - SAT 80/81 - TELE - RIOP Intra-Building Fiber | 2025-01-14 | Completed |  | Not assigned to us but HS responded to questions from Chris Mellinger.
2025-01-13 | YQB04 | 08285.000 - YQB04 RFI-990 - Grounding of DAS outdoor antennas and surge protectors | 2025-01-13 | Completed |  | 1/13/25: HS responded that needs to be rerouted to electrical engineering team. KP emailed Eugene requesting to make sure notifications on new RFI/Submittals sent to HS, BW, KP.
2025-01-14 | AVC43 | AVC43 - Issue #1205 - site plan | 2025-01-16 | Completed |  | 1/16/25: BW responded.
2025-01-14 | AVC43 | AVC43 - Issue #1206 - wrong site reference | 2025-01-16 | Completed |  | 1/16/25: BW responded.
2025-01-14 | AVC43 | AVC43 - Issue #1207 - isp fiber terminations | 2025-01-16 | Completed |  | 1/16/25: BW responded.
2025-01-14 | YTO11 | MSFT YTO11 RFI 579R2 | 2025-01-16 | Complete |  | 1/15: HS responded.
2025-01-15 | YTO11 | MSFT YTO11 RFI 609R2 | 2025-01-16 | Complete |  | 1/15: HS responded.
2025-01-16 | CCO06 | CCO06 Phase I: New RFI 314 (ERRCS Additional Antennas) | 2025-01-21 | Completed |  | HS responded 1/19
2025-01-17 | LVL07 | LVL07 RFI 177 - CAT6 to FACP - 23-60861 | 2025-01-22 | Completed |  | 1/20/25 HS responded
2025-01-17 | SAT80/81 | RFI PH2-1025 - SAT 80/81 - DAS PS/ FA - Point of Interface DAS Monitoring | 2025-01-22 | Complete |  | HS Responded 1/23
2025-01-22 | CCO06 | RFI related to antennas | 2025-01-24 | Completed |  | HS responded to 1/24
2025-01-22 | YTO11 | MSFT YTO11 RFI 609R3 | 2025-01-24 | Complete |  | 1/23/25: HS responded.
2025-01-23 | CCO06 | PS DAS Shop Drawings | 2025-01-23 | Completed |  | HS closed 1/27
2025-01-23 | CLT10 | 35 Div27 request from GC for iBwave file to reference | 2025-01-25 | Complete |  | 1/23: BW completed.
2025-01-23 | IAD11 | HS initiated request to NT - sanity check on coverage in admin area | ? | Closed |  | HS confirmed ok to close 2/12.
2025-01-23 | MNZ03 | RFI0442: Design update to over the air DAS System | 2025-01-29 | Completed |  | HS responded 1/29.
2025-01-23 | SAT15 | RFI 0587 - TeamLinx - Antenna Array Mast Count - MS SAT15 Design - Reminder: FOLLOW PAGE GUIDELINES ON REQUIRED LANGUAGE ON RFI Response | 2025-01-27 | Complete |  | HS responded 1/23 / BW also made note of complete 1/27
2025-01-24 | CHI22 | CHI22 MSF19010 275019-23.0 - Phase 2 DAS Heliax - Test Reports | 2025-01-31 | Completed |  | HS completed 1/30
2025-01-24 | LVL11 | LVL11-270519-002-R1 - (ComNet) - PSDAS System Equipment - 22-60853 | 2025-01-31 | Completed |  | HS responded 1/28
2025-01-30 | LVL04 | LVL04-05 Submittal 1116.0 - Telecom MH Labeling P - 20-60833 - this is pending information from BIR; we need to see cable test reports and CW test | 2025-02-06 | Completed |  | 2/4 HS Responded
2025-01-30 | SAT80-81 | RFI PH2-1032 - SAT 80/81 PKG 2 - ROIP - Base-Station Radios Location | 2025-02-04 | Completed |  | HS responded 2/3
2025-01-31 | LVL07 | LVL07 Submittal 316 - DAS Prefab Shop Drawings - 23-60861- HS responded 2/3 but K Bell responded 2/4 saying did not see response in BB. | 2025-02-07 | Completed |  | HS responded 2/3 - K Belle confirmed 2/4
2025-01-31 | LVL07 | LVL07 Submittal 317 - PSDAS Benchmark Study Test - 23-60861 - HS responded 2/3 but K Bell responded 2/4 saying did not see response in BB. | 2025-02-07 | Completed |  | HS responded 2/3 - K Belle confirmed 2/4
2025-02-03 | PHX72 | PHX72 CA - D3127038 - Submittal 273241-001-01 - RoIP Package PD & SD - this is pending information from E2 – they need to confirm that they included handheld radios | 2025-02-07 | Completed |  | HS responded 2/4
2025-02-04 | LVL04-05 | LVL04-05 Submittal 1125.0 - LVL04 IES Final Telec - 20-60833 when completed, please email K Belle confirming responded to | 2025-02-11 | Completed |  | HS responded to.
2025-02-04 | LVL10 | LVL10-270519-003-R2 - (ComNet) - PSDAS System Des - 22-60848 - 2/10: GC Requeste to Expedite when completed, please email K Belle confirming responded to. | 2025-02-18 | Completed |  | HS responded to.
2025-02-05 | LVL11 | LVL11 RFI 417 - (WA) - PSDAS Annunciator Panel (M - 22-60853 | 2025-02-06 | Completed |  | HS responded 2/5
2025-02-06 | PHX72 | PHX72 CA - D3127038 - Submittal 275019-001-00 - DAS Package PD & SD | 2025-02-11 | Completed |  | HS completed 2/11.
2025-02-07 | CHI11 | CHI11 RFI 0235_DAS Rack_LIU - redirected with 2/12 with responses. Confirm if follow up needed? | 2025-02-14 | Complete |  | HS responded 2/7 - redirected 2/13 with question. Completed again 2/13.
2025-02-07 | EAT12 | PRIORITY: EAT12 Data Center - 6524006 Submittal 275019-002 - 2/14 HS reviewing will respond by 2/18 | ? | Completed |  | BW confirmed completed 2/17. HS reviewing - will respond by 2/18
2025-02-07 | LVL07 | LVL07 RFI 193 - PSDAS Indoor Antenna - 23-60861 | 2025-02-12 | Completed |  | HS completed 2/10.
2025-02-10 | MNZ03 | 270820-2.0 - Fiber Testing for Comm. Systems -2.22.3 Optical Fiber Test Equipment PD | 2025-02-17 | Completed |  | HS responded indicating he didn't think anything for S2A to review.
2025-02-10 | SAT80 | 275019-206 - SAT80 PKG 3 COLO 2 CELL DAS Shop Drawings | 2025-02-17 | Completed |  | HS responded 2/14
2025-02-10 | SAT80 | 275019-207 - SAT80 PKG 3 COLO 2 CELL PS DAS Shop Drawings | 2025-02-17 | Completed |  | HS responded 2/16
2025-02-10 | SAT80 | SAT80 PKG 3 COLO 2 ROIP Shop Drawings - MS SAT80 Rio Medina - Submittal:273241-001 | 2025-02-17 | Completed |  | HS responded 2/14
2025-02-10 | SAT80/81 | RFI PH2-1045 - SAT 80/81 ROIP Panel at Guardhouse | 2025-02-13 | Completed |  | HS confirmed completed 2/11.
2025-02-11 | IAD12-13 | 275019-1.1_Distributed Antenna System_IAD 12-13_SD | 2025-02-18 | Completed |  | HS responded 2/17
2025-02-12 | CHI22 | 275019-23.1 - Phase 2 DAS Heliax - Test Reports | 2025-02-20 | Complete |  | HS responded 2/18.
2025-02-12 | PHX13 | PHX13 CA-D3127062-Sub# 273241-002-00-ROIP System As-Builts-FOR REVIEW | 2025-02-18 | Complete |  | HS responded 2/13.
2025-02-12 | PHX13 | PHX13 CA-D3127062-Sub# 275019-003-00-Commercial DAS System As-Builts-FOR REVIEW | 2025-02-18 | Complete |  | HS responded 2/13.
2025-02-12 | PHX13 | PHX13 CA-D3127062-Sub# 275019-004-00-Admin & COLO 1 ERRCS System As-Builts Drawings | 2025-02-18 | Complete |  | HS responded 2/13.
2025-02-12 | PHX74 | PHX74 - RFP for redesign to Fremont | 2025-02-19 | Completed |  | HS responded to
2025-02-12 | SAT14CA | REV2 - Tranche 1 As-Builts - CLAB - MS SAT14 CA - Submittal:017700-001-01 | 2025-02-18 | Complete |  | 2/21: Andrea Hallock confirmed no response needed from S2A even though we are still getting overdue notifications. 2/18 vendor confirmed uploaded docs to newforma for S2A.
2025-02-14 | CCO07 | CCO-07: Response to RFI #97 (DAS Antenna Detail Clarification) | 2025-02-18 | Completed |  | HS responded 2/14.
2025-02-17 | SAT80/81 | RFI PH2-1050 - SAT 80/81 - ROIP - SER ROIP Panel Location - MS SAT80 Rio Medina | 2025-02-19 | Complete |  | HS responded 2/18.
2025-02-19 | ATL06 | #27 50 19-7.0: DAS Commissioning Plan | 2025-02-26 | Complete |  | HS reponded 2/19
2025-02-19 | ATL06 | 27 50 19-8.0: DAS Benchmark Study | 2025-02-26 | Complete |  | HS responded 2/19
2025-02-19 | CHI22 | 275019-24.0 - Phase 2 Distribution Antenna System - Field Quality Control Test Reports | 2025-02-25 | Complete |  | HS responded 2/19 - revise and resubmit
2025-02-19 | QRO02 | RFI# 728 Power Supply | 2025-02-21 | Complete |  | HS responded 2/19
2025-02-19 | YTO11 | MSFT YTO11 Submittal 730R1 - wire/cable tag | 2025-02-26 | Complete |  | HS responded 2/19
2025-02-20 | LVL06 | LVL06 Submittal 497 - Commercial DAS Test Reports - 23-60857 | 2025-02-27 | Complete |  | HS responded 2/20
2025-02-21 | QRO01 | ROIP Commissioning document | 2025-02-28 | Completed
2025-02-24 | YQB06 | Submittal 27 50 19-002 - No contract in place for CA engagement | 2025-02-26 | Completed |  | HS responded 2/26
2025-02-26 | AVC43 | AVC43 Submittal 27 50 19-3.0 - DRB07- DAS Product - 22-60846 - email K Belle to confirm responded to. | 2025-03-05 | Completed |  | BW completed 2/27
2025-02-27 | LVL11 | LVL11 Submittal 273241-007-R2 - (ComNet) - PSDAS - 22-60853 | 2025-02-28 | Completed |  | HS completed 2/27
2025-02-28 | IAD12/13 | RFI 0715_IAD 12-13_ELEC-DAS_DAS Receptacle Locations | 2025-03-04 | Completed |  | HS completed 3/3
2025-03-02 | LVL06 | LVL06 Submittal 497.1 - Commercial DAS Test Repor - 23-60857 | 2025-03-04 | Completed |  | HS completed 3/4
2025-03-02 | LVL06 | LVL06 Submittal 506 - DAS As-Built Drawings - 23-60857 | 2025-03-04 | Completed |  | HS completed 3/4
2025-03-03 | MNZ03 | MNZ03 #0492 Rooftop Doghouse Antenna | 2025-03-05 | Completed |  | HS responded 3/4
2025-03-04 | SAT15 | RFI 0662 - Fire Alarm Wireless Dialer Details | 2025-03-06 | Completed |  | Not for S2A - redirected.
2025-03-04 | SAT40 | RFI-00641 - DAS Antenna Array RFI - Microsoft SAT40 Design | 2025-03-10 | Completed |  | BW responded 3/6 that this should be reassigned.
2025-03-04 | SAT40 | RFI-00642 - DAS Antenna Array Mast Pipe Count - Microsoft SAT40 Design | 2025-03-07 | Completed |  | BW completed
2025-03-04 | SAT80/81 | RFI PH2-1045-R1 - SAT 80/81 ROIP Panel at Guardhouse R1 - MS SAT80 Rio Medina | 2025-03-10 | Completed |  | HS responded 3/6
2025-03-05 | IAD04 | 21-004233 - IAD04 Loudoun County VA - RFI Forwarded: RFI 0559.2 - FCR DAS Rack 5 Power Requirements | 2025-03-07 | Completed |  | HS responded 3/6
2025-03-06 | LVL06 | LVL06 Submittal 497.2 Commercial DAS test Reports | 3/13/2025 | Completed |  | HS Responded 3/10/2025
2025-03-06 | LVL11 | LVL11-273241-007-R3 - (ComNet) - PSDAS System Des - 22-60853 | 2025-03-20 | Completed |  | HS responded - A/E contractor court
2025-03-06 | SAT40 | RFI-00646 - DAS Equipment Power - Microsoft SAT40 Design | 2025-03-10 | Completed |  | responded to 3/6
2025-03-06 | SAT40 | SUM-01628.0 - 27 50 19 - R0 - Cellular DAS Shop Drawings - WAITING ON OWNER DIRECTION - Bram responded | 2025-03-13 | Completed |  | BW responded
2025-03-06 | SAT40 | SUM-01628.0 - 27 50 19 - R0 - Cellular DAS Shop Drawings | 2025-03-13 | Completed |  | BW responded - Owners court
2025-03-06 | SAT40 | SUM-01630.0 - 27 50 19 - R0 - Cellular DAS Product Submittal | 2025-03-13 | Completed |  | BW responded
2025-03-06 | SAT40 | SUM-01632.0 - 27 50 19 - R0 - DAS Public Safety Product Submittal | 2025-03-13 | Completed |  | BW responded
2025-03-06 | SAT40 | SUM-01632.0 - 27 50 19 - R0 - DAS Public Safety Product Submittal | 2025-03-13 | Completed |  | BW responded - AE/Contractor court
2025-03-06 | SAT40 | SUM-01633.0 - 27 50 19 - R0 - ROIP DAS Product Data | 2025-03-13 | Completed |  | HS responded - not ours
2025-03-06 | SAT40 | SUM-01633.0 - 27 50 19 - R0 - ROIP DAS Product Data | 2025-03-13 | Completed |  | HS reponded - not in our court
2025-03-06 | YQB04 | ODYSSEY YQB04 DATA CENTER: Action Required for RFI #1234 | 2025-03-07 | Completed |  | HS responded.
2025-03-06 | YQB06 | YQB06 - Submittal #27 50 19-001.0 - RF benchmark plan | 2025-03-07 | Completed |  | HS responded 3/6
2025-03-06 | YTO11 | MSFT YTO11 Submittal 270R2 | 2025-03-13 | Completed |  | HS responded - A/E contractor court
2025-03-07 | AVC43 | AVC43 RFI 27.038.0 - DAS ID Clarification - 22-60846 | 2025-03-14 | Completed |  | HS responded - AE/Contractor court
2025-03-07 | AVC43 | AVC43 -RFI#27.038.0 - DAS Labeling conflict | 2025-03-10 | Completed |  | HS responded - AE/Contractor court
2025-03-07 | CCO06 | 27.50.19-11 R0 COMM-DAS Submittal | 2025-03-17 | Completed |  | HS responded 3/7
2025-03-07 | QRO02 | Submittal DIV 27-026 Flipex cabinet components - is this for S2A? | ? | Completed |  | HS reponded
2025-03-10 | IAD04 | 21-004233 - IAD04 Loudoun County VA - RFI Forwarded: RFI 0774 - Updated Cellular Design | 2025-03-13 | Completed |  | HS responded 3/17
2025-03-10 | IAD12/13 | RFI 0738_IAD 12-13_DAS Monitoring Modules in FCRs | 2024-03-13 | Completed |  | HS Responded
2025-03-10 | LVL06 | LVL06 Submittal 506.1 DAS As-built drawings |  | Completed |  | BW responded
2025-03-10 | LVL06 | LVL06 Submittal 570 – Tranche 2 Das Warranty | ? | Completed |  | HS Responded 3/7
2025-03-10 | SAT40 | RFI00647—Cable support Admin loading dock | 2025-03-12 | Completed |  | HW responded 3/10
2025-03-10 | YQB01 | YQB01 - Submittal DA-1041 | 2025-03-11 | Completed |  | HS responded 3/11
2025-03-11 | IAD05 | IAD05 RFI #259 (ROU Panel/DAS Power Locations) | 2025-03-14 | Completed |  | HS reponded 3/17
2025-03-13 | ATL06 | 27 32 41-11.0: RADIO OVER IP - Certifications | 2025-03-20 | Completed |  | HS responded
2025-03-13 | AVC43 | AVC43 RFI 27.038.0-REOPEN2 - DAS ID Clarification - 22-60846 | 2025-03-14 | Completed |  | HS responded - AE/Contractor court
2025-03-13 | LVL10 | LVL10-273241-010-R1 - (ComNet) - DAS Closeout Pac - 22-60848 | 2025-03-21 | Completed |  | HS responded 3/16 - need to be resubmitted
2025-03-13 | LVL10 | LVL10-273241-012-R1 - (ComNet) - DAS As-Built Dra - 22-60848 | 2025-03-27 | Completed |  | HS responded 3/15
2025-03-14 | AVC43 | AVC43 RFI 27.039.0 - DAS Antennas in Mech Galleri - 22-60846 | 2025-03-19 | Completed |  | HS responded 3/17
2025-03-14 | MNZ03 | RFI #542 ROIP & DAS Clairifcations | 2025-03-19 | Completed |  | BW to respond 3/14
2025-03-14 | SAT40 | RFI-00660 Cell DAS Signal Source Backhaul | 2025-03-19 | Completed
2025-03-14 | SAT80/81 | RFI PH2-0827-R1 - SAT80/81 PKG 2 - TELE - ERRCS Frequencies | 2025-03-18 | Completed
2025-03-18 | CHI22 | 273241-24.0_Phase 2 Radio Over IP - As Built | 2025-03-25 | Completed |  | BW responded
2025-03-18 | CHI22 | 275019-25.0_Phase 2 Distributed Antenna System - PS - As Built | 2025-03-25 | Completed |  | BW responded
2025-03-18 | CHI22 | 275019-26.0_Phase 2 Distributed Antenna System - Commercial - As Built | 2025-03-25 | Completed |  | BW responded
2025-03-18 | LVL07 | LVL07 RFI 96.2 - CDAS Verizon BDA - 23-60861 | 2025-03-21 | Completed |  | BW responded
2025-03-19 | LVL07 | LVL07 Submittal 360 - PSDAS Shop Drawings - 23-60861 | 2025-03-26 | Completed |  | HS responded 3/25
2025-03-19 | SAT14CA | RFI 1436 - P2 - Teamlinx - Public Safety Permitting Direction | 2025-03-21 | Completed |  | HS responded
2025-03-20 | ATL06 | 27 50 19-8.1 - Communication Systems Distributed Antenna System (DAS) - DAS Benchmark Study | 2025-03-27 | Completed |  | HS reponded 3/28
2025-03-20 | CCO06 | 27 50 19-12R0 COMM DAS Product Data | 2025-03-19 | Completed |  | HS responded 3/24
2025-03-20 | CCO06 | 27.50.19-11 R1 COMM-DAS Design | 2025-03-19 | Completed |  | HS responded 3/24
2025-03-20 | CHI22 | 275019-24.1-Phase 2 Distribution Antenna System - Field Quality Control Test | 2025-03-28 | Complete |  | BW responded
2025-03-20 | LVL07 | LVL07 RFI 96.2 - CDAS Verizon BDA - 23-60861 | 2025-03-24 | Completed |  | BW responded 3/24 - will issue a design update with RFI.
2025-03-20 | MNZ03 | 275019-3.0 - DAS - Pre-Wall Benchmark Study Report | 2025-03-28 | Completed |  | HS responded 3/20
2025-03-20 | SAT15 | RFI 0688 - FCR DAS Rack Location - MS SAT15 Design | 2025-03-24 | Completed |  | BW responded
2025-03-21 | ATL06 | 27 32 41 11.1 - Security Radio over IP ATL06 | 2025-03-21 | Completed |  | not for S2A - HS responded to reassign.
2025-03-23 | YTO11 | MSFT YTO11 Submittal 269 r2 - A/E looking into. S2A received 270. | 2025-03-25 | Completed |  | HS responded 3/25
2025-03-24 | SAT40 | SUM-01631.0 - 27 50 19 - R0 - Public Safety DAS - Shop Drawings | 2025-03-31 | Completed |  | Harold responded 3/25
2025-03-25 | QRO02 | Item 27 32 41 / #1258 DIV 27-1003 O&M MANUALS ROIP | 2025-04-04 | Completed |  | BW responded 4/4
2025-03-25 | SAT80/81 | RFI PH2-1045-R2 - SAT 80/81 ROIP Panel at Guardhouse R2 | 2025-03-27 | Completed |  | HS responded 3/25
2025-03-26 | LVL06 | LVL06 Submittal 611 - Tranche 3 DAS Warranty - 23-60857 | 2025-04-02 | Completed |  | HS completed 3/31
2025-03-26 | LVL11 | LVL11 RFI 454 - (WA) - Admin FCR - DAS PDU Power - 22-60853 | 2025-03-31 | Completed |  | BW noted - for A/E no scope for S2A
2025-03-26 | YTO11 | YTO11 Submittal 803 DAS Isolation Testing Report | 2025-04-02 | Completed |  | HS responded 3/27
2025-03-27 | PHX71 | PHX71 CA-D3127032-Sub# 017839-013-00-PHX71 - Specialty Low Voltage - Project record Drawings - Redlines-FOR REVIEW | 2025-04-03 | Completed |  | BW responded 3/31.
2025-03-28 | YTO11 | YTO11 RFI 609R4 Bell/Telus DAS Signal Source | 2025-03-31 | Completed |  | HS responded 3/28
2025-03-31 | MNZ03 | 275019-4.0 - DAS - CDAS Pre-Installation Benchmark Study Plan | 2025-04-02 | Completed |  | HS responded 4/1
2025-03-31 | MNZ03 | 275019-5.0 - DAS - PSDAS Post-Installation Benchmark Study Plan | 2025-04-02 | Completed |  | HS responded 4/1
2025-03-31 | MNZ03 | 275019-6.0 - DAS - PSDAS Pre-Installation Benchmark Study Plan | 2025-04-02 | Completed |  | HS responded 4/1
2025-03-31 | QRO? | HS mentioned on call - need details | 2025-04-02 | Completed |  | HS mentioned on call and said was handling.
2025-03-31 | QRO? | HS mentioned on call - need details | 2025-04-02 | Completed |  | HS mentioned on call and said was handling.
2025-03-31 | QRO06 | Item 27 32 41 / #1339 DIV 27-244.1 ROIP TEST SIGNAL INTESITY | 2025-04-03 | Completed |  | HS responded to 4/3.
2025-03-31 | QRO06 | Item 27 50 19 / #1336 DIV 27-243 DTF AND VWSR TEST REPORT | 2025-04-04 | Completed |  | BW responded 4/4
2025-03-31 | QRO06 | Item 27 50 19 / #1337 DIV 27-243.1 DAS TELEPHONY SIGNAL STRENGTH | 2025-04-04 | Completed |  | BW responded 4/4
2025-04-01 | LVL11 | LVL11 RFI 456 - (ComNet) - PSDAS Fiber Cable from - 22-60853 | 2025-04-04 | Completed |  | BW responded 4/6
2025-04-01 | SAT40 | RFI-00690 - Revised Scope for DAS Signal Source | 2025-04-03 | Complete |  | BW indicated completed at touch base 4/14
2025-04-01 | SAT80 | RFI PH2-0827-R2 - SAT 80/81 PKG 2 - TELE - ERRCS Frequencies | 2025-04-03 | Completed
2025-04-01 | YQB06 | 05 50 00-044-0-Support d’antenne télécom | 2025-04-04 | Completed |  | HS responded to 4/3.
2025-04-02 | ATL06 | ATL06: New RFI #336 (FOC AV Equipment Room Cable Support Clarification) | 2025-04-06 | Completed |  | HS advised not for S2A - to redirect to AV team.
2025-04-02 | ATL06 | RFI #337 (DAS, ROIP, Public Safety Pathways Identification) | 2025-04-07 | Completed |  | BW responded 4/3
2025-04-02 | YTO11 | YTO11 Submittal 269R3 DAS Design Package | 2025-04-09 | Completed |  | HS responded 4/6
2025-04-03 | CHI22 | 273241-24.1 - Phase 2 Radio Over IP - As Built | 2025-04-11 | Completed |  | BW responded 4/8
2025-04-03 | CHI22 | 275019-25.1 - Phase 2 Distributed Antenna System - PS - As Built | 2025-04-11 | Completed |  | BW responded 4/10
2025-04-03 | CHI22 | 275019-26.1 - Phase 2 Distributed Antenna System - Commercial - As Built.pdf | 2025-04-11 | Complete |  | BW responded 4/10
2025-04-04 | YQB06 | 27 50 19-002-1-ANTENNA SUPPORT DAS | 2025-04-04 | Completed |  | HS responded to 4/3.
2025-04-04 | YQB06 | 275019-002 - Rotec | 2025-04-04 | Completed |  | HS responded 4/4
2025-04-04 | YQB06 | 275019-003 – ADRF Filter | 2025-04-04 | Completed |  | HS responded 4/4
2025-04-04 | YQB06 | 275019-004 – Array structural support | 2025-04-04 | Completed |  | HS responded 4/4
2025-04-07 | IAD04 | RFI 0801 - ROU Relocation Per Power Plan Coordination | 2025-04-10 | Completed |  | BW responded 4/8
2025-04-08 | ACV01 | #677.0: MC Dean - PS DAS Test Results | 2025-04-15 | Completed |  | HS completed 4/14
2025-04-08 | AVC01 | #678.0: MC Dean - ROIP Coax Test Results - COLOs 2&3 | 2025-04-15 | Completed |  | HS completed 4/14
2025-04-08 | AVC01 | #679.0: MC Dean - CDAS Coverage Capacity Drive Test for VZN - COLOs 2&3 | 2025-04-15 | Completed |  | HS completed 4/14
2025-04-08 | AVC01 | #680.0: MC Dean - CDAS Coverage Capacity Drive Test for ATT - Admin & COLO1 | 2025-04-15 | Completed |  | HS completed 4/14
2025-04-08 | AVC01 | #681.0: MC Dean - CDAS Coverage Capacity Drive Test for VZN - Admin & COLO1 | 2025-04-15 | Completed |  | HS completed 4/14
2025-04-08 | AVC01 | #682.0: MC Dean - CDAS Coverage Capacity Drive Test for ATT - COLOs 2&3 | 2025-04-15 | Completed |  | HS completed 4/14
2025-04-08 | QRO02 | Item 27 32 41 / #1253 DIV 27-026 FLIPEX CABINET COMPONENTS | 2025-04-21 | Completed |  | BW completed 4/21
2025-04-08 | QRO02 | Item 27 50 19 / #1272 DIV 27-257 DAS CABLE TEST FOR DTF AND VWRS | 2025-04-14 | Completed |  | BW completed - revise and resubmit - 4/21
2025-04-08 | YTO40 | YTO40 - Substitution Request #031 RoIP Approved Contractor | 2025-04-08 | Completed |  | HS responded.
2025-04-10 | IAD04 | 21-004233 275019-3.0 - Cellular DAS O&M Manual - A/E requested restamp/resend | 2025-04-18 | Completed |  | HS responded 4/11/25
2025-04-10 | IAD04 | 275019-4.0 - PSDAS O&M Manual | 2025-04-18 | Complete |  | HS responded 4/11/25
2025-04-10 | YTO11 | YTO11 RFI 609R5 | 2025-04-14 | Completed |  | HS responded 4/10
2025-04-11 | IAD04 | #27 32 41-14.0: ROIP Cx Documentation | ? | Completed |  | HS responded 4/11 - before official notification came through.
2025-04-11 | IAD04 | #27 50 19-6.0: PSDAS Cx Documentation | ? | Completed |  | HS responded 4/11 - before official notification came through.
2025-04-14 | IAD04 | 275019-5.0 - Cellular DAS Cx Documentation | 2025-04-21 | Completed |  | HS responded 4/17
2025-04-14 | YTO11 | YTO11 Submittal 269R4 DAS Design Package | 2025-04-21 | Completed |  | HS responded 4/15
2025-04-15 | ATL06 | ATL06: RFI #358 (DAS ROU Circuit Designation) | 2025-04-18 | Complete |  | Per HS - not for S2A
2025-04-15 | LVL07 | LVL07 Submittal 376 - PSDAS Benchmark Study Test - 23-60861 | 2025-04-22 | Completed |  | HS responded 4/18
2025-04-15 | LVL07 | LVL07 Submittal 377 - CDAS Benchmark Study Test R - 23-60861 | 2025-04-22 | Complete |  | HS responded 4/18
2025-04-15 | LVL07 | LVL07 Submittal 378 - CDAS Certification Letter - 23-60861 | 2025-04-22 | Completed |  | HS responded 4/18.
2025-04-15 | LVL07 | LVL07 Submittal 379 - PSDAS Certification Letter - 23-60861 | 2025-04-22 | Completed |  | BW responded 4/17
2025-04-15 | SAT14CA | RFI 1464 - Teamlinx - Reference RFI #753 - P2 - RoIP E-house Coverage | 2025-04-17 | Completed |  | HS responded
2025-04-16 | SAT40 | SUM-01250 - 27 50 19 - R0 - COMMUNICATION SYSTEMS DISTRIBUTED ANTENNA SYSTEM (DAS) - Warranty - Review | 2025-04-24 | Complete |  | HS responded 4/17
2025-04-16 | SAT40 | SUM-01252 - 27 50 19 - R0 - COMMUNICATION SYSTEMS DISTRIBUTED ANTENNA SYSTEM (DAS) - O&M Manual - Review | 2025-04-24 | Completed |  | BW responded 4/17
2025-04-17 | FTY02 | FTY02: Action Required for Submittal (#27 50 19-3.0: Cell & PS DAS Design) | 2025-04-17 | Completed |  | BW requested PM add HS and KP to notifications going forward and S2A team does not have access to link.
2025-04-17 | LVL07 | LVL07 RFI 96.2-REOPEN2 - CDAS Verizon BDA-REOPEN2 - 23-60861 | 2025-04-27 | Completed |  | BW responded 4/17
2025-04-17 | SAT80/81 | RFI PH2-0827-R3 - SAT 80/81 PKG 2 - TELE - ERRCS Frequencies R3 | 2025-04-19 | Completed |  | HS responded 4/17.
2025-04-21 | LVL06 | LVL06 Submittal 650 - Tranche 1-4 DAS As-Builts - 23-60857 | 2025-04-28 | Completed |  | HS completed 4/25
2025-04-22 | LVL11 | LVL11 Submittal - PSDAS NEMA Enclosure Substituti - 22-60853 | 2025-05-05 | Completed |  | BW completed week of 4/28
2025-04-23 | QRO02 | RFI #805 ROIP - ROIP GAIN AND LOSS VALUES | 2025-04-25 | Completed |  | HS completed 4/25
2025-04-23 | SAT15 | RFI 0737 - Follow up to RFI 350 - TeamLinx - Signal Source Options | 2025-04-28 | Completed |  | HS completed 4/25
2025-04-30 | AVC43 | AVC43 RFI 27.041.0 - Additional Admin Conduit for - 22-60846 | 2025-05-05 | Complete |  | HS responded 5/1
2025-04-30 | AVC43 | AVC43 RFI 27.042.0 - PDAS Backer Board - 22-60846 | 2025-05-05 | Complete |  | HS responded 5/1
2025-04-30 | YQB06 | RFI 700 | 2025-04-30 | Complete |  | HS responded 4/30
2025-04-30 | YQB06 | RFI 771 DAS coax cabling between Cell1/Cell2 | 2025-04-30 | Complete |  | HS responded 4/30
2025-04-30 | YQB06 | RFI 772 | 2025-04-30 | Complete |  | HS responded 4/30
2025-05-01 | EAT12 | 0468.1 - Antenna Locations and Structural Framing | 2025-05-02 | Completed |  | HS responded 5/1
2025-05-01 | MNZ03 | MNZ03 - PCO 810161 - RFI 492 - Rooftop Doghouse Addition | 2025-05-01 | Completed |  | HS responded 5/1
2025-05-01 | PHX72 | PHX72 CA-D3127038-Sub# 273241-011-00-DAS-ROIP Certifications-FOR REVIEW | 2025-05-08 | Completed |  | HS responded 5/5
2025-05-05 | MNZ03 | RFI 0414.1 - ROIP IbWave files | 2025-05-08 | Completed |  | HS responded 5/7
2025-05-05 | QRO02 | 27 50 19 - Submittal #1272 - COMMUNICATION SYSTEMS DISTRIBUTED ANTENNA SYSTEM (DAS) | 2025-05-07 | Complete |  | HS + BW completed 5/5
2025-05-05 | SAT15 | RFI 0753 - TeamLinx - ADMIN Annunciator Panel Mounting Location Clarification | 2025-05-07 | Closed |  | not for s2A - was mistakenly routed in our direction.
2025-05-06 | CHI11 | Submittal 275019-001-0_391_Distributed Antenna System | 2025-05-13 | Completed |  | HS responded 5/6.
2025-05-06 | IAD04 | Submittal 275019-4.1 - PSDAS OM Manual | 2025-05-14 | Completed |  | HS responded 5/9
2025-05-07 | AVC43 | AVC43 RFI 27.042.1 - PDAS Backer Board R1 - 22-60846 | 2025-05-12 | Completed |  | HS responded 5/7
2025-05-07 | IAD05 | RFI #359: DAS/PSDAS iBwave Files | 2025-05-07 | Completed |  | HS reponded 5/7
2025-05-07 | PHX82 | PHX82 CA-D3127048-Sub# 273241-001-00-Radio Over IP | 2025-05-13 | Completed |  | HS responded 5/9
2025-05-07 | PHX82 | PHX82 CA-D3127048-Sub# 275019-001-00-DAS Submittal | 2025-05-13 | Completed |  | HS responded 5/9
2025-05-08 | LVL06 | LVL06 RFI 475 - DRB06 Carrier Circuit - 23-60857 | 2025-05-09 | Completed |  | HS responded 5/9
2025-05-08 | YTO11 | YTO11 Submittal 843 | 2025-05-14 | Completed |  | HS responded 5/9
2025-05-12 | PHX72 | D3127038-Sub# 275019-002-00-Antenna Validation Workbook | 2025-05-16 | Completed |  | HS responded 5/14
2025-05-12 | YQB06 | Submittal 27 05 28-025.0 | 2025-05-19 | Completed |  | HS responded 5/12
2025-05-13 | EAT12 | 275019-001 - Rev. 1 Communication Systems Distributed Antenna Systems - Product Data Substitution Request | 2025-05-13 | Completed |  | BW responded 5/14
2025-05-13 | EAT12 | 275019-002 Commercial Cell DAS Shop Drawings submittal | 2025-05-22 | Completed |  | BW completed 5/19
2025-05-13 | LVL06 | LVL06 Submittal 695 - Finalized DAS As-Builts - 23-60857 | 2025-05-15 | Completed |  | HS responded 5/14
2025-05-13 | QRO02 | Submittal #1280-27 32 41 DIV 27-259 ROIP CABLE TEST FOR DTF AND VWSR | 2025-05-20 | Completed |  | HS completed 5/20 - revise and resubmit
2025-05-19 | CHI05 | CHI05 Hoffman - RFI: RFI 1296 - COLO 3 Cell 4 DAS Panel Power | 2025-05-22 | Completed |  | HS/BW responded 5/20
2025-05-20 | QRO02 | Item 27 32 41 / #1282 DIV 27-258 ROIP SIGNAL STRENGTH | 2025-05-26 | Complete |  | HS responded 6/6
2025-05-21 | EAT12 | Submittal 275019-003 - Rev. 0 has new comments EAT12 Data Center - 6524006 | 2025-05-23 | Complete |  | BW responded 5/22
2025-05-21 | IAD04 | 275019-3.1 - Cellular DAS OM Manual | 2025-05-29 | Complete |  | HS responded 5/23
2025-05-21 | IAD04 | 275019-6.1 - PSDAS Cx Documentation | 2025-05-30 | Completed |  | HS responded 5/23
2025-05-21 | LVL06 | LVL06 Submittal 715 - Tranche 5 DAS RoIP Warranty - 23-60857 | 2025-05-28 | Completed |  | BW responded 5/21
2025-05-21 | LVL06 | LVL06 Submittal 718 - COLO4 5 DAS Test Reports - 23-60857 | 2025-05-28 | Completed |  | BW responded 5/23
2025-05-21 | LVL07 | LVL07 RFI 275 - PSDAS NEMA Enclosure - 23-60861 | 2025-05-23 | Completed |  | HS responded 5/22.
2025-05-21 | LVL10 | LVL10-270010-012-R1 - ( ComNet) - Telecom COLO3 W - 22-60848 | 2025-06-03 | Completed |  | BW responded 5/21
2025-05-21 | LVL10 | LVL10-270010-024-R1 - ( ComNet) - Telecom COLO4 W - 22-60848 | 2025-06-03 | Completed |  | BW responded 5/21
2025-05-22 | CPQ03 | Submittal 733 - 006-CPQ03-SUB-T-DAS-006-CPQ03-SUB-T-DAS | 2025-05-23 | Completed |  | 6/23: per HS remove from list.
2025-05-22 | QRO02 | Item 27 32 41 / #1284 DIV 27-261 CONFIGURATION WITH FINAL IP FOR ROIP | 2025-05-28 | Complete |  | HS responded 5/22
2025-05-23 | QRO06 | Item 27 50 19 / #1342 DIV 27-245 CONFIGURATION WITH FINAL IP FOR DAS | 2025-05-29 | Complete |  | HS completed 5/23
2025-05-27 | ATL06 | RFI #417 (Revision 1): DAS Rack 5 in FCR PDU | 2025-05-28 | Completed |  | BW responded 5/27
2025-05-27 | QRO02 | ID 8073 - DIV 27- BMCD PW- Antenna Installation | 2025-05-29 | Complete |  | HS responded 5/27
2025-05-27 | QRO02 | ID 8074 - DIV27- BMCD PW- ROU Installation | 2025-05-29 | Complete |  | HS responded 5/27
2025-05-27 | QRO02 | ID 8075 - DIV27-BMCD PW- SER – Fiplex Master | 2025-05-29 | Complete |  | HS responded 5/27 - rejected.
2025-05-27 | QRO02 | ID 8076- DIV 27- BMCD PW-RoIP ROU –Water Treatment Facility | 2025-05-29 | Complete |  | HS responded 5/27
2025-05-28 | MNZ03 | MNZ03 - 275019-8.0 - CDAS BOM | 2025-06-03 | Complete |  | HS responded 6/4
2025-05-28 | QRO02 | Item 27 32 41 / #1280 (Rev 1) DIV 27-259 ROIP CABLE TEST FOR DTF AND VWSR | 2025-06-03 | Complete |  | HS responded 6/9
2025-05-28 | QRO06 | Item 27 32 41 / #1338 (Rev 1) DIV 27-244 ROIP TEST CABLE | 2025-06-03 | Complete |  | BW responded 6/2.
2025-05-28 | YTO11 | Submittal #852.0 DAS/RoIP labeling | 2025-06-04 | Complete |  | BW responded 6/3
2025-05-29 | IAD05 | Response to RFI #391 (Day Wireless Design Validation - RoIP, Cellular, Public Safety DAS) | 2025-06-09 | Complete |  | HS responded 6/2
2025-05-30 | LVL07 | LVL07 Submittal 387 - CDAS Shop Drawings - 23-60861 | 2025-06-06 | Completed |  | HS reponded 6/1
2025-05-30 | SAT80 | 275019-200 - SAT 80 COLO 3-5 DAS Shop Drawings | 2025-06-06 | Complete |  | HS responded 6/3.
2025-05-31 | QRO06 | Item 27 50 19 / #1342 (Rev 1) DIV 27-245 CONFIGURATION WITH FINAL IP FOR DAS | 2025-06-05 | Complete |  | HS responded 6/2.
2025-05-31 | SAT80 | 273241-002 - SAT 80 COLO 3-5 ROIP Shop Drawings | 2025-06-06 | Complete |  | HS responded 6/3.
2025-05-31 | SAT80 | RFI PH2-1120 - SAT80 DAS Equipment Grounding | 2025-06-03 | Complete |  | HS responded 6/3.
2025-06-02 | MNZ03 | CDAS - Product Certification | 2025-06-06 | Complete |  | BW responded 6/6
2025-06-02 | MNZ03 | MNZ03 - 275019-7.0 - PSDAS BOM | 2025-06-06 | Complete |  | BW responded 6/6
2025-06-02 | MNZ03 | MNZ03 - 275019-9.0 - CDAS - PD | 2025-06-06 | Complete |  | BW responded 6/2.
2025-06-02 | QRO06 | Submittal #1336-27 50 19: DTF & VSWR Testing (Rev1) | 2025-06-06 | Complete |  | BW responded 6/2
2025-06-03 | CYS17 | CYS17 CA-D3128088-Sub# 017700-431-00-CLOSEOUT_CYS17_COLO 3-5 DASROIP | 2025-06-09 | Complete |  | BW responded 6/10
2025-06-03 | LVL07 | LVL07 Submittal 388 - PSDAS Site Acceptance Test - 23-60861 | 2025-06-03 | Complete |  | HS responded 6/3
2025-06-03 | LVL07 | LVL07 Submittal 389 - CDAS Site Acceptance Test P - 23-60861 | 2025-06-03 | Complete |  | HS responded 6/3
2025-06-03 | LVL10 | LVL10-270519-003-R3 - (ComNet) - PSDAS System Des - 22-60848 | 2025-06-10 | Complete |  | HS responded 6/4.
2025-06-03 | PHX72 | PHX72 CA-D3127038-Sub# 275019-001-02-DAS Package PD & SD-FOR REVIEW | 2025-06-10 | Complete |  | HS responded 6/9
2025-06-03 | QRO02 | RFI #858 TCOM - DOCUMENTATION FOR FINAL DELIVERY OF THE ROIP SYSTEM | 2026-06-05 | Complete |  | HS responded 6/5.
2025-06-03 | YTO11 | YTO11 Submittal 895 | 2025-06-10 | Complete |  | HS responded 6/9
2025-06-04 | PHX72 | PHX72 CA-D3127038-Sub# 273241-001-02-RoIP Package PD & SD | 2025-06-11 | Complete |  | HS responded 6/9
2025-06-04 | SAT40 | RFI-00794 - ADMIN Annunciator Panel Mounting | 2025-06-06 | Complete |  | HS responded 6/6
2025-06-05 | ATL06 | ATL06: New RFI #442 (FCR DAS Fiber Housing Unit Location) | 2025-06-10 | Complete |  | HS responded - reroute to telecom
2025-06-05 | MNZ03 | 275019-12.0 - PSDAS Product Data | 2025-06-10 | Complete |  | BW responded 6/10
2025-06-05 | YQB01 | RFI 781 - DAS addition of conduit | 2025-05-30 | Complete |  | HS responded 6/8
2025-06-05 | YQB01 | RFI 782 - Conduit and electrical boxes for cable | 2026-06-02 | Complete |  | HS responded 6/8
2025-06-05 | YQB01 | RFI 784 - DAS Paratonnere to approuves | 2026-06-02 | Complete |  | HS responded 6/8
2025-06-05 | YTO11 | YTO11 Submittal 803R1 - DAS Isolation Testing Report | 2025-06-12 | Complete |  | HS responded 6/5.
2025-06-06 | YQB01 | YQB01 - Submittal DAS benchmark Study-RF Survey- DA-1384 | 2025-06-12 | Complete |  | HS responded 6/10
2025-06-09 | CHI11 | 275019-001-1_391_Distributed Antenna System | 2025-06-16 | Complete
2025-06-09 | LVL11 | LVL11-270010-014-R1 - (ComNet) - Telecom COLO2 Wa - 22-60853 | 2025-06-16 | Complete |  | HS responded 6/10 - reroute to telecom
2025-06-09 | LVL11 | LVL11-270010-019-R1 - (ComNet) - Telecom COLO3 Wa - 22-60853 | 2025-06-16 | Complete |  | HS responded 6/10 - reroute to telecom
2025-06-09 | MNZ03 | RFI 0688 - PS & COMM DAS ROU COLO MOUNTING & GROUNDING | 2025-06-11 | Complete |  | HS responded 6/9
2025-06-09 | QRO02 | RFI #864 DAS - DOCUMENTATION FOR FINAL DELIVERY OF THE DAS SYSTEM | 2025-06-11 | Complete |  | HS responded 6/10
2025-06-10 | EAT12 | Submittal 275019-004-0 - PS DAS Site Survey | 2025-06-17 | Completed |  | BW responded 6/12
2025-06-10 | MNZ03 | RFI 0689 - ROIP Confirmations - Guardhouse ROIP Antenna, Guardhouse Portable ROIP Radio | 2025-06-11 | Complete |  | HS responded 6/10
2025-06-10 | SAT15 | 017700-017 - Closeout Procedures - Punch Walk DAS-ROIP - CL | 2025-06-17 | Completed |  | BW responded 6/12
2025-06-10 | YQB01 | DA-1419 - Antenna F16V28DHFB | 2025-06-23 | Completed |  | HS responded 6/12
2025-06-10 | YQB01 | DA-1420 - Antenna OY19V18D | 2025-06-23 | Completed |  | HS responded 6/12
2025-06-10 | YQB06 | RFI # 848 | 2025-06-13 | Complete |  | HS responded 6/12
2025-06-10 | YQB06 | RFI # 849 | 2025-06-13 | Complete |  | HS responded 6/12
2025-06-10 | YTO11 | YTO11 RFI 954 DAS Pathway - Transition Points | 2025-06-12 | Complete |  | HS responded 6/10
2025-06-11 | PHX13 | PHX13 CA-D3127062-Sub# 275019-005-00-ERRCS Admin - COLO2 Closeout Package | 2025-06-18 | Completed |  | HS responded 6/13
2025-06-12 | MNZ03 | RFI 0687.1 - Methods for Coax Connectors & Jumpers | 2025-06-16 | Completed |  | HS responded 6/12
2025-06-13 | CPQ11 | #1036-1036-CPQ11-SUB-T-W-DAS-202506121336 | 2025-06-13 | Complete |  | BW responded 6/16
2025-06-13 | CPQ11 | #1037-1037-CPQ11-SUB-T-W-DAS-202506121331 | 2025-06-13 | Complete |  | BW responded 6/16
2025-06-13 | CPQ11 | #1038-1038-CPQ11-SUB-T-W-DAS-202506111911 | 2025-06-13 | Complete |  | BW responded 6/16
2025-06-13 | CPQ11 | #1039-1039-CPQ11-SUB-T-W-DAS-202506111901 | 2025-06-13 | Complete |  | BW responded 6/16
2025-06-13 | CPQ11 | #1040-1040-CPQ11-SUB-T-W-DAS-202506111855 | 2025-06-13 | Complete |  | BW responded 6/16
2025-06-13 | CPQ11 | #1041-1041-CPQ11-SUB-T-W-DAS-202506111850 | 2025-06-13 | Complete |  | BW responded 6/16
2025-06-13 | CPQ11 | #1042-1042-CPQ11-SUB-T-W-DAS-202506111827 | 2025-06-13 | Complete |  | BW responded 6/16
2025-06-13 | EAT13 | GC RFI Bidder review | 2025-06-13 | Completed |  | HS responded 6/13
2025-06-13 | SAT15 | SAT15 – RFI#800 | 6/13/25? | Completed |  | HS reponded 6/13
2025-06-16 | CHI11 | CHI11 RFI 0411_Additional Details for the GPS Antenna | 2025-06-17 | Completed |  | HS responded 6/17 - not for S2A
2025-06-16 | QRO02 | RFI #867 TCOM - CHANGE OF RADIO MODEL | 2025-06-18 | Completed |  | HS responded 6/16
2025-06-16 | YQB06 | #27 05 53-001.0: Labelling Panduit | 2325-06-01 | Completed |  | HS responded 6/16
2025-06-17 | CPQ11 | Submittal 1049 - DAS Benchmark Study | 2025-06-24 | Completed |  | HS responded 6/18
2025-06-17 | SAT40 | SUM-01248 - 27 50 19 - R0 - COMMUNICATION SYSTEMS DISTRIBUTED ANTENNA SYSTEM (DAS) - Commissioning Plan - Review | 2025-06-24 | Completed |  | HS responded 6/18
2025-06-18 | YQB04 | RFI #1518 DAS antenna in Electrical room Colo1 | 2025-06-20 | Completed |  | HS responded 6/20
2025-06-18 | YQB06 | #27 50 19-005.0: Antenne 5379_GI081-T6971 | 2025-06-24 | Completed |  | HS responded 6/18
2025-06-19 | ATL06 | RFI #467 (ROIP Power Clarification) | 2025-06-23 | Complete |  | HS 6/23 said to remove from list.
2025-06-19 | IAD04 | 27 32 41-15.0: ROIP Cx Documentation - COLO 3 | 2025-06-20 | Completed |  | HS responded 6/20 - not for S2A
2025-06-19 | IAD04 | 27 32 41-16.0: ROIP Cx Documentation - COLO 4 | 2025-06-20 | Completed |  | HS reponded 6/20 - not for S2A
2025-06-19 | IAD04 | 275019-7.0 - DAS Cx Documentation - C3 | 2025-06-26 | Completed |  | HS responded 6/20
2025-06-19 | MNZ03 | 012500-43.0 - R7 Radio SR | 2025-06-26 | Complete |  | HS responded 6/23
2025-06-19 | MNZ03 | 012500-44.0 - Compact Combining System SR | 2025-06-26 | Completed |  | HS responded 6/20
2025-06-19 | QRO06 | Submittal #1336 DIV 27-243 DTF AND VWSR TEST REPORT status | 2025-06-23 | Completed |  | HS noted ok to complete 6/30
2025-06-20 | YQB04 | #27 50 19.1-2.1: Distributed Antenna System (DAS) | 2025-07-08 | Completed |  | HS responded 6/25
2025-06-20 | YQB04 | RFI 1503 - telus request for 3500MHZ on DAS | 2025-06-20 | Completed |  | HS responded 6/20
2025-06-21 | QRO02 | Issue #8072 DIV27- BMCD PW- DAS Rack | 2026-06-23 | Completed |  | HS responded
2025-06-23 | CPQ03 | CPQ3 - Submittal 775 - 008-CPQ03-SUB-T-DAS-008-CPQ03-SUB-T-DAS | 2025-06-30 | Completed |  | 6/24 HS responded - need more info
2025-06-23 | CPQ11 | #1393 CPQ11-RFI-T-DAS | 2025-06-24 | Completed |  | HS responded 6/23
2025-06-24 | CCO06 | RFI #551 (IFC DAS & DRB13 DAS) | 2025-06-27 | Completed |  | HS noted ok to complete 6/30
2025-06-24 | LYH10 | LYH10 - 000729 - DAS antenna needing new location on the building | 2025-06-26 | Completed |  | HS responded 6/25
2025-06-24 | PHX82 | PHX82 CA-D3127048-Sub# 273241-001-01-Radio Over IP | 2025-07-01 | Completed |  | HS responded 6/25
2025-06-24 | PHX82 | PHX82 CA-D3127048-Sub# 275019-001-01-DAS Submittal | 2025-07-01 | Completed |  | HS responded 6/25
2025-06-24 | QRO01 | #27.50.19-11.1: DAS Test report | 2025-06-25 | Completed |  | HS responded 6/25
2025-06-25 | CHI11 | CHI11 RFI 0436_DAS FBDA Location | 2025-06-27 | Completed |  | HS responded 6/26
2025-06-25 | YQB01 | Submittal #DA-1041-R1 - 041 Support Antenne telecom | 2025-07-03 | Complete |  | HS responded 6/29
2025-06-26 | CPQ03 | CPQ3 - Substitution 386 - Relatório de detalhes do formulário-202506261953 | 2025-06-30 | Completed |  | HS responded 6/29
2025-06-26 | IAD04 | 275019-8.0 - DAS Cx Documentation - COLO 4 | 2025-07-02 | Completed |  | HS responded 6/29
2025-06-26 | MNZ03 | MNZ03 - 273241-4.0 - FCC License Documentation | 2025-07-02 | Completed |  | HS responded 6/29
2025-06-26 | SAT40 | SUM-01248 - 27 50 19 - R1 - COMMUNICATION SYSTEMS DAS - Commissioning Plan | 2025-07-03 | Completed |  | HS responded 6/29
2025-06-27 | CPQ03 | CPQ3 - Submittal 679 - 007-CPQ03-SUB-T-DAS-001-CPQ03-SUB-T-DAS-GEN | 2025-07-09 | Completed |  | Waiting for A/E to send it. HS asked to remove from list 7/9
2025-06-27 | MNZ03 | RFI #731 RoIP Coax Routing | 2025-07-01 | Completed |  | HS responded 6/29
2025-06-27 | QRO02 | Item 27 32 41 / #1299 DIV 27-309 COMMISSIONING ROIP SYSTEM | 2025-07-04 | Completed |  | HS responded 6/30
2025-06-27 | YQB06 | RFI Telus AWS4 | 2025-07-01 | Completed |  | HS - response not needed
2025-06-30 | AVC02 | AVC02: Action Required for RFI #4 | 2025-06-30 | Completed |  | HS - not for S2A
2025-06-30 | LVL11 | LVL11-273241-003-R1 - (ComNet) - ROIP Closeout Pa - 22-60853 | 2025-07-11 | Completed |  | HS - response not needed
2025-06-30 | LVL11 | LVL11-273241-008-R1 - (ComNet) - ROIP As-Built Dr - 22-60853 | 2025-07-11 | Completed |  | HS - response not needed
2025-06-30 | MNZ03 | RFI 0689.1 - ROIP Confirmations - Guardhouse ROIP Antenna, Guardhouse Portable ROIP Radio | 2025-07-01 | Complete |  | HS responded 6/30
2025-07-02 | ATL06 | ATL06: New RFI #487 (ROU Pathways ) | 2025-07-07 | Completed |  | HS responded 7/3
2025-07-02 | LVL10 | LVL10 Submittal 270010-013-R1 COLO5 Warranty | 2025-07-15 | Completed |  | HS responded 7/7
2025-07-03 | MNZ03 | 012500-44.0 - Compact Combining System - SR | 2025-07-10 | Completed |  | HS responded 7/3
2025-07-03 | MNZ03 | RFI #731.1 RoIP Coax Routing | 2025-07-08 | Complete |  | HS responded 7/8
2025-07-03 | SAT14CA | 017700-001-03 - Tranche 1 AsBuilts - CLAB | 2025-07-11 | Completed |  | HS responded 7/7
2025-07-03 | YQB06 | 27 05 53-001.1 Labelling Panduit | 2025-07-10 | Completed |  | HS responded 7/3
2025-07-03 | YQB06 | RFI # 849 - reopened with additional info from GC | 2025-07-07 | Complete |  | HS rereviewed and saw no changes. Confirmed 7/8 option 1.
2025-07-03 | YQB06 | YQB06 - DAS submittal 05 50 00-044 | 2025-07-09 | Completed |  | HS responded 7/7
2025-07-03 | YQB06 | YQB06 - DAS submittal 05 50 00-044 - R2 | 2025-07-09 | Completed |  | HS answered again.
2025-07-04 | YTO11 | MSFT YTO11 RFI 1013 | 2025-07-08 | Completed |  | HS responded 7/7
2025-07-07 | YQB01 | Submittal DA-1511 Rev 0 ADX V fiber distributed antenna system | 2025-07-11 | Completed |  | HS responded 7/7
2025-07-08 | LYH10 | LYH10 RFI # 000729.1 - DAS antenna needing new location on the building - r1 | 2025-07-09 | Completed |  | Logged as responded to on 6/26. HS responded/completed 7/9.
2025-07-08 | YQB06 | YQB06: RFI 892 | 2025-07-09 | Completed |  | HS responded 7/8 but attachment referenced #869
2025-07-08 | YQB06 | YQB06: RFI 896 | 2025-07-09 | Completed |  | HS responded 7/8 on email thread with subject RFI 892
2025-07-09 | QRO06 | 27 32 41 - RADIO COMMUNICATIONS EQUIPMENT | 2025-07-15 | Completed |  | HS responded 7/9
2025-07-10 | CHI11 | CHI11 RFI 0451_DayWireless RoIP Design Review | 2025-07-14 | Completed |  | HS responded 7/11
2025-07-10 | EAT12 | PSDAS Shop Drawing Submital Submittal 275019-002 - Rev. 2 EAT12 Data Center - 6524006 | 2025-07-17 | Complete |  | HS responded 7/14
2025-07-10 | IAD12-13 | RFI 0770_IAD 13 SITE_CIVIL_Retaining Wall Radius - For S2A? | 2025-07-11 | Complete |  | NOT for S2A
2025-07-10 | LYH10 | RFI 745? Change charger locations - KP has no record of RFI notification. | 2025-07-11 | Completed |  | Not for S2A. HS reaching out to have S2A removed.
2025-07-11 | LVL10 | DAS As-Built Drawings - COLO 3 - Microsoft LVL10 - Submittal:LVL10-273241-018 | 2025-07-24 | Complete |  | HS responded 7/11
2025-07-11 | LVL10 | DAS Closeout Package - Admin and COLO 1 to 3 - Submittal:LVL10-273241-017 | 2025-07-24 | Complete |  | HS responded 7/14 - revise and resubmit
2025-07-11 | PHX13 | email from Andrea Frazier-Sanchez to review RFI categories. | 2025-07-11 | Completed |  | KP - nothing on the list for S2A - all for electrical.
2025-07-11 | PHX14 | email from Andrea Frazier-Sanchez to review RFI categories. | 2025-07-11 | Completed |  | KP - nothing on the list for S2A - all for electrical.
2025-07-14 | CHI05 | 27 50 19-102.0_DAS Public Safety Fiber - Test Reports | 2025-07-21 | Completed |  | HS responded 7/16
2025-07-14 | CHI05 | 27 50 19-104.0_Communication Systems Distributed Antenna System (DAS) | 2025-07-21 | Completed |  | HS responded 7/16
2025-07-14 | CHI05 | 27 50 19-105.0_DAS Heliax ROIP - Test Reports | 2025-07-21 | Completed |  | HS responded 7/16
2025-07-14 | CHI05 | 27 50 19-103.0_DAS ROU Fiber - Test Reports | 2025-07-21 | Completed |  | HS responded 7/16
2025-07-14 | QRO06 | 27-244.1 - RoIP test | 2025-07-21 | Completed |  | HS responded 7/16
2025-07-14 | YTO11 | MSFT YTO11 SR 54 R1 Substituion Request RoIP Multicoupling combiners | 2025-07-21 | Complete |  | HS responded again 7/16.HS responded 7/14 - revise and resubmit
2025-07-15 | SAT14CA | RFI 1595 - P2 - Remote Unit DAS Power Supply - MS SAT14 CA | 2025-07-17 | Complete |  | HS responded 7/16 - needs to be addressed by electrical.
2025-07-16 | CPQ03 | CPQ3 - Submittal 679 - 007-CPQ03-SUB-T-DAS-001-CPQ03-SUB-T-DAS-GEN | 2025-07-16 | Completed |  | HS responded 7/17
2025-07-17 | EAT12 | 275019-002 - Rev. 3 | 2025-07-24 | Completed 07/23 |  | HS responded 7/17
2025-07-17 | LVL07 | CDAS Verizon BDA-REOPEN3 RFI 96.2 | 2025-07-19 | Completed |  | Reissued as new RFI under 96.3
2025-07-17 | LVL11 | LVL11 Submittal 270010-020-R1 | 2025-07-25 | Completed |  | HS responded 7/22
2025-07-18 | LVL07 | LVL07 RFI 96.3 | 2025-07-23 | Completed |  | BW responded 7/23 - with note 'issue drawings 7/28'
2025-07-21 | YQB01 | Submittal DA-1556 : Connecteurs JMA | 2025-07-25 | Completed |  | HS responded 7/21
2025-07-21 | YTO11 | RFI 940 - DAS RoIP Jumpers - AE requests to have expedited. | 2025-07-29 | Completed | 2025-07-21 | HS responded 7/21 **Hot email response from AE: Shows as overdue.
2025-07-22 | SAT80-81 | 270820-039 - SAT80-81 - SAT80 to SAT81 DAS Interconnect Testing - Test Reports | 2025-07-29 | Completed |  | HS responded 7/22
2025-07-25 | CHI11 | 273241-001-0_456_ROIP | 2025-07-31 | Completed |  | Harold responded 7/28.
2025-07-25 | QRO02 | Item 27 50 19 / #1308 DIV 27-256 DAS SIGNAL STRENGTH - ASU | 2025-07-31 | Completed |  | HS responded 7/29
2025-07-25 | QRO02 | Item 27 50 19 / Submittal #1309 DIV 27-260 DAS SYSTEM EQUIPMENT CONFIGURATION - ASU | 2025-08-01 | Completed |  | HS responded 7/29
2025-07-25 | YTO11 | MSFT YTO11 Submittal 975 | 2025-08-01 | Completed | 2025-07-29 | HS responded 7/29 **Hot email response from AE: Shows as overdue.
2025-07-28 | QRO06 | Submittal #1336 DIV 27-243 DTF AND VWSR TEST REPORT status | 2025-07-24 | Completed |  | HS responded against 7/28. No record of receiving notification of this one on 7/18.
2025-07-29 | CHI11 | 275019-001-0_458_Commercial DAS | 2025-08-05 | Completed |  | HS responded 7/30
2025-07-29 | CHI11 | 275019-001-0_459_Distributed Antenna System ERRCS PD | 2025-08-05 | Completed |  | HS responded 7/30
2025-07-29 | CHI11 | 275019-001-2_391_Distributed Antenna System | 2025-08-05 | Completed |  | HS responded 7/30
2025-07-29 | LVL07 | LVL07 RFI 96.4 - CDAS Verizon BDA - 23-60861 | 2025-08-01 | Completed |  | BW responded 7/30
2025-07-29 | LVL10 | LVL10 Submittal 2783241-019-R1 - DAS As-Built Drawings - COLO 4 and 5 | 2025-08-06 | Completed |  | HS reponded 7/30
2025-07-29 | LVL10 | LVL10-273241-020-R1 - (ComNet) - DAS Closeout Package - 22-60848 | 2025-08-06 | Completed |  | HS responded 8/1. 7/31: Per K Belle, technically due 8/1 but wasn't forwarded to S2A until 7/29 due to SRI oversight. S2A not on hook for delay
2025-07-29 | LVL11 | LVL11 Submittal 273241-011-R1 - DAS Closeout Package | 2025-08-12 | Completed |  | HS responded 7/29
2025-07-31 | CCO07 | CCO-07: Response to RFI #265 (DRB06 PSDAS) | 2025-08-01 | Completed |  | HS responded 7/29
2025-07-31 | LVL07 | LVL07 RFI 305 - DAS ROU X Camera Clash - 23-60861 | 8/4/2025? | Completed |  | HS responded 8/1.
2025-07-31 | QRO06 | QRO06 ¦ Submittal #1336 DIV 27-243 DTF AND VWSR TEST REPORT - BMcD | 8/7/2025? | Completed | 2025-08-04 | HS responded 8/4
2025-07-31 | YTO11 | MSFT YTO11 Submittal 981 - Bell Mobility DAS Signal Design | 2025-08-07 | Completed |  | HS responded 8/4 - with note bram this will come to you.
2025-08-04 | LYH10 | RFI 767 | 2025-08-06 | Completed |  | HS responded 8/4
2025-08-04 | MNZ03 | RFI 0622.1 - CLSS Fire Alarm Communicator Dual Path - HOT | 2025-08-06 | Completed |  | HS responded 8/4
2025-08-05 | MNZ03 | RFI 0622.2 - Fire Alarm Communicator Dual Path - HOT | 2025-08-07 | Completed | 2025-08-11 | BW responded.
2025-08-06 | QRO02 | ASU - Submittal #1308-27 50 19 | 2025-08-13 | Completed | 2025-08-14 | 8/19: HS responded to the submittal on 8/14/2025. I requested that the contactor revised and resubmit the submittal with ERIP values for the antenna in areas that are underperforming.
2025-08-07 | CCO07 | RFI #244 DRB-06 - AHJ DAS Comment Clarification | ? | Completed | 2025-08-08 | BW confirmed
2025-08-07 | SAT15 | Submittal 273241-013 - Security Radio Over IP - Completed RoIP Commissioning Document - CLTCR | 2025-08-14 | Completed | 2025-08-14
2025-08-07 | SAT15 | Submittal 275019-004 - DAS Communication Systems - Commissioning Plan - TR | 2025-08-14 | Completed | 2025-08-11 | BW responded.
2025-08-07 | YTO11 | YTO11 RFI 1013R1 - DAS Antenna in stairwells | 2025-08-11 | Completed | 2025-08-11 | BW responded.
2025-08-08 | YTO11 | MSFT YTO11 Submittal 981R1 - Bell Mobility DAS Signal Design | 2025-08-15 | Completed | 2025-08-15 | 8/15: BW Responded
2025-08-11 | LVL11 | LVL11-273241-012-R1 Submittal Comm Net DAS as-built drawings | 2025-08-12 | Completed | 2025-08-11 | BW responded noting submittal incomplete.
2025-08-11 | MNZ03 | RFI 0492.1 - Pathway for the DASRoIP GPS antenna and from the roof to the first floor | 2025-08-13 | Completed | 2025-08-14 | 8/14: BW responded.
2025-08-12 | YQB01 | DAS Submittal for review - DA-1572 : Plan antenne telecom | 2025-08-15 | Completed | 2025-08-14
2025-08-12 | YTO11 | RFI 1107 DAS Antenna Ceiling Tile Placement in T-Bar | 2025-08-14 | Completed | 2025-08-13 | Not S2A Scope—BW responded 8/13
2025-08-12 | YTO11 | RFI 1108 DAS Fiber Backbone Cable Type | 2025-08-14 | Completed | 2025-08-13 | Not S2A Scope—BW responded 8/13
2025-08-13 | CPQ3 | RFI 1501 - 008-CPQ03-RFI-T-DAS | 2025-08-19 | Completed | 2025-08-19 | 8/19: TA responded to HS asking for clarification.
2025-08-18 | MNZ03 | 273241-3.0 - RoIP Technician FCC Certifications | 2025-08-20 | Completed | 2025-08-19 | 8/19: HS Responded - Information only
2025-08-18 | MNZ03 | RFI 345 (830) - ROU Location Discrepancy per DRB04 | 2025-08-20 | Completed | 2025-08-19 | 8/19: HS Responded. RFI # in subject line (830) does not match RFI assigned in document (345)
2025-08-19 | MNZ03 | 273241-5.0 - ROIP PD - Microsoft_MNZ03 Data Center Manassas_VA-Project - Submittal | 2025-08-21 | Completed | 2025-08-18 | 8/18: HS Responded
2025-08-19 | MNZ03 | 273241-6.0 - ROIP BOM - Microsoft_MNZ03 Data Center Manassas | 2025-08-21 | Completed | 2025-08-18 | 8/18: HS Responded
2025-08-19 | MNZ03 | RFI 830 - ROU Location Discrepancy per DRB04 | 2025-08-20 | Completed | 2025-08-19 | 8/19: Update and resubmit the correct document
2025-08-19 | YQB06 | RFI 892 - Antenna relocation email (A2 and A19) | 2025-08-19 | Completed | 2025-08-19 | 8/19/2025 - HS reviewed and responded to the email
2025-08-20 | YQB04 | RFI #1597 - Antenna labeling | 2025-08-19 | Completed | 2025-08-20 | 8/20/2025 - HS Responded
2025-08-20 | YQB06 | YQB06-RFI-909 | N/A | Completed | 2025-08-20 | 8/20/2025 - HS -this RFI should have been assinged to the RoIP EOR
2025-08-21 | IAD04 | Submittal #273241-18 ROIP Cx Documentation - COLO 5 | 2025-08-25 | Completed | N/A | 8/22: This is not in S2A's court
2025-08-21 | YTO11 | RFI 1107R1 DAS Antenna Ceiling Tile Placement in T-Bar | 2025-08-25 | Completed | 2025-08-21 | 8/21: HS responded
2025-08-22 | ATL06 | ATL06: New RFI #550 (ERRCS DAS Power Clarification ) | 2025-08-25 | Completed | 2025-08-22 | 8/22: HS responded
2025-08-22 | YQB01 | YQB01 - DAS Submittal for review - DA-1511-R1 : ADX V fiber distributed antenna system | 2025-08-28 | Completed | 2025-08-22 | 8/25: HS, the response will post of 8/25/2025
2025-08-25 | YTO40CA | Submittal #620 Revision 0: DAS Shop Drawing | 2025-08-21 | Completed | 2025-08-26 | 8/26: HS - contractor failed to notifiy S2A of pending submittal until 8/25.
2025-08-25 | YTO40CA | Submittal #623 Revision 0: ROIP Shop Drawings | 2025-08-21 | Completed | 2025-08-26 | 8/26: HS - contractor failed to notifiy S2A of pending submittal until 8/25.
2025-08-26 | IAD12-13 | DAS Questions: iBwave drawings for the PSDAS | ? | N/A |  | 8:26: Email exchange, HS reached out to CL for iBwave drawings for the PSDAS IAD12 & IAD13
2025-08-26 | LVL9-11OneCell? | TMO BYOC 2.0 5G Requirements Upgrade | N/A | NA |  | PO Sent to Andrews
2025-08-26 | PHX81 | Punchlist Walk Admin & COLO 1 Comm/BAS/DAS/EPMS - test data being reviewed. Schedule TBD | ? | Completed | 2025-09-03 | 9/3: BW advised to close. Waiting on test data. 8/26: Email exchange related to scheduling punch walk.
2025-08-26 | SAT80-81 | COR 692& 693 RFI 827.3 VHFPS DAS | ? | N/A |  | 8/26: Ongoing email exchange with AE
2025-08-26 | YTO11 | YTO11 Submittal 981 Bell Mobility DA signal Design | N/A | Completed | 2025-08-26 | HS - we reviewed past submittals and determined that nothing was outstanding
2025-08-27 | LVL09 | A/E requests confirmation all RFI's included in record docs. | 2025-08-28 | Completed | 2025-08-28 | 8/27: Email exchange with Swanson Rink (Mira Lammers)
2025-08-27 | QRO02 | RFI #899 TCOM - CW TEST PARAMETERS | 2025-08-29 | Completed | 2025-08-28 | HS responded
2025-08-28 | EAT12 | Drawings Published (7) for EAT12 Data Center (6524006) | ? | Completed |  | 8/28: HS confirmed nothing for S2A - no billing to client.
2025-08-28 | LYH10 | LYH10 - 000809 - Cell DAS Scope of Work Delineation | 2025-08-29 | Completed | 2025-08-28 | 8/28: BW responded.
2025-08-31 | EAT12 | ISSUE #633 - Typo Clarifiction | ? | Completed | 2025-08-31 | HS - nothing for S2A
2025-08-31 | YQB01 | YQB01 - DA-1617_Antenna AD-PA-195-4200-D - SR | 2025-09-10 | Completed | 2025-09-02 | HS - Reviewed and stamped
2025-08-31 | YQB01 | YQB01-DA-1615_Antenna AD-PA-617-960-D - SR | 2025-09-10 | Completed | 2025-09-02 | HS - Reviewed and stamped
2025-09-02 | CCO06 | Microsoft CCO06 Phase I: Response to RFI #551 (IFC DAS & DRB13 DAS) | 2025-09-03 | Complete |  | Harold Responded
2025-09-02 | CPQ03 | RFI #1501 | 2025-09-04 | Completed | 2025-08-19 | HS - Closed- previously replied to - 8/19/2025
2025-09-02 | CPQ03 | Submittal 775 - 008-CPQ03-SUB-T-DAS | 2025-09-08 | Completed | 2025-09-07 | HS - reviewed and returned
2025-09-02 | CPQ03 | Submittal 830 #009 – Substitution Request | 2025-09-04 | Completed | 2025-09-07 | HS - reviewed and returned
2025-09-02 | IAD12-13 | 275019-2.0_Distributed Antenna System - PD and SD - Microsoft Loudoun County. | 2025-09-08 | Complete |  | BW responded 9/4, advised to send ROiP to the appropriate party. S2A DAS/ERRCS only.
2025-09-02 | IAD12-13 | RFI 0873 PS DAS & ROIP Power Receptacles Needed | 2025-09-04 | Complete |  | BW responded 9/2, forwarded to Electrical
2025-09-02 | IAD12-13 | RFI0874_IAD12-13 Coax Cable and Support Clarification | 2025-09-04 | Complete |  | BW Responded 9/2
2025-09-03 | ATL06 | MSFT ATL06: Response to RFI #550 (ERRCS DAS Power Clarification ) | 2025-08-27 | Closed |  | Harold Responded, not in S2A Scope
2025-09-03 | PHX61 | PHX61 DAS Closeout | NA | NA |  | HS - keep this on the list until we see a response, there is no due date
2025-09-03 | YQB01 | YQB01-DA-1615 Antenna AD | 2025-09-03 | Completed | 2025-09-05 | HS - returned
2025-09-04 | CHI11 | 270820-001-0_496_CHI10 to CHI11 DAS Fiber Test Results | 2025-09-11 | Completed | 2025-09-08 | HS - Fiber test results, reviwed for content
2025-09-04 | CHI11 | 270820-001-0_497_CHI10-CHI11 ROIP Fiber Test Results | 2025-09-11 | Completed | 2025-09-08 | HS - Fiber test results, reviwed for content
2025-09-04 | IAD12-13 | 275019-2.0_Distributed Antenna System - PD and SD - Microsoft Loudoun County. | 2025-09-08 | Completed | 2025-09-07 | HS-reponded and advised submittal needs to be reviewed by EOR
2025-09-07 | CHI11 | CHI11 Busse - Design - Submittal Forwarded: 270820-001-0_496_CHI10 to CHI11 DAS Fiber | 2025-09-11 | Completed | 2025-09-07 | HS - Review and returned
2025-09-07 | CHI11 | CHI11 Busse - Design - Submittal Forwarded: 270820-001-0_497_CHI10-CHI11 ROIP Fiber | 2025-09-11 | Completed | 2025-09-07 | HS - Review and returned
2025-09-07 | CPQ11 | CPQ11 - #1049-SUB-T-W-DAS-202509041403 Bendhmarc Survey | 2025-09-09 | Completed | 2025-09-07 | HS - Review and returned
2025-09-07 | IAD12-13 | IAD12/13 Submittal 275019-2.0_Distributed Antenna System - PD and SD | 2025-09-11 | Completed | 2025-09-07 | HS - This was not for S2A - we reviewed for potential content
2025-09-08 | SAT14CA | RFI 1677 - P2 - TeamLinx - DAS Remote Unit Fiber Counts | 2025-09-10 | Completed | 2025-09-09 | BW responded
2025-09-08 | SAT14CA | RFI 1677 - P2 - TeamLinx - DAS Remote Unit Fiber Counts | 2025-09-10 | Complete | 2025-09-12 | Bram - answered this. A/E requesting additional revisions/clarifications.
2025-09-09 | EAT12 | DRB-022 Drawings Published. | NA | NA |  | Unclear if any action for S2A or not.
2025-09-09 | QRO02 | ASU Item 27 50 19 / #1308 (Rev 2) DIV 27-256 DAS SIGNAL STRENGTH | 2025-09-15 | Completed | 2025-09-12 | HS responded
2025-09-10 | IAD12-13 | RFI 0874_IAD 12-13 - Coax Cable and Antenna Support Clarification | 2025-09-05 | Completed | 2025-09-10 | HS - Reponded
2025-09-10 | MNZ03 | RFI 0492.1 - Pathway for the DASRoIP GPS antenna and from the roof to the first floor | 2025-09-12 | Complete | 2025-09-12 | S2A rereviewed this submittal
2025-09-10 | QRO02 | QRO02 - #1308 Signal Strength Submittal | 2025-09-15 | Complete | 2025-09-12 | We have reviewed this submittal multiple times, there are areas of coverage were the signal strength remains a concern - reference page 65 & 49
2025-09-10 | SAT15CA | P2 - RFI 0950 - Corbins - DAS Unit Power Requirement Clarification | 2025-09-12 | Completed | 2025-09-12 | HS - this was not for S2A, we reviewed and sent back to the A/E
2025-09-11 | LVL07CA | LVL07 Submittal 454 - Admin & COLO 1 CDAS COAX Te - 23-60861 | 2026-09-18 | Complete | 2025-09-14 | HS - Answered - Approved
2025-09-11 | LVL07CA | LVL07 Submittal 455 - Admin COLO1 PSDAS COAX Test - 23-60861 | 2026-09-18 | Complete | 2025-09-14 | HS - Answered - Approved
2025-09-11 | LVL07CA | LVL07 Submittal 456 - Admin COLO1 PSDAS CW Test R - 23-60861 | 2026-09-18 | Complete | 2025-09-14 | HS - Answered. Revise and resubmit, we need to see injection values, distance from antenna measurements were taken, and performance assumptions
2025-09-11 | LVL12CA | LVL12 Submittal 27 50 19-1.0 - ComNet, DAS For Co - 23-60867 | 2025-09-16 | Complete | 2025-09-14 | HS - Answered. Note: Submittal doc shows an intiated date of 9/9 but S2A did not receive notification until 9/11.
2025-09-11 | LVL12CA | LVL12 Submittal 27 50 19-2.0 - ComNet, DAS For Co - 23-60867 | 2025-09-16 | Complete | 2025-09-15 | HS - Answered
2025-09-11 | MNZ03 | 275019-2.0 - PS DAS SD | 2025-09-18 | Complete | 2025-09-15 | HS - Answered, I recommend that they move to a ADRF based PSDAS
2025-09-11 | QRO02 | QRO02 - Issue #8486 Observations/Comments: (DAS ROU –Water Treatment Facility) | 2025-08-25 | Complete | 2025-09-15 | HS - Reviewed and submitted
2025-09-11 | SAT14CA | RFI 1710 - P2 - Teamlinx - ROIP Connection for ADMIN1 to ADMIN2 | 2025-09-15 | Completed | 2025-09-12 | HS - Answered
2025-09-12 | MNZ03 | 273241-2.0 - RoIP Commissioning Submittal | 2025-09-16 | Complete | 2025-09-15 | HS - answered, revise and resubmit, we need to know who is doing the commissioning
2025-09-12 | MNZ03 | 273241-7.0 - RoIP SD | 2025-09-16 | Complete | 2025-09-15 | HS - Complete
2025-09-12 | MNZ03 | 275019-13.0 - CDAS BOM | 2025-09-16 | Complete | 2025-09-15 | HS - Complete - we need the contractor to back out the ISP related scope or have MSFT agree that the contractor is to install it.
2025-09-12 | MNZ03 | MNZ03 - 275019-1.0 - CDAS SD submittal | 2025-09-18 | Complete | 2025-09-15 | 275019-13.0 - CDAS BOM
2025-09-12 | MNZ03 | MNZ03 - MCD RFI#381 - T-Mobile | 2025-09-16 | Complete | 2025-09-12
2025-09-12 | MNZ03 | MNZ03 - RoIP shop drawings #275019-005 | 2025-09-18 | Complete | 2025-09-15
2025-09-12 | MNZ03 | RFI 0881 - CDAS T-Mobile Support | 2025-09-16 | Complete | 2025-09-12 | HS - answered - note that AE identified this RFI with two different #s 381 and #881
2025-09-15 | CHI05 | CHI05 - Punchlist Document | N/A | Complete | 2025-09-17 | HS - we reviewed the CHI05 Punch list document for comments that might impact DAS installations
2025-09-15 | IAD05 | RFI#041 - IAD05 Room number and antenna clarification | 2025-09-15 | N/A | 2025-09-16 | HS - I reviewed the RFI, this is not for S2A
2025-09-15 | MNZ03 | RFI 0689.2 - ROIP Confirmations - Guardhouse ROIP Antenna, Portable ROIP Radio | 2025-09-17 | Complete | 2025-09-15 | BW completed
2025-09-16 | EAT12 | RFI-0645 - EAT12-M-K-00-4 - BAS DETAILS AND POINTS - LIFT STATION Rev. 03 | N/A | N/A | N/A | HS - reviewed. This is not for S2A
2025-09-16 | YTO11 | MSFT YTO11 RFI 1156 | 2025-09-18 | Complete | 2025-09-16 | HS - answered
2025-09-17 | PHX13 | PHX13 CA-D3127062-Sub# 275019-006-00-Commercial DAS O&M's-FOR REVIEW | 2025-09-23 | Complete | 2025-09-18 | BW responded.
2025-09-17 | PHX13 | PHX13 CA-D3127062-Sub# 275019-007-00-Public Safety DAS As-Builts-FOR REVIEW | 2025-09-23 | Complete | 2025-09-22 | BW responded.
2025-09-17 | YQB04 | YQB04 - RFI#1660 Antenna positioning in the electrical rooms | 2025-09-19 | Complete | 2025-09-18 | HS - reviewed and respoded
2025-09-19 | CHI11 | CHI11 - RoIP SD Submittal #511-273241 | 2025-09-26 | Complete | 2025-09-19 | HS - reviewed and responded to.
2025-09-22 | IAD04 | Submittal 017700-21.0 - WT Contract Drawings As-Built DAS | 2025-09-26 | Complete | 2025-09-22 | BW responded.
2025-09-22 | IAD04 | Submittal 017700-22.0 - WT Contract Drawing As-Builts Public Safety | 2025-09-26 | Complete | 2025-09-24 | BW responded.
2025-09-22 | LVL10 | Submittal 273241-020-R2 - (ComNet) - DAS Closeout Pac - 22-60848 | 2025-09-26 | Complete | 2025-09-24 | BW responded.
2025-09-22 | MNZ03 | RFI #570.3 (Antenna Masts - Top of Mast Elevation) | 2025-09-25 | Complete | 2025-09-22 | BW responded.
2025-09-23 | CHI11 | CHI11 Busse - Design - RFI Forwarded: CHI11 RFI 0543_RoiP Radio Programming | 2025-09-25 | Complete | 2025-09-23 | HS - reviewed and responded to
2025-09-23 | CHI11 | CHI11 Busse - Design - RFI Forwarded: CHI11 RFI 0544_FBDA Programming Confirmation | 2025-09-25 | Complete | 2025-09-23 | HS - reviewed and responded to
2025-09-23 | LVL07 | Submittal 459 - DAS as Built Drawings - 23-60861 | 2025-09-24 | Complete | 2025-09-24 | BW responded.
2025-09-23 | LVL11 | LVL11-273241-012-R2 - (ComNet) - DAS As-Built Dra - 22-60853 | 2025-10-07 | Complete | 2025-09-23 | HS - reviewed and responded to
2025-09-24 | AVC17/18 | AVC17/18: New RFI #490 (RoIP Combiner Temp Solution ) | 2025-09-26 | N/A | 2025-09-24 | HS - I reviewed this RFI, this needs to be sent to Day Wireless
2025-09-24 | AVC17/18 | AVC17/18: The Due Date of RFI #487 (CDAS Interface) | 2025-09-26 | Complete | 2025-09-25 | HS - reviewed and responded to
2025-09-24 | AVC17/18 | DRB-09 - COLO 3 & 4 Fit-out (Packages 2 & 3) - Issued for Construction | 2025-09-24 | Complete | 2025-09-24 | HS - added comments to RFIs that impcated the project
2025-09-24 | LVL11 | Submittal 273241-012-R2 - (ComNet) - DAS As-Built Dra - 22-60853 | 2025-09-25 | Complete | 2025-09-26 | 9/26: BW session is closed and BW cannot access it. Not for S2A
2025-09-25 | IAD04 | IAD04 Loudoun County VA - Submittal Forwarded: 275019-13.0 - DAS Cx Documentation | 2025-10-01 | Completed | 2025-09-25 | BW responded 9/25
2025-09-25 | IAD04 | IAD04 Loudoun County VA - Submittal Forwarded: 275019-14.0 - DAS Cx Documentatio | 2025-10-01 | Completed | 2025-09-25 | BW responded 9/25
2025-09-25 | YTO11 | YTO11 - DRB-09 - COLO 3 & 4DAS/ROIP disciplines input on the lessons learned | 2025-09-24 | Completed | 2025-09-24 | HS responded
2025-09-29 | CC008 | GC Bidder Questions | 2025-09-29 | Completed | 2025-09-29 | 9/29: HS nothing for S2A to address
2025-09-29 | LVL07 | Submittal 479 - PSDAS Backbone to LVL06 (OT - 23-60861 | 2025-10-06 | Completed | 2025-09-29 | BW responded
2025-09-29 | LYH10 | RFI 841 DAS Head End Power Requirements Follow Up | 2025-10-01 | Completed | 2025-09-29 | Not for S2A
2025-09-29 | MNZ03 | 273241-2.1 - RoIP Commissioning Submittal | 2025-10-03 | Complete | 2025-10-02 | HS - Reviewed and responded to
2025-09-29 | MNZ03 | RFI 0923 - DASROIP Antenna - Removal of BackBoxesWall Penetrations at Stair 3 | 2025-10-01 | Completed | 2025-09-29 | BW responded.
2025-09-29 | MNZ03 | Submittal 275019-13.1 - CDAS BOM | 2025-10-03 | Completed | 2025-09-30 | BW Responded.
2025-09-29 | YTO40 | Submittal #688.0 - Linkwave Cellular Design Package | 2025-10-03 | Completed | 2025-10-01 | HS - reviewed and responded to.
2025-09-29 | YTO40 | Submittal #689.0 - RoIP Design Package | 2025-10-03 | Completed | 2025-09-30 | HS responded
2025-09-30 | IAD05 | IAD05: New RFI #585 (Confirmation on Use of 4' x 8' Plywood for ROU Panels ) | 2025-10-02 | Completed | 2025-10-01 | HS - reviewed and responded to.
2025-09-30 | LVL12 | Submittal 27 50 19-3.0 - ComNet, DAS Testin - 23-60867 | 2025-10-08 | Complete | 1900-01-09 | BW reviewed and responded
2025-10-01 | LVL07 | Submittal 482 - MCD Telecom DAS O&M Manual - 23-60861 | 2025-10-07 | Complete | 2025-10-07 | BW reviewed and responded
2025-10-02 | QRO02 | Issue #8071 | 2025-10-04 | Complete | 2025-10-02 | HS - Reviewed and responded to
2025-10-02 | YQB01 | DAS Submittal for review - Oct 2 - DA-1647 | 2025-10-03 | Completed | 2025-10-03 | BW reviewed and responded.
2025-10-03 | MNZ03 | 275019-13. 2 - CDAS BOM - Microsoft_MNZ03 Data Center Manassas VA-Project - Submittal:275019-13-2:UEbBu | 2025-10-09 | Completed | 2025-10-03 | BW responded
2025-10-06 | SAT15 | 017700-024 - DAS-ROIP As-Builts - Phase 1 - CLAB | 2025-10-08 | Completed | 2025-10-07 | HS - Reviewed and responded to
2025-10-07 | AVC17/18 | RFI #499 (PSDAS Design Changes) | 2025-10-10 | Completed | 2025-10-08 | HS reviewed and responded to
2025-10-07 | IAD04 | WT Contract Drawings As-Built "DAS" REV1 | 2025-10-13 | Complete | 2025-10-10 | BW reviewed and responded 10/10
2025-10-07 | IAD04 | WT Contract Drawings As-Built "DAS" REV1 | 2025-10-13 | Completed | 2025-10-10 | BW Reponded 10/20. This was a mistake on the A.E. side, they uploaded the wrong version. KC: 10/20: Bram has this been updated so it can be closed out? BW reviewed and responded 10/10
2025-10-07 | LVL07 | Submittal 456.1 - Admin COLO1 PSDAS CW | 2025-10-14 | Completed | 2025-10-13 | BW reviewed and responded to
2025-10-07 | LVL07 | Submittal 494 - Admin COLO1 PSDAS AHJ Appro - 23-60861 | 2025-10-14 | Completed | 2025-10-13 | BW reviewed and responded to
2025-10-07 | LVL10 | 270519-005-R1 - (ComNet) - PSDAS As Built A - 22-60848 | 2025-10-21 | Complete | 2025-10-10 | HS reviewed and responded 10/10
2025-10-07 | LVL10 | 273241-020-R3 - (ComNet) - DAS Closeout Pac - 22-60848 | 2025-10-17 | Completed | 2025-10-13 | HS - reviewed and responded to
2025-10-08 | IAD05 | RFI 0259.1 - WP-1 Relocation in COLO 1 CE3 | 2025-10-14 | Completed | 2025-10-08 | HS reviewed and responded to
2025-10-08 | YTO40 | Submittal #623.1: ROIP Shop Drawings | 2025-10-15 | Completed | 2025-10-08 | HS reviewed and responded to
2025-10-09 | LVL07 | Submittal 513 - Admin & COLO 1 CDAS Antenna - 23-60861 | 2025-10-16 | Completed | 2025-10-13 | BW reviewed and responded to
2025-10-09 | LVL07 | Submittal 514 - Admin & COLO 1 PSDAS Grid a - 23-60861 | 2025-10-16 | Completed | 2025-10-13 | BW reviewed and responded to
2025-10-09 | LVL07 | Submittal 515 - Admin & COLO 1 CDAS Post-In - 23-60861 | 2025-10-16 | Completed | 2025-10-13 | BW reviewed and responded to
2025-10-09 | LVL12 | Submittal 512 - Admin & COLO 1 CDAS Commiss - 23-60861 | 2025-10-16 | Completed | 2025-10-13 | BW reviewed and responded to
2025-10-10 | LVL07 | Submittal 479.1 - PSDAS Backbone to LVL06 ( - 23-60861 | 2025-10-15 | Complete | 2025-10-10 | HS reviewed and responded 10/10
2025-10-13 | MNZ03 | RFI 0949 - SOC ROIP Base Sation Final Placement | 2025-10-15 | Completed | 2025-10-23 | REOPENED: Clark is asking that you coordinate with the Microsoft Ops Team and complete your response. They have reopened for updated response. (10/15) Tom Stewart: This RFI will be tracked and reported in the weekly ITIM meeting.
2025-10-13 | SAT14 | RFI 1769 E-House Coverage | 2025-10-13 | Completed | 2025-10-13 | HS - reviewed and responded to
2025-10-14 | QRO02 | Issue #8463 Observations/Comments: (RoIP ROU –Water Treatment Facility) | 2025-08-25 | Completed | 2025-10-14 | HS: the issue is still open on the contractors side
2025-10-14 | SAT40 | SUM-01251 - 27 50 19 - R0 - COMMUNICATION SYSTEMS DISTRIBUTED ANTENNA SYSTEM (DAS) - Training | 2025-10-16 | Closed | 2025-10-16 | BW Reviewed and responded to
2025-10-15 | YTO11 | RFI 1204: ROIP Channel Talk Group - RFI#1156 Follow Up | 2025-10-17 | Completed | 2025-10-17 | HS reviewed and responded to
2025-10-16 | LYH10 | Ph 01, Pkg 467-27 50 19-REV 0 LYH10 Public Safety DAS Closeout Documentation Admin-COLO2 - Submittal Packages | 2025-10-21 | Completed | 2025-10-20 | BW reviewed and responded to 10/20
2025-10-16 | LYH10 | Ph 01, Pkg 468-275019-REV 0 LYH10 Cellular DAS Closeout Documentation Admin-COLO1 - Submittal Packages | 2025-10-21 | Completed | 2025-10-21 | BW reviewed and responded 10/21.
2025-10-17 | MNZ03 | 275019-13.2 CDAS BOM | 2025-10-17 | Completed | 2025-10-21 | BW reviewed and responded to 10/20
2025-10-20 | PHX14 | D3127072-Sub# 273241-002-00-ROIP System As-Builts | 2025-10-23 | Completed | 2025-10-23 | HS reviewed and responded 10/23
2025-10-20 | PHX14 | D3127072-Sub# 275019-003-00-Public Safety DAS As-Builts | 2025-10-23 | Completed | 2025-10-23 | BW reviewed and responded 10/23
2025-10-20 | PHX14 | D3127072-Sub# 275019-004-00-Commercial DAS System As-Builts | 2025-10-23 | Completed | 2025-10-23 | BW reviewed and responded 10/23
2025-10-21 | AVC17/18 | RFI 512 CDAS Signal Source | 2025-10-22 | Completed | 2025-10-21 | BW reviewed and responded 10/21.
2025-10-21 | YTO11 | RFI 1215 in BlueBeam | 2025-10-23 | Completed | 2025-10-22 | HS reviewed and responded 10/22
2025-10-23 | SAT81 | RFI PH2-0827-R4 -SAT 81 PKG 4 & 13 - TELE - SAT 81 Colo 2-5 Fitout DAS-ROIP | 2025-10-27 | Closed | 2025-10-24 | Not in S2A scope
2025-10-23 | YQB06 | O&M Manuals - Submittals_Telecom_dépot initial | 2025-10-31 | Completed | 2025-10-29 | HS reviewed and responded to
2025-10-24 | LVL10 | 273241-020-R4 - (ComNet) - DAS Closeout Pac - 22-60848 | 2025-11-07 | Completed | 2025-10-29
2025-10-24 | SAT14 | RFI 1798 - P2 - TeamLinx - Dedicated Signal Sources.pdf | 2025-10-27 | Completed | 2025-10-27 | HS reviewed and responded to
2025-10-27 | CCO06 | RFI #733 - FOC & SOC RoIP Power Requirements | 2025-10-30 | Completed | 2025-10-27 | HS reviewed and responded to: not for SCA
2025-10-27 | LVL07 | RFI 337 - CDAS WSPs and Frequency bands - 23-60861 | 2025-10-30 | Completed | 2025-10-27 | HS reviewed and responded to
2025-10-27 | MNZ03 | RFI 0949 - SOC ROIP Base Sation Final Placement | 2025-10-27 | Closed | 2025-10-27 | HS reviewed and responded to
2025-10-27 | PHX82 | RFI #387 FCR DAS equipment location | 2025-10-28 | Closed | 2025-10-28 | HS reviewed and responded to
2025-10-27 | SAT15 | RFI 0979 - Teamlinx - Updated Signal Source - DAS System.pdf | 2025-10-29 | Completed | 2025-10-27 | HS reviewed and responded to
2025-10-28 | AVC17/18 | RFI #525 (MC Dean - Discontinued PSDAS Components) | 2025-11-03 | Completed | 2025-10-28 | HS reviewed and responded to
2025-10-28 | YTO40CA | Submittal #689.1 - RoIP Design Package | 2025-11-04 | Completed | 2025-10-30 | Forwarded from telecom
2025-10-30 | SAT40DS | RFI-01033 - Request to shift position of admin Antenna | 2025-11-03 | Completed | 2025-10-30 | HS reviewed and responded to.
2025-11-03 | IAD12-13 | 275019 2.1 - Distributed Antenna System - PD and SD | 2025-11-03 | Completed | 2025-11-03 | HS reviewed and responded to
2025-11-03 | MNZ03 | 273241-8.0 - ROIP Tech Certifications | 2025-11-07 | Completed | 2025-11-03 | HS reviewed and responded to
2025-11-03 | QRO02 | #1308 (Rev 3) DIV 27-256 DAS SIGNAL STRENGTH | 2025-11-07 | Completed | 2025-11-03 | HS reviewed and responded to
2025-11-04 | SAT40 | Submittal 275019-209 - SAT 81 VHF PS DAS System | 2025-11-10 | Completed | 2025-11-09 | HS reviewed and responded to
2025-11-04 | SAT80 | Submittal 275019-208 - SAT 80 VHF PS DAS System | 2025-11-10 | Completed | 2025-11-09 | HS reviewed and responded to
2025-11-04 | SAT80-81 | SAT81 COLO 2-5 Fit out Pkg 4, 11-13 Technical Exceptions | ? | Completed | 2025-11-10 | see attached RFI 827.3 response and confirm the team’s response is “ERRCS (both 800MHz and VHF) frequencies to be included in this scope.”
2025-11-05 | CCO06 | Phase I: Response to RFI #743 (PS DAS Protective Barrier) | 2025-11-07 | Completed | 2025-11-05 | HS reviewed and responded to
2025-11-05 | IAD04 | PSDAS Cx Documentation - COLO 4 | 2025-11-10 | Completed | 2025-11-10 | HS reviewed and responded to
2025-11-05 | IAD04 | PSDAS Cx Documentation - COLO 5 | 2025-11-10 | Completed | 2025-11-10 | HS reviewed and responded to
2025-11-05 | YQB06 | Submittal #27 50 19-006 Revision 0: Grounding Kit | 2025-11-14 | Completed |  | This is a substitution submittal. If approved, please provide your stamp on the cover page and signature on substitution form (2nd page).
2025-11-06 | AVC17/18 | RFI #533 (Guardhouse RoIP & Security Enclosure Clash ) | 2025-11-11 | Completed | 2025-11-08 | Not in S2A scope
2025-11-11 | AVC17/28 | Submittal (#570.0: MC Dean - AVC17 RoIP - Shop Drawings) | 2025-11-15 | Completed | 2025-11-11 | Not in S2A scops
2025-11-11 | CCO06 | RFI #746 (Public Safety DAS Backboard) | 2025-11-13 | Completed | 2025-11-11 | Not in S2A scope
2025-11-11 | YQB06 | RFI 1034 | 2025-11-02 | Closed | 2025-11-21 | Mohammed Taleb confirmed closed
2025-11-13 | CCO07 | PS DAS Protective Barrier Clarification | 2025-11-15 | Completed | 2025-11-13 | HS reviewed and responded to
2025-11-13 | IAD04 | Submittal Distributed: (#27 50 19-10.0: PSDAS Cx Documentation - COLO 4) | 2025-11-20 | Completed | 2025-11-10 | HS reviewed and responded to
2025-11-13 | IAD04 | Submittal Distributed: (#27 50 19-12.0: PSDAS Cx Documentation - COLO 5) | 2025-11-20 | Completed | 2025-11-10 | HS reviewed and responded to
2025-11-17 | IAD04 | 275019-7.1 - DAS Cx Documentation - COLO 3 | 2025-11-04 | Completed | 2025-11-17
2025-11-18 | CCO06 | RFI #743 (PS DAS Protective Barrier) | 2025-11-20 | Completed | 2025-11-18 | Not in S2A scope
2025-11-19 | AVC17/18 | Submittal (#577.0: MC Dean - AVC17 CDAS BOM) | 2025-11-26 | Completed | 2025-11-24 | HS reviewed and responded to
2025-11-19 | AVC17/18 | Submittal (#578.0: MC Dean - AVC17 PSDAS BOM) | 2025-11-26 | Completed | 2025-11-24 | HS reviewed and responded to
2025-11-19 | AVC17/18 | Submittal (#579.0: MC Dean - AVC17 CDAS - Shop Drawings) | 2025-11-26 | Completed | 2025-11-24 | HS reviewed and responded to
2025-11-19 | AVC17/18 | Submittal (#580.0: MC Dean - AVC17 PSDAS - Shop Drawings) | 2025-11-26 | Completed | 2025-11-24 | HS reviewed and responded to
2025-11-19 | AVC17/18 | Submittal (#581.0: MC Dean - AVC17 Tranche 1 PSDAS - O&Ms) | 2025-11-26 | Completed | 2025-11-24 | HS reviewed and responded to
2025-11-19 | AVC17/18 | Submittal (#582.0: MC Dean - AVC17 CDAS - O&Ms) | 2025-11-26 | Completed | 2025-11-25 | HS reviewed and responded to
2025-11-19 | LVL07 | Submittal 581 COLO2-3 DAS Backbone | 2025-11-26 | Completed | 2025-11-20 | BW reviewed and responded to
2025-11-21 | YTO11 |  | 2025-11-26 | Completed | 2025-11-24 | HS reviewed and responded to
2025-11-24 | FTY02 | 27 50 19 - Distributated Antenna System | 2025-11-27 | Completed | 2025-11-25 | BW reviewed and responded to
2025-11-24 | YQB01 | RFI 1136 Mast for one outdoor wall-mounted ROIP antennas | 2025-11-26 | Completed | 2025-11-24 | HS reviewed and responded to
2025-11-25 | CLT10 | GC RFI item #32 | 2025-11-25 | Completed | 2025-11-25 | HS reviewed and responded to
2025-11-25 | IAD05 | RFI 0651 - ROU Panel FiberCoax Pathway | 2025-11-28 | Completed | 2025-11-25 | HS reviewed and responded to
2025-11-26 | CCO06 | RFI #769 (PS DAS monitoring Modem) | 2025-12-01 | Completed | 2025-11-26 | For owner, not S2A
2025-11-26 | IAD04 | Submittal (#27 50 19-9.0: PSDAS Cx Documentation - COLO 3) | 2025-11-25 | Completed | 2025-12-01 | HS asks that the contractor needs to provide or directs us accordingly to additional information
2025-11-26 | LVL07 | Submittal 585 - PSDAS COLO 2 & COLO 3 Grid - 23-60861 | 2025-12-03 | Completed | 2025-12-02 | BW reviewed and responded to
2025-11-26 | LVL07 | Submittal 586 - CDAS COLO 2 & COLO 3 Antenn - 23-60861 | 2025-12-03 | Completed | 2025-12-02 | BW reviewed and responded to
2025-11-26 | LVL07 | Submittal 587 - COLO 2 & COLO 3 CDAS Post-I - 23-60861 | 2025-12-03 | Completed | 2025-12-02 | BW reviewed and responded to
2025-11-26 | LVL07 | Submittal 588 - COLO 2 & COLO 3 PSDAS Anten - 23-60861 | 2025-12-03 | Completed | 2025-12-02 | BW reviewed and responded to
2025-11-26 | MNZ03 | Submittal 273241-8.1 - ROIP Tech Certifications | 2025-12-01 | Completed | 2025-11-26 | HS reviewed and responded to
2025-12-01 | IAD05 | RFI 0391.1 - Further Clarification on DASPS-DAS Design | 2025-12-03 | Completed | 2025-12-02 | HS reviewed and responded to
2025-12-01 | MNZ03 | 273241-8.1 - ROIP Tech Certifications | 2025-12-01 | Completed | 2025-11-26 | HS reviewed and responded to
2025-12-01 | MNZ03 | 275019-1.1 - CDAS Shop Drawings | 2025-12-03 | Completed | 2025-12-02 | BW reviewed and responded to
2025-12-02 | LYH10 | Signal Source DAS Switch Configuration/Programming | 2025-12-03 | Completed | 2025-12-02 | HS reviewed and responded to
2025-12-02 | MNZ03 | 275019-14.0 - CDAS - Post Wall RF Benchmark Study Report | 2025-12-04 | Completed | 2025-12-02 | HS reviewed and responded to
2025-12-02 | MNZ03 | 275019-15.0 - PSDAS — Post Wall RF Benchmark Study Report | 2025-12-05 | Completed | 2025-12-02 | HS reviewed and responded to
2025-12-02 | SAT40 | 27 50 19 - R0 - COMMUNICATION SYSTEMS DISTRIBUTED ANTENNA SYSTEM (DAS) - Warranty (Admin and COLO-1) - Review | 2025-12-04 | Completed | 2025-12-03 | BW reviewed and responded to
2025-12-02 | SAT40 | 27 50 19 - R0 - COMMUNICATION SYSTEMS DISTRIBUTED ANTENNA SYSTEM (DAS) - Warranty (COLO-2) | 2025-12-04 | Completed | 2025-12-03 | BW reviewed and responded to
2025-12-02 | SAT40 | 27 50 19 - R0 - COMMUNICATION SYSTEMS DISTRIBUTED ANTENNA SYSTEM (DAS) - Warranty (COLO-3) - Review | 2025-12-04 | Completed | 2025-12-03 | BW reviewed and responded to
2025-12-02 | SAT40 | RFI-01057-Rev 1 - Clarification on Antenna Height Above Roof | 2025-12-04 | Completed | 2025-12-02 | (REOPENED) HS reviewed and responded to
2025-12-02 | SAT80-81 | Submittal 275019-208-01 - SAT 80 VHF PS DAS System | 2025-12-09 | Completed | 2025-12-08 | HS reviewed and responded to.
2025-12-02 | SAT80-81 | Submittal 275019-209-01 - SAT 81 VHF PS DAS System | 2025-12-09 | Completed | 2025-12-08 | HS reviewed and responded to.
2025-12-02 | YTO11 | RFI 1307 ROIP Power requirements | 2025-12-02 | Completed | 2025-12-02 | HS reviewed and responded to
2025-12-02 | YTO40 | RFI-592 - SER ROIP Power Requirements | 2025-12-03 | Completed | 2025-12-02 | HS reviewed and responded to, 12/3: EMAIL QUESTION FROM KEVIN PATEL: if GC needs extra receptacle for 2nd ATS then they can use the same source as 1st ATS, not 4 different source are required for 4 different receptacle correct?
2025-12-03 | EAT03 | EAT03 - Record Documents Instructions | ? | Completed | 2025-12-08 | BW submitted
2025-12-03 | YQB06 | RFI 1034 | ? | Completed |  | BW reviewed and responded to
2025-12-09 | LVL07 | LVL07 Submittal 592 - COLO 2 & COLO 3 CDAS Commis | 2025-12-15 | Completed | 2025-12-11 | BW reviewed and responded to.
2025-12-09 | LVL07 | LVL07 Submittal 593 - COLO 2 & COLO 3 PSDAS COAX - | 2025-12-15 | Completed | 2025-12-11 | BW reviewed and responded to.
2025-12-09 | LVL07 | LVL07 Submittal 594 | 2025-12-15 | Completed | 2025-12-11 | BW reviewed and responded to.
2025-12-11 | SAT40 | RFI-01070 - VZW Signal Source DAS System Clarification | 2025-12-12 | Completed | 2025-12-11 | HS reviewed and responded to.
2025-12-12 | YTO11 | RFI 1321 ROIP Cabinet | 2025-12-16 | Completed | 2025-12-12 | HS reviewed and responded to.
2025-12-12 | YTO11 | RFI 1322 Base Station Ceiling Antenna | 2025-12-16 | Completed | 2025-12-12 | HS reviewed and responded to.
2025-12-12 | YTO40 | Submittal #783.1- DAS / ROIP Rooftop Antenna Mast Non-Penetrating | 2025-12-12 | Completed | 2025-12-12 | HS reviewed and responded to.
2025-12-15 | LVL07 | Submittal 605 - COLO 2 & COLO 3 PSDAS AHJ A - 23-60861 | 2025-12-22 | Completed | 2025-12-21 | HS reviewed and responded to
2025-12-15 | SAT80-81 | 275019-208-02 - SAT 80 VHF PS DAS System | 2025-12-22 | Completed | 2025-12-21 | HS reviewed and responded to
2025-12-15 | SAT80-81 | Submittal 275019-209-02 - SAT 81 VHF PS DAS System | 2025-12-22 | Completed | 2025-12-22 | HS reviewed and responded to
2025-12-17 | CLT10 | GC TE's for Review | 2025-12-19 | Completed | 2025-12-17 | HS reviewed and responded to
2025-12-17 | CPQ3 | RFI 1623 - 008-CPQ03-RFI-T-DAS | 2025-12-17 | Completed | 2025-12-17 | HS reviewed and responded to
2025-12-18 | LVL07 | Submittal 608 - Tranche 2 & 3 PSDAS and CDA - 23-60861 | 2025-12-25 | Completed | 2025-12-21 | HS reviewed and responded to
2025-12-18 | YQB01 | DA-1041-R2 - 041 support antenne télécom | 2025-01-06 | Completed | 2025-12-21 | HS reviewed and responded to
2025-12-19 | FYT02 | Submittal # 27 05 19-7.0 | 2025-12-22 | Completed | 2025-12-22 | HS reviewed and responded to
2025-12-22 | YQB01 | DFC-0026 Operation & Maintenance Manual for Commercial DAS - Telecon | 2025-12-22 | Completed | 2025-12-30 | HS reviewed and responded to
2025-12-22 | YQB06 | 01 78 23-007 O&M Manuals - Submittals_Telecom_dépot initial | 2025-12-23 | Completed | 2025-12-30 | HS reviewed and responded to
2025-12-26 | IAD04 | 275019-11.0 - PSDAS Cx Documentation - COLO 2 | 2025-12-26 | Closed | 2025-12-29 | BW reponded
2025-12-29 | CPQ7 | RFI-737-COLO1 ANTENNA POSITION | 2026-01-02 | Completed | 2026-01-05 | HS reviewsed and responded to
2025-12-29 | MNZ03 | RFI 1073 - Removal of GPS antenna from DAS Scope - Microsoft_MNZ03 Data Center Mana | 2025-12-31 | Completed | 2026-12-31 | BW reviewed and responded to
2025-12-30 | PHX72 | RFI #547 | 2025-12-30 | Completed | 2025-12-30 | HS reviewed and responded to - nothing for S2A
2026-01-05 | CPQ3 | Submittal 679 - 007-CPQ03-SUB-T-DAS | 2026-01-06 | Completed | 2026-01-06 | Ricardo originally sent on 12/19
2026-01-20 | EAT12 | Submittal 275019-005 - Rev. 0 has new comments (EAT12 Data Center - 6524006) | 2026-01-05 | Completed | 2026-01-05 | BW reviewed and responded to
2026-01-30 | FTY02 | 27 50 19-3 Revision 3 Cell DAS Design | 2026-02-05 | Completed | 2026-02-02 | BW reviewed and responded to
2026-01-30 | FTY02 | 27 50 19-8 Revision 1 FTY02 DAS Benchmark Study - RF Benchmark | 2026-02-05 | Completed | 2026-02-02 | BW reviewed and responded to
2026-01-29 | IAD05 | 275019-1.1 - AdminCOLO 1 - DAS Cx Documentation | 2026-02-05 | Completed | 2026-02-01 | BW reviewed and responded to
2026-01-06 | LVL07 | Submittal 608.1 - Tranche 2 & 3 PSDAS and C - 23-60861 | 2026-01-13 | Completed | 2026-01-12 | BW reviewed and responded to
2026-01-23 | LVL13 | Redesign GC RFP RFI Log for Review | 2026-01-27 | Completed | 2026-01-27 | BW reviewed and responded to
2026-01-26 | PHX14 | Submittal 275019-005-00-commercial DAS system O & M | 2026-02-02 | Completed | 2026-01-29 | BW reviewed and responded to
2026-01-14 | SAT14 | 275019-017 - DAS - Closeout Package - Phase 1 | 2026-01-21 | Completed | 2026-01-19 | Duplicate
2026-01-15 | YTO40 | RFI-602.1 Relocated ROIP Antenna Location and Rerouted Conduit | 2026-01-15 | Completed | 2026-01-15 | Follow-up: See email with Michael Rostecki from today, 1/15
2026-01-30 | AVC17 | RFI #609 GPS Antenna Junction Box | 2026-02-03 | Completed | 2026-02-01 | HS reviewed and responded to
2026-01-06 | CCO06 | RFI #743 (PS DAS Protective Barrier) | 2026-01-07 | Completed | 2026-01-07 | HS reviewed and responded to
2026-01-12 | CCO07 | Sub# 275019-005-00- Public Safety Distributed Antenna System (PS DAS) | 2026-01-13 | Completed | 2026-01-12 | HS reviewed and responded to
2026-01-23 | CCO07 | RFI 409 - Pathway Conflict and Reroute Request – Admin to COLO1 Cell 1 Backboard | 2026-01-25 | Completed | 2026-01-23 | HS reviewed and responded to
2026-01-20 | IAD05 | 275019-2.0 - AdminCOLO 1 - PSDAS Cx Documentation | 2026-01-22 | Completed | 2026-01-22 | HS reviewed and responded to
2026-01-26 | IAD05 | 275019-2.1 - AdminCOLO 1 - PSDAS Cx Documentation | 2026-02-02 | Completed | 2026-01-27 | HS reviewed and responded to
2026-01-15 | SAT15 | SAT15 - 27_50_19-017 - DAS - Closeout Package - Phase 1 - CLTCR | 2026-01-16 | Completed | 2026-01-19 | HS reviewed and responded to
2026-01-26 | SAT40 | SUM-01253 - 27 50 19 - R0 - COMMUNICATION SYSTEMS DISTRIBUTED ANTENNA SYSTEM (DAS) - As-Builts – Review | 2026-01-16 | Completed | 2026-01-16 | HS reviewed and responded to
2026-01-05 | SAT80 | RFI PH2-1184 -SAT80 Colo3 DAS-PS backbone fiber | 2026-01-07 | Completed | 2026-01-06 | HS reviewed and responded to
2026-01-06 | SAT80 | RFI PH2-1184 -SAT80 Colo3 DAS-PS backbone fiber | 2026-01-07 | Completed | 2026-01-07 | HS reviewed and responded to
2026-01-13 | SAT80 | RFI PH2-1184-R1 - SAT80 Colo3 DAS-PS backbone fiber | 2026-01-15 | Completed | 2026-01-16 | HS reviewed and responded to
2026-01-05 | YQB06 | 27 50 19 - COMMUNICATION SYSTEMS DISTRIBUTED ANTENNA SYSTEM (DAS | 2026-01-30 | Completed | 2026-01-05 | HS reviewed and responded to
2026-01-05 | YTO11 | RFI 1338 Bell Fiber Proposal | 2026-01-08 | Completed | 2026-01-06 | HS reviewed and responded to
2026-01-21 | YTO11 | ROIP Corpnet Connection - Test Results | 2026-01-21 | Completed | 2026-01-21 | HS reviewed and responded to
2026-01-12 | IAD04 | 275019-8.1 - DAS Cx Documentation - COLO 4 | 2026-01-17 | Completed | 2026-01-12 | HS reviewed and responded to
2026-01-12 | IAD04 | 275019-9.1 - PSDAS Cx Documentation - COLO 3 | 2026-01-17 | Completed | 2026-01-12 | HS reviewed and responded to
2026-01-12 | PHX72 | RFI 547 | 2026-01-12 | Completed | 2026-01-12 | HS reviewed and responded to
2026-01-12 | CCO07 | 273241-008-00 - Radio Over Ip | 2026-01-13 | Completed | 2026-01-12 | HS reviewed and responded to - not for S2A
2026-01-12 | IAD04 | RFI 682 - RoIP Fiber Master Unit | 2026-01-13 | Completed | 2026-01-12 | HS reviewed and responded to - not for S2A
2026-01-15 | MNZ03 | RFI: #1101: Public Safety DAS Headend Equipment Confirmation | 2026-01-20 | Completed | 2026-01-29 | HS reviewed and responded to.
2026-01-20 | AVC17/18 | GPS Antenna Junction Box | 2026-01-20 | Completed |  | HS reviewed and responded to. They need to resubmit.
2026-01-15 | EAT04 | 27 32 41 - RADIO OVER IP - ROIP PRODUCT DATA & SHOPS - PRODUCT DATA | 2026-01-21 | Completed | 2026-01-19 | Not for S2A
2026-01-20 | IAD05 | RFI #682 (RoIP Fiber Master Unit) | 2026-01-22 | Completed | 2026-01-22 | Not for S2A
2026-01-23 | SAT40 | SUM-02145 - 27 32 41 - R0 - Radio over IP - As Builts - Review | 2026-01-29 | Completed | 2026-01-23 | Not for S2A
2026-01-27 | YTO11 | RFI 1365 Guardhouse rPDU Clarification | 2026-01-27 | Completed | 2026-01-27 | Not for S2A
2026-01-30 | FTY02 | 27 08 20-5 Revision 1 Admin & Colo 1 - Test Reports - Package 1 | 2026-02-05 | Completed | 2026-02-03 | Not for S2A - Fiber Reports
2026-01-30 | FTY02 | 27 08 20-8 Revision 0 ADMIN & COLO 1 - Test Reports Package 2 | 2026-02-05 | Completed | 2026-02-03 | Not for S2A - Fiber Reports
2026-01-14 | CCO07 | 273241-008-00 - Radio Over Ip | 2026-01-14 | Completed | 2026-01-14 | Not in S2A scope
2026-01-14 | YQB04 | 27 08 20 - Fiber Testing for Communications Systems | 2026-01-16 | Completed | 2026-01-19 | S2A responded to, waiting for revised response
2026-01-20 | YQB04 | 27 08 20 - Fiber Testing for Communications Systems | 2026-01-22 | Completed | 2026-01-22 | Waiting for response if a further response from S2A is needed.
2026-02-01 | IAD04 | 275019-14.1 - DAS Cx Documentation - COLO 5 | 2026-02-04 | Completed | 2026-02-01 | HS reviewed and responded to
2026-02-01 | PHX13 | 273241-003-00-ROIP System Closeout PackageTest Reports | 2026-02-05 | Completed | 2026-02-04 | HS reviewed and responded to
2026-02-01 | PHX13 | 275019-009-00-Public Safety DAS Test Reports | 2026-02-05 | Completed | 2026-02-01 | HS reviewed and responded to
2026-02-01 | PHX14 | 275019-007-00-Public Safety DAS Test Reports-FOR REVIEW | 2026-02-05 | Completed | 2026-02-01 | HS reviewed and responded to
2026-02-01 | SAT40 | 27 50 19 - R1 - COMMUNICATION SYSTEMS DISTRIBUTED ANTENNA SYSTEM (DAS) - As-Builts - Review | 2026-02-06 | Completed | 2026-02-10 | HS reviewed and responded to
2026-02-02 | IAD04CA | 275019-13.1 - DAS Cx Documentation - COLO 2 | 2026-02-09 | Completed | 2026-02-03 | BW reviewed and responded to
2026-02-02 | MNZ03 | RFI 1120 - Carrier DAS Service - EFEMTO System | 2026-02-04 | Completed | 2026-02-02 | BW reviewed and responded to
2026-02-02 | PHX13 | 275019-010-00-Commercial DAS Test Reports-FOR REVIEW | 2026-02-05 | Completed | 2026-02-04 | HS reviewed and responded to
2026-02-02 | YQB01 | DA-1781-R3 27-50-19 DAS- Repeater- SDR-33-AC | 2026-02-09 | Completed | 2026-02-03 | BW reviewed and responded to
2026-02-02 | YTO40CA | RFI-660 Revision 0: DAS Pathway - Transition Points | 2026-02-05 | Completed | 2026-02-03 | HS reviewed and responded to
2026-02-03 | MNZ03 | RFI 949.1 - FOC and SOC ROIP Base Station Confirmation | 2026-02-05 | Completed | 2026-02-03 | HS reviewed and responded to
2026-02-03 | PHX14 | D3127072-Sub# 273241-003-00-ROIP Systems Closeout Package-FOR REVIEW | 2026-02-05 | Completed | 2026-02-05 | HS reviewed and responded to
2026-02-05 | AVC43 | 27 00 10-2.0 IES BIR O&M | 2026-02-12 | Completed | 2026-02-10 | BW reviewed and responded to
2026-02-05 | CCO07 | Sub# 275019-005-01-Public Safety Distributed Antenna System (PS DAS)) -FOR REVIEW-Due 02-11-2026 | 2026-02-11 | Completed | 2026-02-05 | HS reviewed and responded to
2026-02-05 | CPQ11 | RFI 1651-RFI-T-DAS | 2026-02-05 | Completed | 2026-02-10 | HS reviewed and responded to
2026-02-05 | IAD05 | RFI 413.3 - (Expedite Requested) ROIP Base Station AHU01 Circuit Overlap | 2026-02-05 | Completed | 2026-02-05 | Note for S2A
2026-02-05 | YQB06 | RFI 1127 | 2026-02-05 | Completed | 2026-02-05 | Note for S2A
2026-02-05 | YQB06 | RFI-1161 R1- DAS Modules delayed for AWS4 - Retard pour les modules DAS AWS4 | 2026-02-05 | Completed | 2026-02-05 | HS reviewed and responded to
2026-02-05 | YTO40CA | RFI-670: GPS Antenna - Coax Jumper | 2026-02-05 | Completed | 2026-02-05 | Note for S2A
2026-02-05 | YTO40CA | RFI-673: DAS Fiber Backbone Cable Type | 2026-02-09 | Completed | 2026-02-10 | HS reviewed and responded to
2026-02-09 | SAT14 | RFI RFI 1895 - P2 - Follow up to RFI 1798 - Dedicated Signal Sources | 2026-02-11 | Completed | 2026-02-10 | HS reviewed and responded to
2026-02-09 | YQB01 | RFI-1215 DAS REPEATER BAND AWS4 REQUESTED TELUS | 2026-02-11 | Completed | 2026-02-10 | HS reviewed and responded to
2026-02-09 | YTO40CA | RFI-667 Revision 1: DAS Donor Antenna Relocation | 2026-02-11 | Completed | 2026-02-10 | HS reviewed and responded to
2026-02-09 | YTO40CA | Submittal #913 Revision 0: DAS Design - Carrier Approvals | 2026-02-13 | Completed | 2026-02-10 | HS reviewed and responded to
2026-02-10 | CCO06 | Phase I: Status Update on RFI #743, PS DAS Protective Barrier | 2026-02-10 | Completed | 2026-02-10 | HS reviewed and responded to
2026-02-10 | CCO06 | Phase I: Status Update on RFI #818, Antenna Mast Junction Box | 2026-02-10 | Completed | 2026-02-10 | HS reviewed and responded to
2026-02-10 | IAD04 | 275019-13.1 - DAS Cx Documentation - COLO 2 submittal (275019-13.0) | 2026-02-05 | Completed | 2026-02-10 | BW reviewed and responded to
2026-02-10 | MNZ03 | RFI 949.1 - FOC and SOC ROIP Base Station Confirmation | 2026-02-05 | Completed | 2026-02-05 | HS reviewed and responded to
2026-02-10 | PHX72 | D3127038-Sub# 275019-003-00-Admin DAS-ROIP Backbone-FOR REVIEW | 2026-02-16 | Completed | 2026-02-13 | BW reviewed and responded to
2026-02-10 | YTO40CA | Submittal #688 Revision 1: Linkwave - Cellular Design Package | 2026-02-14 | Completed | 2026-02-10 | HS reviewed and responded to
2026-02-10 | YTO40CA | Submittal #924 Revision 0: ER1 to IDF (2x24SMF) Fiber Backbone Test Results | 2026-02-17 | Completed | 2026-02-10 | HS reviewed and responded to
2026-02-11 | LYH10 | 107696 Microsoft LYH10, Ph 01, Pkg 521-270519-REV 0 LYH10 Public Safety DAS Closeout Documentation COLO3-5 - Submittal Packages | 2026-02-18 | Completed | 2026-02-13 | BW reviewed and responded to
2026-02-11 | LYH10 | 107696 Microsoft LYH10, Ph 01, Pkg 522-275019-REV 0 LYH10 Cellular DAS Closeout Documentation COLO2-5 - Submittal Packages | 2026-02-18 | Completed | 2026-02-13 | BW reviewed and responded to
12/24/2025 | MNZ03 | RFI 689 - Guardhouse ROIP Proposal | 12/24/2025 | Closed | 2025-12-29 | BW reviewed and responded to
2026-02-12 | PHX72 | Data Center: Response to RFI #547 (ROIP and DAS Receptacle Locations ) | 2026-02-12 | Completed | 2026-02-12 | HS reviewed and responded to
2026-02-12 | PHX13 | Sub# 275019-009-01-Public Safety DAS Test Reports-FOR REVIEW-Due 02-19-2026 | 2026-02-19 | Completed | 2026-02-18 | BW reviewed and responded to
2026-02-13 | PHX72 | RFI #577: Confirmation of Available Rack Space and Head-End Equipment Expansion at PHX70 | 2026-02-16 | Completed | 2026-02-13 | HS reviewed and responded to
2026-02-17 | EAT04 | Submittal 797.0, COMMUNICATION SYSTEMS DISTRIBUTED ANTENNA SYSTEM (DAS) - PUBLIC SAFETY - PRODUCT DATA | 2026-02-26 | Completed | 2026-02-17 | HS reviewed and responded to
2026-02-17 | EAT04 | EAT04: Status Update on Submittal 796.0, COMMUNICATION SYSTEMS DISTRIBUTED ANTENNA SYSTEM (DAS) - TELECOM DAS - PRODUCT DATA | 2026-02-26 | Completed | 2026-02-17 | HS reviewed and responded to
2026-02-18 | LVL07 | Submittal 674 - COLO 4 DAS Backbone Fiber T - 23-60861 | 2026-02-25 | Completed | 2026-02-24
2026-02-18 | YTO40CA | Submittal #913 Revision 1: DAS Design - Carrier Approvals | 2026-02-25 | Completed | 2026-02-24 | HS reviewed and responded to
2026-02-18 | YQB06 | RFI-1161 R2 - DAS Modules delayed for AWS4 - Retard pour les modules DAS AWS4 | 2026-02-18 | Completed | 2026-02-18 | HS reviewed and responded
2026-02-23 | LVL07 | Submittal 677 COLO 5 DAS | ? | Completed | 2026-02-24
2026-02-20 | LYH10 | Submittal #526 Cellular Das Redlines | 2026-02-25 | Completed | 2026-02-20 | BW responded 2-20
2026-02-20 | LYH10 | Submittal #528 Public Safety DAS Redlines | 2026-02-25 | Completed | 2026-02-24
2026-02-13 | PHX14 | 275019-007-0 Public Safety Test | 2025-02-19 | Completed | 2026-02-20 | BW Responded. We were late.
2026-02-23 | LVL12 | RFI 302 | ? | Completed | 2026-02-24 | HS reviewed and responded to
2026-02-24 | YTO40CA | RFI-667 Revision 1: DAS Donor Antenna Relocation | 2026-02-24 | Completed | 2026-02-24
2026-02-23 | CPQ11 | RFI 1667 - CPQ11-RFI-T-DAS | ? | Completed | 2026-02-24 | HS reviewed and responded to
2026-02-25 | CPQ11 | Submittal 3106 - CPQ11-R-DAS - #08 - Pranchas de DAS - E-mial 04 de 04 | 2026-03-04 | Completed | 2026-03-02 | HS Reviewed and responded to
2026-02-24 | LYH10 | Ph 01, Pkg 526-27 50 19-REV 1 LYH10 - Cellular DAS Redline Drawings - Submittal Packages | 2026-03-03 | Completed | 2026-02-27 | Bram reviewed and responded to
2026-02-24 | LYH10 | Ph 01, Pkg 528-27 50 19-REV 1 LYH10 - Public Safety DAS Redline Drawings - Submittal Packages | 2026-03-03 | Completed | 2026-02-27 | Bram reviewed and responded to
2026-02-25 | LVL12 | RFI 308 | 2026-02-27 | Completed | 2026-02-25 | Not for S2A
2026-02-25 | LVL12 | RFI 307 | 2026-02-27 | Completed | 2026-02-25 | Not for S2A
2026-02-25 | LVL12 | RFI 306 | 2026-02-27 | Completed | 2026-02-25 | HS reviewed and responded to
2026-02-25 | FTY02 | Submittal #27 50 19-9.0 - DAS ROIP Equipment - O&M Manual 27 50 19 - Communication Systems Distributed Antenna System (DAS) | 2026-02-25 | Completed | 2026-02-25 | HS reviewed and responded to
2026-02-26 | CPQ3 | Submittal 010-CPQ03-SUB-T-DAS-010-CPQ03-SUB-T-DAS-R00 | 2026-03-05 | Completed | 2026-02-27 | HS reviewed and responded to.
2026-02-26 | AVC43 | Submittal 01 77 00-80.0 | 2026-03-05 | Completed | 2026-03-02 | HS Reviewed and responded to
2026-02-26 | YTO40CA | RFI-712 Revision 0 - DAS Antennas in Stairwells | 2026-03-02 | Completed | 2026-02-27 | HS reviewed and responded.
2026-02-26 | IAD05 | RFI 710 - Admin L02Colo 3 DAS Cable Reroute | 2026-03-03 | Completed | 2026-02-27 | HS reviewed and responded.
2026-03-03 | ALT06 | RFI #699, Colo 5 DAS fiber housing location. | 2026-03-05 | Completed | 2026-03-03 | HS reviewed and responded to
2026-03-02 | AVC43 | Submittal 27 08 20-23.0 | 2026-03-06 | Completed | 2026-03-04 | HS reviewed and responded to
2026-03-02 | CCO06 | RFI #833 | 2026-03-05 | Completed | 2026-03-02 | HS Reviewed and responded to
2026-03-09 | CHI11 | Design - Submittal Forwarded: 275019-001-0_617_ERRCS As Built Drawing | 2026-03-16 | Completed | 2026-03-13 | HS reviewed and responded to
2026-03-09 | CHI11 | Design - Submittal Forwarded: 273241-001-0_618_ROIP As Built Drawings | 2026-03-16 | Completed | 2026-03-13 | HS reviewed and responded to
2026-03-09 | CHI11 | Design - Submittal Forwarded: 275019-001-0_615_Commercial DAS As Builts | 2026-03-16 | Completed | 2026-03-13 | HS reviewed and responded to
2026-03-06 | CPQ11 | RFI 1667 - CPQ11-RFI-T-DAS | ? | Completed | 2026-03-10 | HS reviewed and responded to
2026-03-02 | EAT04 | Submittal 797.2, COMMUNICATION SYSTEMS DISTRIBUTED ANTENNA SYSTEM (DAS) | 2026-03-06 | Completed | 2026-03-04 | HS reviewed and responded to this submittal
2026-03-03 | IAD04 | Submittal Forwarded: 275019-9.2 - PSDAS Cx Documentation - COLO 3 | ? | Completed | 2026-03-06 | Due date says 2/19
2026-03-12 | IAD05 | RFI 710.1 - Admin L02Colo 3 DAS Cable Reroute | 2026-03-13 | Completed | 2026-03-12 | HS reviewed and responded to
2026-03-25 | IAD05 | IAD05_P18436_COR_0494_Coax_Pathway_to_ROU | 2026-02-23 | Completed | 2026-04-02 | HS reviewed and responded to
2026-03-25 | IAD05 | 017700-5.0 - Whole IFC Set Tranche 1 As-Built | 2026-03-27 | Completed | 2026-04-08 | Waiting on contract extension
2026-03-06 | IAD12-13 | RFI 0915_ROIP-R56 Certification | 2026-03-10 | Completed | 2026-03-09 | BW reviewed and responded to
2026-03-02 | IAD12-13 | 273241-3.0_ROIP - Installer Qualifications and Test Tech Cert | 2026-03-06 | Completed | 2026-03-09 | HS reviewed and responded to
2026-03-06 | LVL07 | Submittal 693 - COLO 4 & 5 CDAS As-Builts | 2026-03-13 | Completed | 2026-03-09 | BW reviewed and responded to
2026-03-06 | LVL07 | Submittal 695 - COLO 4 & 5 CDAS Commissioning Report | 2026-03-13 | Completed | 2026-03-09 | BW reviewed and responded to
2026-03-06 | LVL07 | Submittal 696 - COLO 4 & 5 CDAS Antenna Verification Test Results | 2026-03-13 | Completed | 2026-03-09 | BW reviewed and responded to
2026-03-06 | LVL07 | Submittal 698 - COLO 4 & 5 CDAS Post-Installation Walk Test Report | 2026-03-13 | Completed | 2026-03-09 | BW reviewed and responded to
2026-03-06 | LVL07 | Submittal 701 - COLO 4 & 5 CDAS COAX Test Results | 2026-03-13 | Completed | 2026-03-09 | BW reviewed and responded to
2026-03-06 | LVL07 | Submittal 702 - CDAS Warranty | 2026-03-13 | Completed | 2026-03-09 | BW reviewed and responded to
2026-03-06 | LVL07 | Submittal 694 - COLO 4 & 5 PSDAS As-Builts | 2026-03-13 | Completed | 2026-03-10 | HS reviewed and responded to
2026-03-06 | LVL07 | Submittal 697 - PSDAS Grid and DAQ Test Results | 2026-03-13 | Completed | 2026-03-10 | HS reviewed and responded to
2026-03-06 | LVL07 | Submittal 699 - COLO 4 & 5 PSDAS Antenna Verificatiion Test Results | 2026-03-13 | Completed | 2026-03-10 | HS reviewed and responded to
2026-03-06 | LVL07 | Submittal 700 - COLO 4 & 5 PSDAS COAX Test Results | 2026-03-13 | Completed | 2026-03-10 | HS reviewed and responded to
2026-03-06 | LVL07 | Submittal 703 - PSDAS Warranty | 2026-03-13 | Completed | 2026-03-10 | HS reviewed and responded to
2026-03-25 | MNZ03 | RFI 1193 - L2L3 Secure IT Storage CR | 2026-03-27 | Completed |  | Not for S2A
2026-03-24 | MNZ03 | RFI 361.4 - Cable Access in LV01-ADMIN Corridor E | 2026-03-26 | Completed |  | Not for S2A
2026-03-18 | PHX81 | Sub# 275019-003-00-RWC Documentation for DAS (For Record Submittal)-FOR REVIEW-Due 03-24-2026 | 2026-03-24 | Completed | 2026-03-18 | HS reviewed and responded to
2026-03-20 | PHX82 | PHX82 CA-D3127048-Sub# 275019-002-00-Radio Over IP Design for Colo 3 | 2026-03-23 | Closed-HS
2026-03-25 | SAT14 | P2 - 273243-002 - Team LINX - ROIP Product Data | 2026-04-01 | Completed |  | HS reviewed and responded to
2026-03-18 | SAT14 | P2 - 273243-001 - Team LINX - ROIP Shop Drawings - SD.pdf | 2026-03-25 | Completed
2026-03-16 | SAT40 | SUM-01254 - 27 50 19 - R0 - COMMUNICATION SYSTEMS DISTRIBUTED ANTENNA SYSTEM (PS DAS) - Test Reports - Review | 2026-03-20 | Completed | 2026-03-16 | HS reviewed and responded to
2026-03-16 | SAT40 | SUM-02170 - 27 50 19 - R0 - COMMUNICATION SYSTEMS DISTRIBUTED ANTENNA SYSTEM (DAS) - Equipment List - Review | 2026-03-20 | Completed | 2026-03-16 | HS reviewed and responded to
2026-03-16 | SAT40 | SUM-02171 - 27 50 19 - R0 - COMMUNICATION SYSTEMS DISTRIBUTED ANTENNA SYSTEM (DAS) - Review | 2026-03-20 | Completed | 2026-03-16 | HS reviewed and responded to
2026-03-19 | SAT81 | COLO 2-5 ROIP Shop Drawings | 2026-03-26 | Completed
2026-03-27 | YQB04 | Submittal 27 50 19-1.0: DAS SWEEP TEST REPORT. | 2026-03-27 | Completed | 2026-03-27 | HS reviewed and responded to
2026-03-13 | YQB04 | Submittal 27 50 19-2.0: DAS RAPPORT SCANNER REPORT POST INSTALL. | 2026-03-24 | Completed
2026-03-13 | YQB04 | Submittal 27 50 19-3.0: DAS RAPPORT SCANNER REPORT PRE-INSTALL. | 2026-03-24 | Completed
2026-03-23 | YQB06 | O&M Manuals - Submittals_Telecom_dépot initial | 2026-04-02 | Completed | 2026-03-31 | HS reviewed and responded to
2026-03-31 | YTO11 | Preliminary Design | 2026-04-07 | Completed | 2026-04-08 | HS reviewed and responded to
2026-03-31 | YTO11 | As-Builts | 2026-04-07 | Completed | 2026-04-08 | HS reviewed and responded to
2026-03-09 | YTO40 | Submittal #688 Revision 2: Linkwave - Cellular Design Package | ? | Completed | 2026-03-11 | HS responded to email
2026-03-16 | YTO40 | SUB 1034 - DAS Cellular- Rooftop Antenna Relocation (SUB 688 Follow up) | 2026-03-16 | Completed | 2026-03-16 | HS reviewed and responded to
2026-03-31 | YTO40 | Submittal 1036 Revision 1 - Rooftop Antenna Location | 2026-04-07 | Completed | 2026-03-31 | HS reviewed and responded to
2026-03-02 | YTO40CA | Submittal #688 Revision 2: Linkwave - Cellular Design Package | 2026-03-06 | Completed | 2026-03-02 | HS Reviewed and responded to
2026-03-12 | YTO40CA | RFI-740 ROIP Electrical Power Source | 2026-03-16 | Completed | 2026-03-12 | HS reviewed and responded to
2026-03-18 | YTO40CA | SUB 1034 - DAS Cellular- Rooftop Antenna Relocation (SUB 688 Follow up) | ? | Completed | 2026-03-18 | HS reviewed and responded to
2026-03-18 | YTO40CA | Submittal 1036 Revision 0 - Rooftop Antenna Location | 2026-03-24 | Completed | 2026-03-18 | HS reviewed and responded to
2026-04-01 | YQB04 | Submittal 27 50 19-2.1: DAS RAPPORT SCANNER REPORT POST INSTALL. | 2026-04-09 | Completed | 2026-04-01 | HS reviewed and responded
2026-04-02 | CHI11 | Submittal Forwarded: 275019-001-1_617_ERRCS As Built Drawings | 2026-04-09 | Completed | 2026-04-07
2026-04-06 | MNZ | RFI 1120.1. | ? | Completed | 2026-04-07 | formal response this week with an updated design.
2026-04-07 | MNZ03 | 282300-5.1 - O&M Submittal | 2026-04-13 | Completed | 2026-04-13 | BW reviewed and responded to
2026-04-07 | MNZ03 | 281300-2.1 - O&M | 2026-04-13 | Completed | 2026-04-13 | BW reviewed and responded to
2026-04-08 | YTO40 | Submittal 1034 Revision 1 - DAS Cellular- Rooftop Antenna Relocation (SUB 688 Follow up) | 2026-04-14 | Completed | 2026-04-16 | Not for S2A
2026-04-09 | IAD04_05 | 270820-46.0 - COLO 1 DASRoIP Fiber Test Results | 2026-04-15 | Completed | 2026-04-15 | BW reviewed and responded to
2026-04-09 | MNZ03 | 273241-9.0 - ROIP Coverage Test | 2026-04-16 | Completed | 2026-04-14 | BW reviewed and responded to
2026-04-12 | CPQ11 | Submittal 011-CPQ11-SUB-T-DAS-GEN-R01 | 2026-04-16 | Completed | 2026-04-16 | HS reviewed and responded to
2026-04-13 | CPQ7 | SUBMITTAL 743 - DASY - DAS Documentation | 2026-04-20 | Completed | 2026-04-15 | HS reviewed and responded to
2026-04-13 | CPQ3 | 011-CPQ03-SUB-T-DAS | 2026-04-20 | Completed | 2026-04-16 | HS reviewed and responded to
2026-04-13 | CPQ7 | CPQ 7 - Testing DAS | 2026-04-17 | Completed | 2026-04-16 | HS reviewed and responded to
2026-04-14 | CPQ11 | Waiting on submittal number from Ricardo | 2026-04-20 | Completed | 2026-04-20 | Duplicate
2026-04-14 | IAD04_05 | 275019-1.2 - Admin-COLO 1 - DAS Cx Documentation | 2026-04-20 | Completed | 2026-04-20 | BW reviewed and responded to
2026-04-13 | MNZ03 | RFI 266.2 - ROIP System Plug Types | 2026-04-13 | Completed | 2026-04-13 | BW reviewed and responded to
2026-03-31 | YTO11 | DAS-ROIP Asbuilts | 2026-04-13 | Completed | 2026-04-13 | HS reviewed and responded to
2026-04-14 | YTO40CA | RFI 789 Revision 0: Conduit for ROIP Base Station Antenna | 2026-04-10 | Completed | 2026-04-14 | HS reviewed and responded to
2026-04-14 | EAT05 | RFI #127, Vestibule and Mech Gallery DAS Pathway Change | 2026-04-17 | Completed | 2026-04-14 | HS reviewed and responded to
2026-04-15 | SAT14 | P2 - 017700-028 - Closeout Procedures - DAS-ROIP As-builts - CLAB | 2026-04-20 | Completed | 2026-04-16 | HS reviewed and responded to
2026-04-16 | YTO40CA | RFI #740 Revision 1: ROIP Electrical Power Source | 2026-04-20 | Completed | 2026-04-20 | HS reviewed and responded to
2026-04-17 | MNZ03 | RFI 1222 - Additional Power Requirement for SOC Transaction Drawers | 2026-04-21 | Completed | 2026-04-20 | Not for S2A
2026-04-17 | SAT14 | P2 - 017700-028 - Closeout Procedures - DAS-ROIP As-builts - CLAB | 2026-04-20 | Completed | 2026-04-20 | Duplicate
2026-04-20 | YTO40 | RFI 797 Revision 0: Fleet Map Confirmation | 2026-04-22 | Completed | 2026-04-20 | HS reviewed and responded to
2026-04-20 | YQB01 | YQB - Class A's - DAS | 2026-04-22 | Completed | 2026-04-21 | Email from Abbas Mouhaidli asking for information for the DAS system across sites
2026-04-20 | YQB04 | YQB - Class A's - DAS | 2026-04-22 | Completed | 2026-04-21 | Email from Abbas Mouhaidli asking for information for the DAS system across sites
2026-04-20 | YQB06 | YQB - Class A's - DAS | 2026-04-22 | Completed | 2026-04-21 | Email from Abbas Mouhaidli asking for information for the DAS system across sites
2026-04-20 | IAD05 | 275019-1.2 - Admin-COLO 1 - DAS Cx Documentation | 2026-04-20 | Completed | 2026-04-20 | BW reviewed and responded to
2026-04-20 | MNZ03 | Submittal: 275019-16.0 - O&M | 2026-04-20 | Completed | 2026-04-20 | BW reviewed and responded to
2026-04-20 | EAT02 | RFI 96.3: Cell DAS ROU Connectivity to EAT02 Headend Clarification | 2026-04-23 | Completed | 2026-04-21 | HS reviewed and responded to
2026-04-23 | SAT40 | STRUCT-SUM-270000-022 SAT 40 DAS PD & SD (270000-022) | 2026-04-28 | Completed | 2026-04-27 | HS reviewed and responded to
2026-04-23 | CHI05 | Submittal Forwarded: 27 50 19-106.0_DAS COLOs 2-5 - Coverage Report - Submittal:27 50 19-106.0:SNLTE | 2026-04-30 | Completed | 2026-04-27 | HS reviewed and responded to
2026-04-27 | MNZ03 | RFI 1601 - PS DAS Submittal Comments | 2026-05-01 | Completed | 2026-04-28 | BW reviewed and responded to
2026-04-28 | MNZ03 | RFI 1240 - DAS ROU Layout Confirmation | 2026-04-29 | Completed | 2026-04-28 | BW reviewed and responded to
2026-04-28 | MNZ03 | RFI 0689.3 - Confirmation of ROIP removal from Guardhouse | 2026-04-30 | Completed | 2026-04-28 | BW reviewed and responded to
2026-04-28 | MNZ03 | RFI 1120 - Carrier DAS Service | 2026-05-01 | Completed | 2026-04-28 | BW reviewed and responded to
2026-04-28 | CHI11 | Submittal Forwarded: 275019-001-2_617_ERRCS As Built Drawings | 2026-04-30 | Completed | 2026-04-30 | HS reviewed and responded to
2026-04-28 | MNZ03 | RFI 1243 - Guardhouse PNL03 & 04 Circuitry | 2026-05-01 | Completed | 2026-04-28 | Not for S2A
2026-04-27 | EAT12 | RFI 0906 - ERCES DONOR ANTENNA | 2026-04-29 | Completed | 2026-04-29 | BW reviewed and responded to
2026-04-30 | CPQ11 | Submittal 011-CPQ11-SUB-T-DAS-GEN | 2026-05-07 | Completed | 2026-05-06 | HS reviewed and responded to
2026-04-30 | IAD05 | Submittal Forwarded: 017700-6.0 - Whole IFC Set Tranche 2 As-Built | 2026-05-06 | Completed | 2026-05-06 | HS reviewed and responded to
2026-05-01 | PHX81 | Sub# 275019-004-00-Cell+PS+ROIP DAS Warranty-FOR REVIEW-Due 05-01-202 | 2026-05-01 | Completed | 2026-05-01 | HS reviewed and responded to
2026-05-04 | YQB04 | Submittal 27 00 10-07 DAS O&M | 2026-05-12 | Completed | 2026-05-04 | HS reviewed and responded to
2026-05-04 | CHI05 | 27 50 19-106.1_DAS COLOs 2-5 - Coverage Report | 2026-05-08 | Completed | 2026-05-05 | BW reviewed and responded to
2026-05-04 | CCO08 | RFI-58 RFI issued for review | 2026-05-06 | Completed | 2026-05-04 | Not S2A Scope
2026-05-04 | CCO08 | RFI-59 RFI issued for review | 2026-05-06 | Completed | 2026-05-04 | Not S2A Scope
2026-05-04 | IAD04 | 275019-14.2 - DAS Cx Documentation - COLO 5 | 2026-05-11 | Completed | 2026-05-11 | BW reviewed and responded to
2026-05-04 | IAD04 | 275019-8.2 - DAS Cx Documentation - COLO 4 | 2026-05-11 | Completed | 2026-05-11 | BW reviewed and responded to
2026-05-06 | IAD05 | 017700-6.0 - Whole IFC Set Tranche 2 As-Built | 2026-05-06 | Completed | 2026-05-11 | HS reviewed and responded to
2026-05-04 | EAT12 | RFI 0906 - NEW COMMENTS | 2026-05-08 | Completed | 2026-05-11 | BW reviewed and responded to
2026-05-06 | IAD05 | Tranche 2 DAS - PSDAS As-Built.pdf | 2026-05-06 | Completed | 2026-05-06 | HS reviewed and responded to
2026-05-06 | CPQ07 | Walk Test Report | 2026-05-06 | Completed | 2026-05-06 | HS reviewed and responded to
2026-05-06 | CPQ07 | Passive Test Report | 2026-05-06 | Completed | 2026-05-06 | HS reviewed and responded to
2026-05-06 | CPQ07 | As-Builts | 2026-05-06 | Completed | 2026-05-06 | HS reviewed and responded to
2026-05-07 | SAT40 | SUM-01266 - 27 32 41 - R0 - RADIO OVER IP-Certifications - Workforce - Review | 2026-05-14 | Completed | 2026-05-13 | Not for S2A
2026-05-07 | YTO40CA | RFI 826 Revision 0 - Guardhouse rPDU Clarification | 2026-05-11 | Completed | 2026-05-13 | Just for visibility for S2A?
2026-05-07 | SAT40 | SUM-01262 - 27 32 41 - R0 - RADIO OVER IP - Validation Reports - Review | 2026-05-14 | Completed | 2026-05-13 | Not for S2A
2026-05-07 | SAT40 | SUM-01261 - 27 32 41 - R0 - RADIO OVER IP - Bill of Material - Review | 2026-05-14 | Completed | 2026-05-13 | Not for S2A
2026-05-07 | SAT40 | SUM-01260 - 27 32 41 - R0 - RADIO OVER IP - Reports - Review | 2026-05-14 | Completed | 2026-05-13 | Not for S2A
2026-05-07 | SAT40 | SUM-01259 - 27 32 41 - R0 - RADIO OVER IP - Installed Repeater Report | 2026-05-14 | Completed | 2026-05-13 | Not for S2A
2026-05-07 | SAT40 | SUM-01256 - 27 32 41 - R0 - RADIO OVER IP - License Docs - Review | 2026-05-14 | Completed | 2026-05-13 | Not for S2A
2026-05-07 | YQB04 | Submittal 27 00 00-1.0: 27 - Closeout documents - O&M manuals - Telecom . | 2026-05-19 | Completed | 2026-05-07 | HS reviewed and responded to
2026-05-07 | YTO40CA | RFI 818 Revision 0 - DAS ROU Missing Electrical Power | 2026-05-07 | Completed | 2026-05-07 | HS Reviewed and responded to
2026-05-08 | IAD05 | 275019-3.0 - Colo 2-3-4-5 PSDAS Cx Documentation | 2026-05-12 | Completed | 2026-05-12 | HS reviewed and responded to
2026-05-08 | IAD05 | 275019-4.0 - COLO 2-3-4 - DAS Cx Documentation | 2026-05-12 | Completed | 2026-05-12 | HS reviewed and responded to
2026-05-11 | YQB06 | 01 78 23-070.1 - Training - DAS / plan de formation | 2026-05-15 | Completed | 2026-05-11 | Told to remove from list by WZMH
2026-05-11 | YQB04 | Submittal #27 00 00-1 Revision 1: 27 - Closeout documents - O&M manuals - Telecom | 2026-05-15 | Completed | 2026-05-13 | HS reviewed and responded to
2026-05-12 | IAD05 | 270820-46.1 - COLO 1 DASRoIP Fiber Test Results | 2026-05-19 | Completed | 2026-05-14
2026-05-12 | YTO40CA | Submittal 1034 Revision 1 - DAS Cellular- Rooftop Antenna Relocation (SUB 688 Follow up) | 2026-05-19 | Completed | 2026-05-12 | Looking for a “Not Reviewed / For Record Only” stamp
2026-05-12 | CPQ11 | Submittal 011-CPQ11-SUB-T-DAS-GEN R3 | 2026-05-19 | Compelted | 2026-05-20 | HS reviewed and responded to
2026-05-11 | AVC01 | Submittal 752.0, MC Dean - COLOs 4&5 PSDAS Shop Drawing | 2026-05-15 | Completed | 2026-05-14 | HS reviewed and responded to
2026-05-13 | SAT40 | SUM-02170-R1 - 27 50 19 - R1 - COMMUNICATION SYSTEMS DISTRIBUTED ANTENNA SYSTEM (DAS) - Equipment List - Review | 2026-04-22 | Completed | 2026-05-15 | HS reviewed and responded ot
2026-05-13 | SAT40 | SUM-01249 - 27 50 19 - R0 - COMMUNICATION SYSTEMS DISTRIBUTED ANTENNA SYSTEM (PS & DAS) - Benchmark Study - Review | 2026-04-27 | Completed | 2026-05-15 | HS reviewed and responded to.
2026-05-13 | SAT40 | SUM-01254-R1 - 27 50 19 - R1 - COMMUNICATION SYSTEMS DISTRIBUTED ANTENNA SYSTEM (PS DAS) - Test Reports - Review | 2026-04-27 | Completed | 2026-05-18 | HS reviewed and responded to
2026-05-14 | CHI05 | 27 50 19-107.0_PS DAS - Commissioning CoP | 2026-05-19 | Completed | 2026-05-15 | HS reviewed and responded to.
2026-05-14 | CHI05 | 27 50 19-106.2_DAS COLOs 2-5 - Coverage Report | 2026-05-19 | Completed | 2026-05-18 | HS reviewed and responded to
2026-05-14 | CHI05 | 27 32 41-105.0_Radio Over Internet Protocol - Commissioning CoP | 2026-05-19 | Completed | 2026-05-15 | HS reviewed and responded to.
2022-05-18 | CCO07CA | Sub# 275019-005-04-Public Safety Distributed Antenna System (PS DAS) | 2026-05-22 | Completed | 2026-05-18 | HS reviewed and responded to
2026-05-19 | IAD05 | 270820-45.2 - Admin DASRoIP Fiber Test Results | 2026-05-26 | Completed | 2026-05-19 | BW reviewed and responded to
2026-05-19 | YQB06 | 01 78 23-070.1 | 2026-05-26 | Completed | 2026-05-19 | BW reviewed and responded to
2026-05-19 | IAD05 | 270820-47.0 - COLO 3 DASRoIP Fiber Test Results | 2026-05-26 | Completed | 2026-05-20 | BW reviewed and responded to
2026-05-19 | YTO11 | SUB 1241 Colo 3 - DAS Design Package | 2026-05-26 | Completed | 2026-05-26 | HS reviewed and responded to
2026-05-19 | IAD05 | 270820-48.0 - COLO 4 DASRoIP Fiber Test Results | 2026-05-26 | Completed | 2026-05-20 | BW reviewed and responded to
2026-05-21 | CHI05 | 27 32 41-105.1_Radio Over Internet Protocol - Commissioning CoP | 2026-05-28 | Completed | 2028-05-26 | BW reviewed and responded to
2026-05-21 | CHI05 | Submittal Forwarded: 27 32 41-106.0_Verizon Wireless Rebroadcast Agreement - Close Out | 2026-05-28 | Completed | 2028-05-26 | BW reviewed and responded to
2026-05-21 | EAT12 | RFI 906.1 R2 | 2026-05-23 | Completed | 2026-05-22 | HW reviewed and responded to
2026-05-26 | CPQ07 | Submittal 743: DAS Documentation | 2026-05-28 | Completed | 2026-05-26 | HS reviewed and responded to
2026-05-20 | EAT12 | RFI 0914 | 2026-05-20 | Completed | 2026-05-20 | Not for S2A
2026-05-26 | IAD05 | 017700-7.0 - Whole IFC Set Tranche 3 As-Built | 2026-05-28 | Complete | 2026-05-28 | BW reviewed and responded to
2026-05-20 | CCO07 | sub# 275019-005-04-Public Safety Distributed Antenna System (PS DAS)) | 2026-05-22 | Completed | 2026-05-22 | HS reviewed and responded to
2026-05-20 | CPQ11 | Submittal 011-CPQ11-SUB-T-DAS-GEN | 2026-05-20 | Completed | 2026-05-20 | HS reviewed and responded to
2026-05-14 | CHI05 | Submittal Forwarded: 27 32 41-105.0_Radio Over Internet Protocol - Commissioning CoP | 2026-05-19 | Completed | 2026-05-19 | HS reviewed and responded to
2026-05-26 | AVC01 | Submittal 757.0, COLO 4&5 CDAS Shop Drawings | 2026-06-02 | Complete | 2026-05-28 | HS reviewed and responded to
2026-05-27 | EAT05 | RFI 152: EAT05 CELL SDR Solution Confirmation | 2026-06-01 | Complete | 2026-05-28 | HS reviewed and responded to
2021-05-18 | IAD05 | 270820-48.0 - COLO 4 DASRoIP Fiber Test Results | 2026-05-21 | Completed | 2026-05-20 | BW reviewed and responded to
2021-05-18 | IAD05 | 270820-47.0 - COLO 3 DASRoIP Fiber Test Results | 2026-05-21 | Completed | 2026-05-20 | BW reviewed and responded to
2021-05-18 | IAD05 | 270820-45.2 - Admin DASRoIP Fiber Test Results | 2026-05-21 | Completed | 2026-05-20 | BW reviewed and responded to
2026-05-29 | YQB06 | 01 78 23-070.2 Training - DAS / Documents de présentation de formation complet | 2026-06-04 | Complete | 2026-06-02 | HS reviewed and responded to
2026-06-01 | CCO07 | Response to RFI #467, DRB-09 Clarifications | 2026-06-01 | Complete | 2026-06-01 | HS reviewed and responded to
2026-06-03 | EAT13 | RFI 0303 has been assigned to you (Microsoft EAT 13 - 6525008) | 2026-06-04 | Complete | 2026-06-04 | HS reviewed and responded to
2026-06-04 | AVC17/18 | Response to RFI #709, AVC18 RoIP Sub-Contractor | 2026-06-04 | Complete | 2026-06-04 | HS reviewed and responded to
2026-06-05 | YTO11 | Submittal 1277 ROIP As Builts | 2026-06-11 | Complete | 2026-06-10 | HS reviewed and responded to
2026-06-08 | YQB04 | FULL REVIEW Submittal 01 78 23-8.0: Closeout Documents - AS-BUILT Deliverables. | 2026-09-08 | Completed | 2026-08-26 | BW Reviewed and responded to
2026-06-08 | YQB04 | INITIAL REVIEW Submittal 01 78 23-8.0: Closeout Documents - AS-BUILT Deliverables. | 2026-06-10 | Completed | 2026-08-26 | BW Reviewed and responded to
2026-06-12 | SAT15 | P2 - 273241-019 - DAS-ROIP Warranty - TeamLinx Wireless - COLO 3 | 2026-06-19 | Complete | 2026-06-12 | HS reviewed and responded to
2026-06-16 | CHI05 | Submittal Forwarded: 27 50 19-108.0_CHI05 P2 - DAS_PS_ROIP - As Builts | 2026-06-23 | Complete | 2026-06-22 | HS reviewed and responded to
2026-06-15 | YQB04 | submittal 01 77 00-1.0, Closeout Document - Warranty Booklet | 2026-06-18 | Complete | 2026-06-16 | HS reviewed and responded to
2026-06-18 | PHX72 | Sub# 273241-012-00-Admin: DAS-ROIP - Test Reports-FOR REVIEW-Due 06-18-2026 | 2026-06-18 | Complete | 2026-06-18 | HS reviewed and responded to
2026-06-18 | PHX72 | Sub# 273241-013-00-COLO 1: DAS-ROIP - Test Reports-FOR REVIEW-Due 06-18-2026 | 2026-06-18 | Complete | 2026-06-18 | HS reviewed and responded to
2026-06-18 | PHX72 | Sub# 273241-014-00-COLO 2: DAS-ROIP - Test Reports-FOR REVIEW-Due 06-18-2026 | 2026-06-18 | Complete | 2026-06-18 | HS reviewed and responded to
2026-06-18 | SAT14 | Submittal P2 - 017700-053 - Team LINX - Phase 2 DAS-ROIP As-Builts - CLAB | 2026-06-24 | Complete | 2026-06-24 | HS reviewed and responded to
2026-06-19 | CCO07 | RFI #480, 7/8" Coax Color - DRB09 - PSDAS | 2026-06-23 | Complete | 2026-06-22 | HS reviewed and responded to
2026-06-22 | IAD05 | Submittal Forwarded: 275019-5.0 - COLO 5 - DAS Cx Documentation | 2026-06-29 | Complete | 2026-07-05 | HS received files to review on 6/30
2026-06-30 | YQB04 | O&M Manuals - Submittals_Telecom_dépot initial | 2026-07-03 | complete | 2026-07-03 | HS reviewed and responded to
2026-06-30 | IAD05 | 017700-8.0 - Whole IFC Set Tranche 4 As-Built | 2026-07-01 | Complete | 2026-07-01 | HS reviewed and responded | Open
2026-07-01 | YQB06 | O&M Manuals - Submittals_Telecom_dépot initial | 2026-07-03 | Complete | 2026-07-02 | HS reviewed and responded | Complete
2026-07-06 | YTO40CA | YTO40 Action Required: RFI-890 Revision 0: RoIP Radio IDs Confirmation | 2026-07-03 | Complete | 2026-07-03 | HS reviewed and responded to
2026-07-07 | PHX81 | Sub# 270010-006-00-CELL, PUBLIC SAFETY & ROIP DAS Closeout Package (As-builts)-FOR REVIEW-Due 07-07-2026 | 2026-07-07 | Complete | 2026-07-08 | HS reviewed and responded to
2026-07-06 | PHX82 | DASROIP | 2026-07-07 | Complete | 2026-07-08 | HS reviewed and responded
2026-07-07 | EAT13 | EAT13 - Communication Systems Distributed Antenna Systems - Reports - Submittal 275019-001 | 2026-07-08 | Complete | 2026-07-08 | HS reviewed and responded to
2026-07-07 | EAT13 | DAS Design Submittal 275019-004 | 2026-07-08 | Complete | 2026-07-08 | HS reviewed and responded to
2026-07-07 | EAT13 | Submittal 275019-002 | 2026-07-08 | Complete | 2026-07-08 | HS reviewed and responded to
2026-07-02 | YQB01 | DFC-0026-R1 O&M - DAS | 2026-07-21 | Completed | 2026-07-21 | HS reviewed and responded to
2026-07-14 | AVC17/18 | #729 - CDAS Terminations | 2026-07-14 | Complete | 2026-07-15 | HS reviewed and responded to
2026-07-14 | FTY02 | DAS-ROIP O&M Manuals | 2026-07-17 | Complete | 2026-07-17 | HS reviewed and responded to
2026-07-17 | YQB04 | Submittal 01 77 00-1.1: Closeout Document - Warranty Booklet. | 2026-07-27 | Complete | 2026-07-17 | HS reviewed and responded to
2026-07-17 | YQB04 | submittal 01 77 00-1.1, Closeout Document - Warranty Booklet | 2026-07-27 | Complete | 2026-07-17 | HS reviewed and responded to
2026-07-27 | SAT15 | P2 - 273241-020 - DAS-ROIP Warranty - TeamLinx Wireless - COLO 4 - CLW | 2026-07-27 | Complete | 2026-07-27 | HS reviewed and responded to
2026-07-28 | AVC17/18 | #891 - MC Dean - AVC18 CDAS Shop Drawings | 2026-07-28 | Complete | 2026-07-28 | HS reviewed and responded to
2026-07-28 | AVC17/18 | #892 - MC Dean - AVC18 PSDAS Shop Drawings | 2026-07-28 | Complete | 2026-07-28 | HS reviewed and responded to
2026-07-29 | QRO06 | EXP Submittal #112 | 2026-07-20 | Complete | 2026-07-29 | Not for S2A
2026-07-29 | IAD12-13 | PCO 332 - Design Revision Bulletin 6 | 2026-08-04 | Complete | 2026-08-04 | Not for S2A
2026-07-17 | YQB04 | Submittal 01 77 00-1.1: Closeout Document - Warranty Booklet | 2026-07-27 | Complete | 2026-07-29 | Closed
2026-08-04 | MNZ04 | RFI #4, MNZ04 - Parking Garage Telecom Device Plan | 2026-08-07 | Complete | 2026-08-06 | HS reviewed and responded to
2026-08-05 | ATL06 | Submittal 27 50 19-9.0: Communication Systems Distributed Antenna System - O&M Manual. | 2026-08-11 | Completed | 2026-08-05 | BW reviewed and responded to
2026-08-07 | PHX82 | RFI 612 | 2026-08-11 | Completed | 2026-08-07 | HS reviewed and responded to
2026-08-11 | YTO40CA | Submittal 1408 Revision 0: - Cellular DAS Design Package - 27 50 19 - COMMUNICATION SYSTEMS DAS | 2026-08-17 | Completed | 2026-08-17 | HS Reviewed and responded to
2026-08-13 | YTO11 | submittal 1329.0, DAS Cellular Coax Cable Test Results - YTO11 Package 1 (Admin, COLO 1, COLO 2) | 2026-08-20 | Completed | 2026-08-20 | HS reviewed and responded to
2026-08-13 | YTO11 | submittal 1330.0, ROIP Coax Cable Testing Results - YTO11 Package 1 (Admin, COLO 1 and COLO 2) | 2026-08-20 | Completed | 2026-08-20 | HS reviewed and responded to
2026-08-14 | AVC17/18 | RFI #747, AVC18 Exterior RoIP Antenna | 2026-08-19 | Completed | 2026-08-19 | Not for S2A
2026-08-14 | EAT13 | RFI 0370 - DAS Wall mount FCR Fiber housing conflict | 2026-08-19 | Completed | 2026-08-19 | BW Reviewed and responsed to
2026-08-14 | EAT13 | Public Safety DAS (ERRCS) - Shop Drawings | 2026-08-19 | Complete | 2026-08-17 | BW reviewed and responded to
2026-08-18 | AVC17/18 | Submittal 915.0: MC Dean - AVC18 CDAS Product Data | 2026-08-25 | Completed | 2026-08-26 | BW Reviewed and responded to
2026-08-18 | AVC17/18 | Submittal 916.0: MC Dean - AVC18 PSDAS Product Data | 2026-08-25 | Completed | 2026-08-26 | BW Reviewed and responded to
2026-08-18 | YQB01 | YQB01-Substantial completion certificate **URGENT** | 2026-08-18 | Completed | 2026-08-18 | HS Reviewed and responded to
2026-08-18 | YQB01 | Site Reports | 2026-08-18 | Completed | 2026-08-18 | HS Reviewed and responded to
2026-08-18 | AVC17/18 | Submittal #918 AVC18 PSDAS Test Plans | 2026-08-25 | Completed | 2026-08-26 | BW Reviewed and responded to
2026-08-18 | AVC17/18 | Submittal #917 AVC18 CDAS Test Plans | 2026-08-25 | Completed | 2026-08-26 | BW Reviewed and responded to
2026-08-19 | ATL06 | ATL06 – 27-50-19-9, O&M Manuals | 2026-08-20 | Completed | 2026-08-20 | HS Reviewed and responded to
2026-08-26 | MNZ03 | 273241-10.1 - RoIP - Sample Warranty - Microsoft_MNZ03 Data Center Manassas_VA-Project - Submittal:273241-10.1:UEbBu | 2026-08-26 | Completed | 2026-08-26 | BW Reviewed and responded to
2026-08-26 | MNZ03 | 275019-17.0 - DAS - Sample Warranty - Microsoft_MNZ03 Data Center Manassas_VA-Project - Submittal:275019-17.0 :UEbBu | 2026-08-26 | Completed | 2026-08-26 | BW Reviewed and responded to
2026-08-28 | EAT13 | EAT13 RFI - 0370 | 2026-09-01 | Completed | 2026-09-01 | HS reviewed and responded to
2026-09-02 | YQB06 | O&M Manuals - Submittals_Telecom_dépot initial | 2026-09-02 | Completed | 2026-09-02 | Not for S2A
2026-09-02 | YQB06 | As-Builts_Telecom_TELECON | 2026-09-06 | Completed | 2026-09-06 | Not for S2A
2026-09-02 | YQB04 | Closeout Document - Warranty Booklet | 2026-09-04 | Completed | 2026-09-04 | HS reviewed and responded to
2026-09-04 | YTO11 | Submittal 1353.0: DAS & ROIP Closeout Package | 2026-09-14 | Open
2026-09-10 | SAT15 | P2 - 273241-021 - DAS-ROIP Warranty - TeamLinx Wireless - COLO 5 - CLW.pdf | 2026-09-17 | Open
2026-09-09 | EAT13 | RFI 0395 - COLO 1 DAS Equip. Location Clarification | 2026-09-11 | Open

## Billing Issue Log
Added | Priority Level | Completed Date | Project | Proposal | Contract | Balance | Invoiced to Date | Status
|  |  | MNZ03 | 78748 | 78748 | 99.16% | 73548 | 5200 | 0 | 78088 | 2026-05-16 | 660 |  | 23381 | 54707
|  |  | LVL12-14DS | 140124 | 140124 | 99.31% | 140124 | 0 | 0 | 139151 | 2026-05-17 | 973 | BILLED COMPLETE | 127801 | 11350
|  |  | QRO02 | 97200 | 38546 | 102.5% | 38546 | 0 | 0 | 39498 | 2025-11-25 | -952 | Must notify contractor when billings hit 80% of contract. | 37001 | 2497
|  |  | CPQ04DS | 96792 | 45460 | 92.88% | 40860 | 4600 | 0 | 42222 | 2026-05-25 | 3238 |  | 41314 | 908
|  |  | FTY02 | 67106 | 33553 | 89.3% | 33553 | 0 | 0 | 29964 | 2026-04-30 | 3589 |  | 7037 | 22927
|  |  | IAD04_05CA | 116306 | 116306 | 85.38% | 116306 | 0 | 2830.49 | 99305.49 | 2026-05-13 | 17000.51 |  | 45173 | 54132.49
|  |  | LVL07 | 77045.5 | 79645.5 | 88.64% | 77045.5 | 2600 | 0 | 70597 | 2026-05-26 | 9048.5 |  | 38590 | 32007
|  |  | PHX15 | 83536 | 41768 | 92.39% | 41768 | 0 | 0 | 38590 | 2025-04-16 | 3178 |  | 38590 | 0

## Travel-Project Close Out
Project | Date Added | Contacts | Notes | Completed? | Expense Report Captured? | Scheduled Date | Travel Confirmed | Punchwalk date | Testing Reports Received | Closeout Materials Received? | Site walk report status | Expenses Submitted for Invoicing
AVC17/18 |  | Todd Wescott | 4/15: On weekly touch base call T Wescott indicated he'd be reaching out to all disciplines to coordinate site visits within the next couple of weeks. |  |  | 8/20-8/23/25 | BW - Yes
IAD04 | [5 empty] | 6/3-6/4 | BW |  |  |  |  | Y
LVL06 |  |  | BIR
LVL08 |  |  | BW walkthrough with Verizon. Out all day Thursday, out in the morning on Friday. |  |  | 8/20-8/21 | BW
LVL10 |  |  | BIR
LYH10 |  |  | 7/9/25: HS asked to have added to site visit list. |  |  | 8/27-8/29 | BW- Yes
PHX13 |  | remington.Clausen@skanska.com - on site Candy.Glass@jacobs.com - Jacobs On-site CM | Emailed Remington/Candy S2A contacts 4/10/25
PHX14 |  | michael.Cheung@skanska.com - on site coordinator Candy.Glass@jacobs.com - Jacobs On-site CM | Michael advised 4/10/25 - target week of 5/25 |  |  | 2025-05-30 | HS
PHX14-COLO3 |  | michael.Cheung@skanska.com - on site coordinator Candy.Glass@jacobs.com - Jacobs On-site CM | TENTATIVE - 7/24: Email received from Michael Cheung requesting to pick date/time for punch walk visit. S2A advised not going. |  |  | 2025-08-19 | BW
PHX71 |  | karen.walker@jacobs.com - Jacobs On-site CM | Per K Walker 4/15: turned over to client.
PHX72 |  | karen.walker@jacobs.com - Jacobs On-site CM | Per K Walker 4/15/25: PHX72 is at erecting steel framing and roofing, along with constructing infrastructure. Will keep us posted on walk thru sched - still aways out.
PHX81 |  | Brian.Gailfus@jacobs.com | 8/26: Test data is being reviewed. |  |  | TBD
QRO02 |  |  | BURNS |  |  | 4/22-4/24 - HS | Yes
QRO06 |  |  | BURNS
SAT14 |  |  | LINX
SAT15 |  |  | LINX |  |  | 6/9-6/12 | BW - Yes |  |  |  |  | Y
SAT80 |  |  | LINX
IAD |  |  | DWS
ATL06 |  |  | 6/16/25: BW called out may need visit soon.
YQB's |  |  | 6/16/25: HW called out may be coming up.
MNZ03 | 2025-10-15 |  | 10/14/25: BW called out may need visit soon. TBD.
PHX13 | 2025-11-06 |  | 11/6: Need two hours at each site | x
PHX14 | 2025-11-06 |  | 11/6: Need two hours at each site | x
CHI11 | 2025-11-06 |  | 10/31: Sultan Katrangi: S2A will do a single visit when the system is tested. ($5,200 for expenses)
YTO11 | 2025-11-06 |  | 11/07: Punchwalk will be first week of December - Scope is Package 1, but COLO1+Admin only, COLO2 will come later, at which we’ll be setting up another punch walk.
CPQs |  |  | 11/10-11/15
ATL06 | Early Dec |  | 11/10: The DAS Cx team will be on site the week of 11/17/2025.

## Centerline-OpenPO
Open PO | 75000 | Estimates to Date | 48250 | Balance: | 26750 |  | Invoiced Amount | 48400
Project | Scope |  |  | Estimate | Approved | Delivered | Inv Amt | Balance | Invoiced to A/E | Month Billed | Centerline Invoice # | S2A Invoice# | Notes
EAT03CA | Colo 4 did not pass AHJ test |  |  | 400 | Y | Y | 400 | 0 | Y | 2025-06-01 | 176399
EAT12CA | Moving PS Antenna |  |  | 900 | Y | Y | 900 | 0 | Y | 2025-07-01 | 178716
IAD04DRB10 | IAD04 HeadEnd Mod |  |  | 650 | Y | Y | 650 | 0 | Y | 2025-07-01 | 180730
IAD11DRB | IAD11 HeadEnd Mod |  |  | 650 | Y | Y | 650 | 0 | Y | 2025-07-01 | 180730 |  | IAD11DCN08
LVL09 | update ibwaves - reflect new dedicated signal source in LVL08 |  |  | 350 | Y | Y | 350 | 0 | Y | 2025-07-01 | 181437
LVL10 | update ibwaves - reflect new dedicated signal source in LVL08 |  |  | 350 | Y | Y | 350 | 0 | Y | 2025-07-01 | 181437
MNZ03DRB04 | MNZ03 HeadEnd Mod |  |  | 650 | Y | Y | 650 | 0 | Y | 2025-06-01 | 176399
SJC02Revision | Substation ROiP Revisions - to be delivered in IFP/IFC package |  |  | 650 | Y | Y | 650 | 0 | Y | 2025-09-01 | 187434 |  | Needs to be billed to A/E after IFP issuance 8/14
YTO40DCN03 | run test without shell space antennas |  |  | 350 | Y | Y | 350 | 0 | Y | 2025-07-01 | 180730
CCO08 | PSDAS Update - City of Palmetto code changes - design+CAD |  |  | 2100 | Y | Y | 2100 | 0 | Y | 2025-07-01 | 184126 |  | CADS delivered 7/17 ($1,300) - ibWaves delivered 7/10 - S2A to review and then CL will start CADS
PHX82 | 7/1 Title and Date CAD updates |  |  | 375 | Y | Y | 375 | 0 | Y | 2025-08-01 | 184126
CYS17 | 7/11 Title and Date CAD (PDF?) updates |  |  | 375 | Y | Y | 375 | 0 | Y | 2025-07-01 | 184126 |  | sheet index, too, and CADs. client to be billed with July cycle.
IAD11 | Update cads based on updated ibWaves |  |  | 1500 | Y | Y | 1500 | 0 | Y | 2025-07-01 | 187432 |  | delievered 7/16
PHX72 | Descope DRB08 IFC package 7/10 |  |  | 375 | Y | Y | 375 | 0 | Y | 2025-06-01 | 184126
LVL | Consolidation of LVL 9,10,11 data centers into LVL08 file |  |  | 2000 | Y | Y | 2000 | 0 | Y | 2025-08-01 | 187433 |  | bill to LVL10CA contract.
PHX72 | Reverse of PHX72 descope done in May |  |  | 700 | Y | Y | 700 | 0 | Y | 2025-08-01 | 212237 |  | 11/03: Only partially billed. Original estimate was $2,350 for both PHX72 and 82. 8/28: Estimate $2,350 CADS only
PHX82 | Reverse of PHX82 descope done in May (CANCELED) |  |  | 0 | Y | N | 0 | 0 | Y | - | - |  | 1/26: Work canceled and never billed by CL11/07: CL work back on but reduced, similar to work done for PHX72 11/03: CL work canceled. 8/28: Estimate $2,350 CADS only
CPQ11 | add in colo 4 to ibwaves |  |  | 2600 | Y | Y | 2600 | 0 | Y | 2025-09-01 |  |  | 10/1: Contract added to Notora Open PO contract folder
YTO11 | CAD Updates |  |  | 500 | ? | Y | 650 | -150 | Y | 2025-10-01 | 201632 |  | Had a note about a $500 obligation to Stephen. Perhaps the original estimate amount was changed?
CCO08 | CAD Reprint? |  |  | 650 | Y | Y | 650 | 0 | Y | 2025-10-01 | 203713 |  | This was a NTP (BW has email)
CCO08 | PSDAS design that includes the Admin area and all 5 COLOs |  |  | 1300 | Y | Y | 1300 | 0 | Y | 2025-10-01 | 201629
LVL13 | Design Revision + CADs |  |  | 2800 | Y | Y | 2800 | 0 | Y | 2025-11-01 | 212233
IAD12 | Design Revision |  |  | 1300 | Y | Y | 1300 | 0 | Y | 2025-12-01 | 228337 |  | $1,300 for DES REV per site, $3,150 for CADs per site
IAD13 | Design Revision |  |  | 1300 | Y | Y | 1300 | 0 | Y | 2025-12-01 | 228340 |  | $1,300 for DES REV per site, $3,150 for CADs per site
IAD12 | CADS |  |  | 3150 | Y | Y | 3150 | 0 | Y | 2026-01-01 | 232308 |  | $1,300 for DES REV per site, $3,150 for CADs per site
IAD13 | CADS |  |  | 3150 | Y | Y | 3150 | 0 | Y | 2026-01-01 | 232309 |  | $1,300 for DES REV per site, $3,150 for CADs per site
CLT04 | Design Revision |  |  | 1300 | Y | Y | 1300 | 1300 | Y | 2025-12-01 | 228331 | 2733 | Each project would be $1,300 for the revision and $1,500 for the CAD updates
CLT04 | CADS |  |  | 1500 | Y | Y | 1500 | 1500 | Y | 2025-12-01 | 228332 | 2733 | Each project would be $1,300 for the revision and $1,500 for the CAD updates
CLT10 | Design Revision |  |  | 1300 | Y | Y | 1300 | 1300 | Y | 2025-12-01 | 228334 | 2734 | Each project would be $1,300 for the revision and $1,500 for the CAD updates
CLT010 | CADS |  |  | 1500 | Y | Y | 1500 | 1500 | Y | 2026-03-01 | 236332 | 2830 | Each project would be $1,300 for the revision and $1,500 for the CAD updates
CLT17 | Design Revision |  |  | 1300 | Y | Y | 1300 | 1300 | Y | 2025-12-01 | 228335 | 2735 | Each project would be $1,300 for the revision and $1,500 for the CAD updates
CLT17 | CADS |  |  | 1500 | Y | Y | 1500 | 1500 | Y | 2026-02-26 | 233523 | 2784 | Each project would be $1,300 for the revision and $1,500 for the CAD updates
CCO07 | Design Revision |  |  | 1000 | Y | Y | 1000 | 1000 | Y | 2026-03-26 | 240955 | 2845
LYH10 | Verizon iBwave Package |  |  | 700 | Y | Y | 700 | 700 | Y | 2026-04-26 | 243440 | 2871
QRO01 | Design |  |  | 700 | Y | Y | 700 | 700 | Y | 2026-04-26 | 243444 | 2899
MNZ03 | Update design |  |  | 700 | Y | Y | 700 | 700 | Y | 2026-04-26 | 243061 | 2855
FTY02 | iBwave Design Package |  |  | 700 | Y | Y | 700 | 700 | Y | 2026-03-26 | 239646 | 2839
QRO01 | CAD set |  |  | 1125 | Y | Y | 1125 | 1125 | Y | 2026-05-17 | 247235 | 2839
CCO08 | Design Revision |  |  | 1300 | Y | Y | 1300 | 1300 | Y | 2026-04-01 | 243982 | 2864
LVL10/11 | Contractor Questions |  |  | 700 | Y | Y | 700 | 700 | N |  | 241963
LVL10/11 | OEM Research and Revision |  |  | 625 | Y | Y | 625 | 625 | N |  | 247697
LVL10/11 | Public Safety Design Revision |  |  | 1300 | Y | Y | 1300 | 1300 | N |  | 241963
CCO08 | CAD Updates |  |  | 1125 | Y | Y | 1125 | 1125 | Y | 2026-05-01 | 245268 | 2864
CHI11 | CAD Revisions |  |  | 750 | Y | Y | 750 | 750 | N |  | 248558
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Additional $25k Open PO initiated 10/8
Note on A6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Kristen Pearcy I think this project name was entered wrong. It's IAD04 in the "Scope" and also IAD04 Design Revision on Jenna's list.
Note on G6: Kristen Pearcy: estimate was originally $675
Note on G7: Kristen Pearcy: estimate was originally $675

## Program Management
Week | Day | Task | January | February | March | April | May | June | July | August | Sep | October | November | December
Week 1 | Monday | Open Items
Prepare Invoice Template & Time Tracker Doc For Each Project
| Tuesday | Open Items
3:00 PM - Weekly Touch Base Meeting
| Wednesday | Open Items
Update Project List and Create New Timesheets
| Thursday | Open Items
| Friday | Open Items
YQB Invoices Due
Week 2 | Monday | Open Items
| Tuesday | Open Items
3:00 PM - Weekly Touch Base Meeting
| Wednesday | Open Items
| Thursday | Open Items
Notora Invoice Reconciliation
| Friday | Open Items
Week 3 | Monday | Open Items
Log Into MSFT Account
| Tuesday | Open Items
3:00 PM - Weekly Touch Base Meeting
| Wednesday | Open Items
| Thursday | Open Items
| Friday | Open Items
All Invoicing Due Date
Week 4 | Monday | Open Items
Reconcile Received to Date Amount in Billing Spreadsheet
Send out A/R Reports
Archive Important Docs
| Tuesday | Open Items
3:00 PM - Weekly Touch Base Meeting
| Wednesday | Open Items
| Thursday | Open Items
Notora Invoice Reconciliation
| Friday | Open Items
Process Timesheets
Monthly Billing/Contracts/AR Status Meeting with Harold
Week 5 | Monday | Open Items
| Tuesday | Open Items
3:00 PM - Weekly Touch Base Meeting
Last Day of the Month - Prepare Monthly Billing Spreadsheet

## CA (hidden)
Active | NAME | LOCATION | A/E | Phase (Design or CA) | AE-PM Name | AE-PM Contact | S2 PM | 50% IFR - Notora | 50% IFR - AE | 100% IFR - Notora | 100% IFR - AE | IFP - Notora | IFP - AE | IFC | Project Start | Submittal | Substantial Completion | Completion | Commissioning | Action Item Needed | Comments
1 | ATL06 | ATLANTA, GA | Highland Associates | CA | Hector Hernandez | hhernandez@ha-ny.com | Catherine Hannon | Complete | Complete | Complete | Complete | Complete | Complete | Complete
2 | AVC01 | SOUTH HILL, VA | Highland Associates | CA | Hector Hernandez | hhernandez@ha-ny.com | Nick Mayor | Complete | Complete | Complete | Complete | Complete | Complete | Complete
3 | AVC09 | SOUTH HILL, VA | Highland Associates | CA | Hector Hernandez | hhernandez@ha-ny.com | Nick Mayor | Complete | Complete | Complete | Complete | Complete | Complete | Complete
4 | BN49-CA | BOYDTON, VA | Syska | CA | Daniel Jones |  | Nick Mayor | Complete | Complete | Complete | Complete | Complete | Complete | Complete
5 | BN80-CA | BOYDTON, VA | Syska | CA | Daniel Jones |  | Nick Mayor | Complete | Complete | Complete | Complete | Complete | Complete | Complete
6 | CCO06 | BOYDTON, VA | Highland Associates | CA | Hector Hernandez | hhernandez@ha-ny.com | Catherine Hannon | Complete | Complete | Complete | Complete | Complete | Complete | Complete
7 | CHI05 | CHICAGO | Syska | CA | Andrew Krebs | akrebs@syska.com | Harold Sheley | Complete | Complete | Complete | Complete | Complete | Complete | Complete
8 | CHI10 | CHICAGO | Syska | CA | Andrew Krebs | akrebs@syska.com | Harold Sheley | Complete | Complete | Complete | Complete | Complete | Complete | Complete
9 | CHI11 | CHICAGO | Syska | CA | Andrew Krebs | akrebs@syska.com | Harold Sheley | Complete | Complete | Complete | Complete | Complete | Complete | Complete
10 | CHI22 | CHICAGO | Syska | CA | Clint Moreno |  | Harold Sheley | Complete | Complete | Complete | Complete | Complete | Complete | Complete
11 | CO09 | QUINCY, WA | CPG | CA | Mark Heinrich |  | Harold Sheley | Complete | Complete | Complete | Complete | Complete | Complete | Complete
12 | CYS13 |  | Jacobs | CA | Kristin McCue | Kristin.McCue@jacobs.com | Harold Sheley | Complete | Complete | Complete | Complete | Complete | Complete | Complete
13 | CYS17 |  | Turner
13 | EAT02 | WEANATCHEE, WA | ESD | CA | Chad Mendell | cmendell@esdglobal.com | Harold Sheley | Complete | Complete | Complete | Complete | Complete | Complete | Complete
14 | EAT03 | WEANATCHEE, WA | ESD | CA | Chad Mendell | cmendell@esdglobal.com | John Clark | Complete | Complete | Complete | Complete | Complete | Complete | Complete
15 | FTY01 | GEORGIA | Morrison Hershfield | CA | Lee Percy | LPercy@morrisonhershfield.com | Catherine Hannon | Complete | Complete | Complete | Complete | Complete | Complete | Complete | 2023-02-02 | [5 empty] | Colo 1 is scheduled to start being built around 6/5/2023
16 | IAD02/03 | LEESBURG, VA | Syska | CA | Christopher Lay | clay@syska.com | Catherine Hannon | Complete | Complete | Complete | Complete | Complete | Complete | Complete | [6 empty] | POC is Marty Angeli
17 | IAD04 | LEESBURG, VA | Syska | CA | Christopher Lay | clay@syska.com | Catherine Hannon | Complete | Complete | Complete | Complete | Complete | Complete | Complete
18 | IAD05 | LEESBURG, VA | Syska | CA | Christopher Lay | clay@syska.com | Catherine Hannon | Complete | Complete | Complete | Complete | Complete | Complete | Complete
19 | IAD11 | LEESBURG, VA | Syska | CA | Christopher Lay | clay@syska.com | Catherine Hannon | Complete | Complete | Complete | Complete | Complete | Complete | Complete
20 | LVL01-03 | BOYDTON, VA | K-WMCE | CA | Ryan Sims |  | Harold Sheley | Complete | Complete | Complete | Complete | Complete | Complete | Complete
21 | LVL04 | BOYDTON, VA | Swanson Rink | CA | Ryan Sims | RSims@swansonrink.com | Catherine Hannon | Complete | Complete | Complete | Complete | Complete | Complete | Complete
22 | LVL05 | BOYDTON, VA | Swanson Rink | CA | Ryan Sims | RSims@swansonrink.com | Catherine Hannon | Complete | Complete | Complete | Complete | Complete | Complete | Complete
23 | LVL08 | BOYDTON, VA | Swanson Rink | CA | Ryan Sims | RSims@swansonrink.com | Harold Sheley | Complete | Complete | Complete | Complete | Complete | Complete | Complete
24 | LVL09 | BOYDTON, VA | Swanson Rink | CA | Ryan Sims | RSims@swansonrink.com | Catherine Hannon | Complete | Complete | Complete | Complete | Complete | Complete | Complete
25 | LVL10 | BOYDTON, VA | Swanson Rink | CA | Ryan Sims | RSims@swansonrink.com | Catherine Hannon | Complete | Complete | Complete | Complete | Complete | Complete | Complete
26 | PHX11 | PHOENIX, AZ | Jacobs | CA | Howard Way | Howard.Way@jacobs.com | John Clark | Complete | Complete | Complete | Complete | Complete | Complete | Complete
27 | PHX12 | PHOENIX, AZ | Jacobs | CA | Blake Giles | Blake.Giles@jacobs.com | John Clark | Complete | Complete | Complete | Complete | Complete | Complete | Complete
28 | PHX13 | PHOENIX, AZ | Jacobs | CA | Blake Giles | Blake.Giles@jacobs.com | John Clark | Complete | Complete | Complete | Complete | Complete | Complete | Complete
29 | PHX14 | PHOENIX, AZ | Jacobs | CA | Blake Giles | Blake.Giles@jacobs.com | John Clark | Complete | Complete | Complete | Complete | Complete | Complete | Complete
30 | QRO1 | MEXICO CITY, MEXICO | Burns & McDonnell | CA | Charlie Ussery | cmussery@burnsmcd.com | John Clark | Complete | Complete | Complete | Complete | Complete | Complete | Complete
31 | QRO2 | MEXICO CITY, MEXICO | Burns & McDonnell | CA | Charlie Ussery | cmussery@burnsmcd.com | John Clark | Complete | Complete | Complete | Complete | Complete | Complete | Complete
32 | QRO6 | MEXICO CITY, MEXICO | Burns & McDonnell | CA | Charlie Ussery | cmussery@burnsmcd.com | John Clark | Complete | Complete | Complete | Complete | Complete | Complete | Complete
33 | SAT12 | SAN ANTONIO, TX | K-WMCE | CA | James Ball |  | Harold Sheley | Complete | Complete | Complete | Complete | Complete | Complete | Complete
34 | SAT14 | SAN ANTONIO, TX | Page Southerland Page Inc. | CA | Lauren Alexander | lalexander@pagethink.com | Nick Mayor | Complete | Complete | Complete | Complete | Complete | Complete | Complete
35 | SCL03 | LIMA, CHILE | Black and Veatch | CA | Shilpa A. Maganti | MagantiSA@bv.com | John Clark | Complete | Complete | Complete | Complete | Complete | Complete | Complete
36 | SCL05 | LIMA, CHILE | Black and Veatch | CA | Shilpa A. Maganti | MagantiSA@bv.com | John Clark | Complete | Complete | Complete | Complete | Complete | Complete | Complete
KP Adds:
A | SAT80-81 |  | Pagethink | CA | David Lamutt | dlamutt@pagethink.com
A | LYH10 |  | Highland Associates | CA | Jason Guzman | jguzman@ha-ny.com
A | PHX12 | PHOENIX, AZ | Jacobs | CA | Blake Giles | Blake.Giles@jacobs.com | John Clark
A | DSM40 |  | ? | CA | ? | ? | ?
A | YBQ01 |  | WZMH | CA | kyurkovska@wzmh.com
A | YQB04 |  | WZMH | CA | kyurkovska@wzmh.com
A | YQB06 |  | WZMH | CA | kyurkovska@wzmh.com
A | YQB11 |  | WZMH | CA | kyurkovska@wzmh.com
A | CYS13CA |  | Jacobs | CA | Kristin McCue | [9 empty] | 2024-08-01 | [5 empty] | CYS13 Record Drawings (Admin and COLOs 1 through 5) to close out the project. The latest federated model is available in Navisworks and all disciplines should have final approved redlines (with the exception of Mechanical, where we are tracking down some last info). Please begin working on Record Drawings with the idea to submit as early as possible in August (date TBC once we receive final Mech info). The client has asked us to submit these as soon as possible, so we’re being asked to advance what we can.

## Sheet1
Phase | Task | Subtask | Due Date | Microsoft (Progress) | Andrews (Progress) | S2 Advisors (Progress) | DAS Contractor (Progress)
PAPERWORK | Contract Organization | Draft contracts | 2025-08-30 | [Progress ▼] | [Progress ▼] | [Progress ▼] | [Progress ▼]
PAPERWORK | Purchase Orders | Submit to finance | 2025-09-05 | [Progress ▼] | [Progress ▼] | [Progress ▼] | [Progress ▼]
CONSTRUCTION | Site Prep | Clear land | 2025-09-20 | [Progress ▼] | [Progress ▼] | [Progress ▼] | [Progress ▼]
CONSTRUCTION | Electrical Install | Install conduits | 2025-10-01 | [Progress ▼] | [Progress ▼] | [Progress ▼] | [Progress ▼]